{"text_format":"1","workbook":"xlsx","n_sheets":3,"sheets":["Feuil1","Feuil2","Feuil3"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Feuil1","index":0,"n_rows":83,"n_cols":8,"rows_kept":83,"cut":false,"hidden":false,"merged":[]}
["Date début planifié","Date fin planifiée","Statut système","Date lancem. théor.","Date lancem. réelle","Date fin confirm.",null,"totaux"]
["2015-04-07","2015-04-09","TCLO CONF LIVR CCRP ARCO ECRT MMEf RIMP","2015-04-07","2015-04-09","2015-04-09",null,{"$f":"SUMPRODUCT(--(E2:E83>D2:D83))","v":55}]
["2015-04-07","2015-04-09","TCLO IMPR CONF LIVR CCRP ARCO ECRT MMEf*","2015-04-07","2015-04-08","2015-04-13",null,{"$f":"SUMPRODUCT(--(E2:E83<D2:D83))","v":9}]
["2015-04-08","2015-04-10","TCLO CONF LIVR CCRP ARCO ECRT MMEf RIMP","2015-04-08","2015-04-10","2015-04-13",null,{"$f":"SUMPRODUCT(--(E3:E84<D3:D84))","v":9}]
["2015-04-08","2015-04-10","TCLO CONF LIVR CCRP ARCO ECRT MMEf RIMP","2015-04-08","2015-04-13","2015-04-13"]
["2015-04-08","2015-04-10","TCLO CONF LIVR CCRP ARCO ECRT MMEf RIMP","2015-04-08","2015-04-13","2015-04-13"]
["2015-04-08","2015-04-10","TCLO CONF LIVR CCRP ARCO ECRT MMEf RIMP","2015-04-08","2015-04-09","2015-04-13"]
["2015-04-09","2015-04-13","TCLO CONF LIVR CCRP ARCO ECRT MMEf RIMP","2015-04-09","2015-04-13","2015-04-13"]
["2015-04-09","2015-04-13","TCLO CONF LIVR CCRP ARCO ECRT MMEf RIMP","2015-04-09","2015-04-13","2015-04-14"]
["2015-04-09","2015-04-13","TCLO CCRP ARCO ECRT RIMP","2015-04-09"]
["2015-04-09","2015-04-13","TCLO CONF LIVR CCRP ARCO ECRT MMEf RIMP","2015-04-09","2015-04-15","2015-04-15"]
["2015-04-09","2015-04-13","TCLO CONF LIVR CCRP ARCO ECRT MMEf RIMP","2015-04-09","2015-04-15","2015-04-24"]
["2015-04-09","2015-04-13","TCLO ARTM CONF LIVR CCRP ECRT MMEf RIMP","2015-04-09","2015-04-15","2015-04-22"]
["2015-04-10","2015-04-14","TCLO ARTM CONF LIVR CCRP ECRT MMEf RIMP","2015-04-10","2015-04-16","2015-04-22"]
["2015-04-10","2015-04-14","TCLO ARTM CONF LIVR CCRP ECRT MMEf RIMP","2015-04-10","2015-04-16","2015-04-22"]
["2015-04-10","2015-04-14","TCLO ARTM CONF LIVR CCRP ECRT MMEf RIMP","2015-04-10","2015-04-21","2015-04-22"]
["2015-04-10","2015-04-14","TCLO ARTM CONF LIVR CCRP ECRT MMEf RIMP","2015-04-10","2015-04-16","2015-04-17"]
["2015-04-10","2015-04-14","TCLO ARTM CONF LIVR CCRP ECRT MMEf RIMP","2015-04-10","2015-04-17","2015-04-20"]
["2015-04-13","2015-04-15","TCLO ARTM CONF LIVR CCRP ECRT MMEf RIMP","2015-04-13","2015-04-17","2015-04-22"]
["2015-04-13","2015-04-15","TCLO CONF LIVR CCRP ARCO ECRT MMEf RIMP","2015-04-13","2015-04-17","2015-04-24"]
["2015-04-13","2015-04-15","TCLO ARTM CONF LIVR CCRP ECRT MMEf RIMP","2015-04-13","2015-04-17","2015-04-17"]
["2015-04-14","2015-04-16","TCLO CONF LIVR CCRP ARCO ECRT MMEf RIMP","2015-04-14","2015-04-14","2015-04-14"]
["2015-04-14","2015-04-16","TCLO CONF LIVR CCRP ARCO ECRT MMEf RIMP","2015-04-14","2015-04-14","2015-04-14"]
["2015-04-14","2015-04-16","TCLO CONF LIVR CCRP ARCO ECRT MMEf RIMP","2015-04-14","2015-04-14","2015-04-15"]
["2015-04-14","2015-04-15","TCLO CONF LIVR CCRP ARCO ECRT MMEf RIMP","2015-04-14","2015-04-14","2015-04-14"]
["2015-04-14","2015-04-16","TCLO ARTM CONF LIVR CCRP ECRT MMEf RIMP","2015-04-14","2015-04-16","2015-04-17"]
["2015-04-14","2015-04-16","TCLO ARTM CONF LIVR CCRP ECRT MMEf RIMP","2015-04-14","2015-04-16","2015-04-17"]
["2015-04-14","2015-04-16","TCLO CONF LIVR CCRP ARCO ECRT MMEf RIMP","2015-04-14","2015-04-15","2015-04-24"]
["2015-04-14","2015-04-16","TCLO ARTM CONF LIVR CCRP ECRT MMEf RIMP","2015-04-14","2015-04-20","2015-04-20"]
["2015-04-14","2015-04-16","TCLO IMPR CONF LIVR CCRP ARCO ECRT MMEf*","2015-04-14","2015-04-22","2015-04-23"]
["2015-04-15","2015-04-16","TCLO CONF LIVR CCRP ARCO CNA  ECRT MMEf*","2015-04-15","2015-04-15","2015-04-15"]
["2015-04-15","2015-04-17","TCLO ARTM CONF LIVR CCRP ECRT MMEf RIMP","2015-04-15","2015-04-17","2015-04-22"]
["2015-04-15","2015-04-17","TCLO ARTM CONF LIVR CCRP ECRT MMEf RIMP","2015-04-15","2015-04-17","2015-04-20"]
["2015-04-15","2015-04-17","TCLO CONF LIVR CCRP ARCO ECRT MMEf RIMP","2015-04-15","2015-04-22","2015-04-27"]
["2015-04-15","2015-04-17","TCLO CONF LIVR CCRP ARCO ECRT MMEf RIMP","2015-04-15","2015-04-22","2015-04-22"]
["2015-04-15","2015-04-17","TCLO ARTM CONF LIVR CCRP ECRT MMEf RIMP","2015-04-15","2015-04-21","2015-04-21"]
["2015-04-15","2015-04-17","TCLO ARTM CONF LIVR CCRP ECRT MMEf RIMP","2015-04-15","2015-04-21","2015-04-21"]
["2015-04-15","2015-04-17","TCLO IMPR CONF LIVR CCRP ARCO ECRT MMEf*","2015-04-15","2015-04-15","2015-04-22"]
["2015-04-15","2015-04-17","TCLO CONF LIVR CCRP ARCO ECRT MMEf RIMP","2015-04-15","2015-04-15","2015-04-22"]
["2015-04-15","2015-04-17","TCLO CONF LIVR CCRP ARCO ECRT MMEf RIMP","2015-04-15","2015-04-15","2015-04-22"]
["2015-04-15","2015-04-17","TCLO CONF LIVR CCRP ARCO ECRT MMEf RIMP","2015-04-15","2015-04-15","2015-04-22"]
["2015-04-15","2015-04-17","TCLO CONF LIVR CCRP ARCO ECRT MMEf RIMP","2015-04-15","2015-04-15","2015-04-22"]
["2015-04-15","2015-04-17","TCLO CONF LIVR CCRP ARCO ECRT MMEf RIMP","2015-04-15","2015-04-15","2015-04-22"]
["2015-04-15","2015-04-17","TCLO CONF LIVR CCRP ARCO ECRT MMEf RIMP","2015-04-15","2015-04-15","2015-04-22"]
["2015-04-15","2015-04-17","TCLO CONF LIVR CCRP ARCO ECRT MMEf RIMP","2015-04-15","2015-04-15","2015-04-17"]
["2015-04-15","2015-04-17","TCLO ARTM CONF LIVR CCRP ECRT MMEf RIMP","2015-04-15","2015-04-15","2015-04-17"]
["2015-04-16","2015-04-20","TCLO CONF LIVR CCRP ARCO ECRT MMEf RIMP","2015-04-16","2015-04-17","2015-04-17"]
["2015-04-17","2015-04-20","TCLO CONF LIVR CCRP ARCO ECRT MMEf RIMP","2015-04-17","2015-04-16","2015-04-17"]
["2015-04-20","2015-04-22","TCLO CONF LIVR CCRP ARCO ECRT MMEf RIMP","2015-04-20","2015-04-27","2015-05-05"]
["2015-04-20","2015-04-22","TCLO IMPR CONF LIVR CCRP ARCO ECRT MMEf*","2015-04-20","2015-04-22","2015-04-30"]
["2015-04-20","2015-04-22","TCLO ARTM CONF LIVR CCRP ECRT MMEf RIMP","2015-04-20","2015-04-21","2015-04-22"]
["2015-04-20","2015-04-22","TCLO CONF LIVR CCRP ARCO ECRT MMEf RIMP","2015-04-20","2015-04-21","2015-04-21"]
["2015-04-20","2015-04-22","TCLO ARTM CONF LIVR CCRP ECRT MMEf RIMP","2015-04-20","2015-04-21","2015-04-21"]
["2015-04-21","2015-04-23","TCLO CONF LIVR CCRP ARCO ECRT MMEf RIMP","2015-04-21","2015-04-22","2015-04-23"]
["2015-04-21","2015-04-23","TCLO CONF LIVR CCRP ARCO ECRT MMEf RIMP","2015-04-21","2015-04-27","2015-05-05"]
["2015-04-21","2015-04-23","TCLO CONF LIVR CCRP ARCO ECRT MMEf RIMP","2015-04-21","2015-04-22","2015-04-22"]
["2015-04-21","2015-04-23","TCLO CONF LIVR CCRP ARCO ECRT MMEf RIMP","2015-04-21","2015-04-21","2015-04-22"]
["2015-04-21","2015-04-23","TCLO CONF LIVR CCRP ARCO ECRT MMEf RIMP","2015-04-21","2015-04-27","2015-05-05"]
["2015-04-21","2015-04-23","TCLO CONF LIVR CCRP ARCO ECRT MMEf RIMP","2015-04-21","2015-04-27","2015-04-28"]
["2015-04-21","2015-04-23","TCLO CONF LIVR CCRP ARCO ECRT MMEf RIMP","2015-04-21","2015-04-23","2015-04-24"]
["2015-04-21","2015-04-23","TCLO CONF LIVR CCRP ARCO ECRT MMEf RIMP","2015-04-21","2015-04-23","2015-04-23"]
["2015-04-21","2015-04-23","TCLO CONF LIVR CCRP ARCO ECRT MMEf RIMP","2015-04-21","2015-04-24","2015-04-24"]
["2015-04-21","2015-04-23","TCLO CONF LIVR CCRP ARCO ECRT MMEf RIMP","2015-04-21","2015-04-27","2015-04-28"]
["2015-04-23","2015-04-27","TCLO CONF LIVR CCRP ARCO ECRT MMEf RIMP","2015-04-23","2015-04-24","2015-04-24"]
["2015-04-23","2015-04-27","TCLO CONF LIVR CCRP ARCO ECRT MMEf RIMP","2015-04-23","2015-04-24","2015-04-24"]
["2015-04-23","2015-04-27","TCLO CONF LIVR CCRP ARCO ECRT MMEf RIMP","2015-04-23","2015-04-28","2015-04-29"]
["2015-04-23","2015-04-27","TCLO CONF LIVR CCRP ARCO ECRT MMEf RIMP","2015-04-23","2015-04-24","2015-04-24"]
["2015-04-23","2015-04-27","TCLO CONF LIVR CCRP ARCO ECRT MMEf RIMP","2015-04-23","2015-04-24","2015-04-24"]
["2015-04-27","2015-04-29","TCLO CONF LIVR CCRP ARCO ECRT MMEf RIMP","2015-04-27","2015-04-27","2015-05-05"]
["2015-04-27","2015-04-29","TCLO CONF LIVR CCRP ARCO ECRT MMEf RIMP","2015-04-27","2015-04-28","2015-04-28"]
["2015-04-27","2015-04-29","TCLO CONF LIVR CCRP ARCO ECRT MMEf RIMP","2015-04-27","2015-04-28","2015-04-28"]
["2015-04-27","2015-04-29","TCLO CONF LIVR CCRP ARCO ECRT MMEf RIMP","2015-04-27","2015-04-28","2015-04-28"]
["2015-04-28","2015-04-30","TCLO CONF LIVR CCRP ARCO ECRT MMEf RIMP","2015-04-28","2015-04-29","2015-04-30"]
["2015-04-28","2015-04-30","TCLO CONF LIVR CCRP ARCO ECRT MMEf RIMP","2015-04-28","2015-04-28","2015-04-28"]
["2015-04-29","2015-05-04","TCLO CONF LIVR CCRP ARCO ECRT MMEf RIMP","2015-04-29","2015-04-30","2015-05-04"]
["2015-04-30","2015-05-05","TCLO CONF LIVR CCRP ARCO ECRT MMEf RIMP","2015-04-30","2015-04-29","2015-04-30"]
["2015-04-30","2015-05-05","TCLO CONF LIVR CCRP ARCO ECRT MMEf RIMP","2015-04-30","2015-04-28","2015-04-30"]
["2015-04-30","2015-05-05","TCLO CONF LIVR CCRP ARCO ECRT MMEf RIMP","2015-04-30","2015-04-28","2015-04-30"]
["2015-04-30","2015-05-05","TCLO CONF LIVR CCRP ARCO ECRT MMEf RIMP","2015-04-30","2015-04-28","2015-04-29"]
["2015-04-30","2015-05-05","TCLO CONF LIVR CCRP ARCO ECRT MMEf RIMP","2015-04-30","2015-04-30","2015-04-30"]
["2015-04-30","2015-05-05","TCLO CONF LIVR CCRP ARCO ECRT MMEf RIMP","2015-04-30","2015-04-29","2015-04-30"]
["2015-04-30","2015-05-05","TCLO CONF LIVR CCRP ARCO ECRT MMEf RIMP","2015-04-30","2015-04-29","2015-04-30"]
["2015-04-30","2015-05-05","TCLO CONF LIVR CCRP ARCO ECRT MMEf RIMP","2015-04-30","2015-04-29","2015-04-30"]

{"sheet":"Feuil2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"Feuil3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}