{"text_format":"1","workbook":"xlsx","n_sheets":4,"sheets":["Entrée de charge","Livraison","TB","KPI"],"not_rendered":{"charts":3,"images":3,"macros":1,"external_links":1,"defined_names":1,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Entrée de charge","index":0,"n_rows":1313,"n_cols":21,"rows_kept":1313,"cut":false,"hidden":false,"merged":[]}
["Reference","Opportunité","Date \nCréation","ENTITE","CONSULTANT","user name","CLE","DESCRIPTION","Date \nCible","Status","Date fin de plan d'action","Justificatif du retard","Date de livraison","Timming","Date du retour","Retour \nQualité","QG1","QG2","Description2","Colonne3","Colonne4"]
["MCSH-8068-L-95751","EST - MCSI","2015-08-17T15:15:00","EACC",null,null,"OF_PIECE","X7RR : AVE (X7RR) : Officialisation d'une pièce","2015-12-19","Annulé",null,null,"2016-01-04","Retard",null,"ACCEPTE_DEFAUT"]
["MCSH-7486-L-80787","EST - MCSI","2014-12-16T17:49:07","ELPS",null,"qsdfgqsdfg","DO_BE_CESARE","X74E : SIRENE_LIN_SSCAS,RUPTEUR_CAPOT,MUS2 : Livraison BE Cesare pour TI","2016-01-05","En cours",null,null,"2016-01-05","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-6641-L-80519","EST - MCSI","2014-12-15T22:43:47","ELPS",null,"qsdfgqsdfg","RT_BILAN_HW","P1UO : FEUX_AR : Revue Technique de bilan de conception électronique","2016-01-05","En cours",null,null,"2016-01-05","OTD","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-8125-L-98427","EST - MCSI","2015-10-22T14:15:17","EACC",null,null,"OF_PIECE","X7RR : JDV (CHINE - Rec X7RR) : Officialisation d'une pièce - Reconduction vis fixation","2016-01-21","En cours",null,null,"2016-01-05","OTD","2016-02-02","FTR"]
["MCSH-8064-L-95713","EST - MCSI","2015-08-14T13:43:01","ELAC",null,null,"DO_CCA_TOPHW","R83E,X74E : SONDE : Fiche CCA phase 2 (conception)","2016-02-04","En cours",null,null,"2016-01-05","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-4192-L-99384","AIT - MCSI","2015-11-20T16:39:19","CSAC",null,null,"OF_PIECE","X81_Chine : CVM (X81_Chine) : Reconduction CVM niv2 D5.1 pour PRSEL1","2016-01-29","En cours",null,null,"2016-01-06","OTD","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-7400-L-89706","EST - MCSI","2015-04-22T16:58:35","ELPS",null,null,"DO_FC_VRS","X74E : FEU_AV : Fiches composants pour SDP VRS","2015-12-05","En cours","2015-12-31","Retard fournisseur","2016-01-07","Retard",null,"ACCEPTE_DEFAUT"]
["MCSH-6555-L-65104","EST - MCSI","2014-02-21T14:30:28","ELAC",null,null,"OF_PIECE","P1MO : GRPE_CLIM : Officialisation 2D & 3D fournisseur en RANG 2 stade OCM","2016-01-08","Attente GO",null,null,"2016-01-07","OTD","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-6555-L-97962","EST - MCSI","2015-10-12T15:23:07","ELAC",null,null,"OF_PIECE","P1MO : GRPE_CLIM : Officialisation faisceau 2D/3D FNR (Dil EE) RFTA Monozone ","2016-01-08","Attente GO",null,null,"2016-01-07","OTD","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-6555-L-98485","EST - MCSI","2015-10-26T14:36:10","ELAC",null,null,"OF_PIECE","MODULE_HAB05 : GRPE_CLIM : Officialisation sonde enso version CH/RF","2016-01-08","Attente GO",null,null,"2016-01-07","OTD","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-6555-L-98661","EST - MCSI","2015-11-05T10:41:51","ELAC",null,null,"OF_PIECE","P1MO : GRPE_CLIM : Officialisation faisceau 2D/3D FNR (Dil EE) RFTA bizone","2016-01-08","Attente GO",null,null,"2016-01-07","OTD","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-3042-L-76721","AIT - MCSI","2014-10-09T15:40:24","CSAC",null,null,"DO_CESARE","K0 : RADAR GÉN3 (K0) : Livraison BE CESARE D5.1b pour EL2 (TMC 16 selon FSP 13_2)","2016-01-29","Attente GO",null,null,"2016-01-07","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7480-L-92353","AIT - MCSI","2015-06-08T12:00:35","CSAC",null,null,"OF_DOTE","B751_3_4_MV : RADAR GÉN3 (B753_4  MV) : Pour Stade OCM VRS1 (C4)","2016-05-20","Attente GO",null,null,"2016-01-07","OTD","2016-01-12","FTR"]
["MCSH-3934-L-76595","EST - MCSI","2014-10-08T11:54:21","ELAC",null,null,"DO_DIVERS","MODULE_HAB06,P8X,X74E : PULSEUR_AR : Mise en nomenclature des référence APV","2015-12-14","Attente GO",null,null,"2016-01-08","Retard",null,"ACCEPTE_DEFAUT"]
["MCSH-5751-L-80303","EST - MCSI","2014-12-15T16:46:12","ELAC",null,null,"DO_NOMEN_APV","P8X : TDC AR : Mise en nomenclature des référence APV","2015-12-14","Attente GO",null,null,"2016-01-08","Retard","2016-06-10","FTR"]
["MCSH-5885-L-64857","AIT - MCSI","2014-02-21T10:01:02","CSAC",null,null,"OF_CAL","B618 : AAS,SAM : Officialisation d'une calibration","2016-01-08","Attente GO",null,null,"2016-01-08","OTD","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-7486-L-80752","EST - MCSI","2014-12-16T17:48:27","ELPS",null,null,"DO_CDCI_BILAN","X74E : SIRENE_LIN_SSCAS,RUPTEUR_CAPOT,MUS2 : CDCI validé pour VRS1\r\nRupteur capot","2016-01-08","Attente GO",null,null,"2016-01-08","OTD","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-4158-L-84954","EST - MCSI","2015-02-19T17:37:21","EEMS",null,null,"SYN_A3_QUAL_DOM","_RITUELS : _RITUEL_EEMS_Qualité : IQC_METIER_A3 Pole-SVAC","2016-01-08","Attente GO",null,null,"2016-01-08","OTD","2016-08-17","FTR"]
["MCSH-4158-L-84955","EST - MCSI","2015-02-19T17:37:21","EEMS",null,null,"SYN_A3_QUAL_ORG","_RITUELS : _RITUEL_EEMS_Qualité : IQC_ORGANE_A3-EVAV","2016-01-08","Attente GO",null,null,"2016-01-08","OTD","2016-08-17","FTR"]
["MCSH-4158-L-84956","EST - MCSI","2015-02-19T17:37:21","EEMS",null,null,"SYN_A3_QUAL_DOM","_RITUELS : _RITUEL_EEMS_Qualité : IQC_METIER_A3 Pole-EACH","2016-01-08","Attente GO",null,null,"2016-01-08","OTD","2016-08-17","FTR"]
["MCSH-4158-L-84957","EST - MCSI","2015-02-19T17:37:21","EEMS",null,null,"SYN_A3_QUAL_ORG","_RITUELS : _RITUEL_EEMS_Qualité : IQC_ORGANE_A3-LVE/LVEAP","2016-01-08","Attente GO",null,null,"2016-01-08","OTD","2016-08-17","FTR"]
["MCSH-4158-L-84958","EST - MCSI","2015-02-19T17:37:21","EEMS",null,null,"SYN_A3_QUAL_ORG","_RITUELS : _RITUEL_EEMS_Qualité : IQC_ORGANE_A3-RETROS","2016-01-08","Attente GO",null,null,"2016-01-08","OTD","2016-08-17","FTR"]
["MCSH-4158-L-84959","EST - MCSI","2015-02-19T17:37:21","EEMS",null,null,"SYN_A3_QUAL_ORG","_RITUELS : _RITUEL_EEMS_Qualité : IQC_ORGANE_A3-MEAP","2016-01-08","Attente GO",null,null,"2016-01-08","OTD","2016-08-17","FTR"]
["MCSH-4158-L-88662","EST - MCSI","2015-04-16T13:23:32","EEMS",null,null,"SYN_A3_QUAL_ORG","_RITUELS : _RITUEL_EEMS_Qualité : IQC_ORGANE_A3-SERRURES","2016-01-08","Attente GO",null,null,"2016-01-08","OTD","2016-08-17","FTR"]
["MCSH-4158-L-88663","EST - MCSI","2015-04-16T13:23:32","EEMS",null,null,"SYN_A3_QUAL_ORG","_RITUELS : _RITUEL_EEMS_Qualité : IQC_ORGANE_A3-SIEGES","2016-01-08","Attente GO",null,null,"2016-01-08","OTD","2016-01-08","FTR"]
["MCSH-8072-L-95755","EST - MCSI","2015-08-17T15:28:00","EACC",null,null,"OF_PIECE","C84_Chine : ANTENNE_BACKUP (C84) : Officialisation d'une pièce","2015-12-11","Attente GO",null,null,"2016-01-10","Retard","2016-07-25","NOT FTR"]
["MCSH-3745-L-101254","AIT - MCSI","2016-01-08T03:17:11","SWES",null,null,"SYN_DC_ORGANE","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_SR-Push FSE Marquardt","2016-01-11","Attente GO",null,null,"2016-01-11","DR","2016-04-01","FTR"]
["MCSH-7773-L-95784","EST - MCSI","2015-08-18T16:03:41","EACC",null,null,"OF_PIECE","X74E : ANTENNE_BACKUP (X74E) : Reconduction de l'antenne passive sur X74€\r\npour la DAD","2016-01-22","Attente GO",null,null,"2016-01-11","OTD","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-7480-L-92351","AIT - MCSI","2015-06-08T12:00:35","CSAC",null,null,"LIV_SW_CAL","B751_3_4_MV : RADAR GÉN3 (B753_4  MV) : Calibration pour Mulet livrée par le FNR","2016-01-12","Attente GO",null,null,"2016-01-12","OTD","2016-01-15","FTR"]
["MCSH-7480-L-100333","AIT - MCSI","2015-12-14T11:22:09","CSAC",null,null,"LIV_SW_CAL","B751_3_4_MV : RADAR GÉN3 (B753_4  MV) : Calibration pour Mulet livrée par le FNR","2016-01-12","Attente GO",null,null,"2016-01-12","DR","2016-01-15","FTR"]
["MCSH-7480-L-92350","AIT - MCSI","2015-06-08T12:00:35","CSAC",null,null,"DO_CESARE","B751_3_4_MV : RADAR GÉN3 (B753_4  MV) : Livraison BEs mulets ADAS.","2016-01-13","Attente GO",null,null,"2016-01-12","OTD","2016-01-15","FTR"]
["MCSH-7480-L-100332","AIT - MCSI","2015-12-14T11:22:09","CSAC",null,null,"DO_CESARE","B751_3_4_MV : RADAR GÉN3 (B753_4  MV) : Livraison BEs pour Mulets ADAS","2016-01-13","Attente GO",null,null,"2016-01-12","DR","2016-01-15","FTR"]
["MCSH-3132-L-35383","EST - MCSI","2013-01-21T11:41:45","ELPS",null,null,"DO_ETAT_ACCEPT","K0 : CAPT_ALARME (Adapt K0) : Réunion tripartite de détermination de l'état d'acceptation pour VRS2","2016-01-13","Attente GO","2015-06-22","Retard fournisseur","2016-01-13","OTD","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-7467-L-81030","EST - MCSI","2014-12-18T22:18:01","ELPS",null,null,"DO_CDCI_BILAN","R82E,R83E : SIRENE_LIN_SSCAS,RUPTEUR_CAPOT,MUS2 : CDCI validé pour VRS1","2016-01-10","Attente GO","2016-01-14","Retard fournisseur","2016-01-14","OTD","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-5736-L-80429","EST - MCSI","2014-12-15T22:07:48","ELPS",null,null,"DO_EDS","X81_Chine : PROJ : Renseigner OPHELIE EDS Tool pour le stade consolidé","2015-02-20","Attente GO","2016-01-15","Retard fournisseur","2016-01-15","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-8071-L-95754","EST - MCSI","2015-08-17T15:25:18","EACC",null,null,"OF_PIECE","C84_Chine : AVE (C84_Chine,C84_Export) : Officialisation d'une pièce","2015-12-30","Attente GO","2015-12-30","Retard fournisseur","2016-01-15","Retard",null,"ACCEPTE_DEFAUT"]
["MCSH-7415-L-96988","EST - MCSI","2015-09-22T08:49:59","ELAC",null,null,"RT_CALIB","X74E : GRPE_CLIM : RT robustesse calibration BCC ->CAL 1 pour TI/IVP","2016-01-15","Attente GO",null,null,"2016-01-15","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7415-L-96994","EST - MCSI","2015-09-22T08:49:59","ELAC",null,null,"LIV_PARAM_GRP_RG_1","X74E : GRPE_CLIM : Réception du Fichier paramètrage  ADTH validé pour calibration 1 TI/IVP","2016-01-15","Attente GO",null,null,"2016-01-15","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-3745-L-101145","AIT - MCSI","2016-01-08T12:01:50","SWES",null,null,"SYN_A3_QUAL_ORG","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_A3-COM2008 Premium Valeo","2016-01-15","Attente GO",null,null,"2016-01-15","DR","2016-04-01","FTR"]
["MCSH-3745-L-101232","AIT - MCSI","2016-01-08T01:45:38","SWES",null,null,"SYN_DC_ORGANE","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_SR-Volant équipé","2016-01-15","Attente GO",null,null,"2016-01-15","DR","2016-04-01","FTR"]
["MCSH-2937-L-100798","EST - MCSI","2015-12-23T15:02:10","ELPS",null,null,"SYN_ALTIS ","K0 : PROJ : Synthèse ALTIS\r\n(FT n°7055770 : le niveau d'éclairement des feux de position correspond toujours à des feux diurnes)","2016-01-15","Attente GO",null,null,"2016-01-15","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-7154-L-99459","AIT - MCSI","2015-11-23T16:06:19","CSAC",null,null,"OF_PIECE","P1UO : CVM (P1UO) : Reconduction CVM niv2 D5.1","2015-12-20","Attente GO",null,null,"2016-01-18","NDR","2016-01-21","FTR"]
["MCSH-7154-L-99460","AIT - MCSI","2015-11-23T16:06:35","CSAC",null,null,"OF_PIECE","P1UO : CVM (P1UO) : Reconduction CVM niv1 D5.1","2015-12-20","Attente GO",null,null,"2016-01-18","NDR","2016-01-21","FTR"]
["MCSH-3540-L-93849","AIT - MCSI","2015-07-02T14:35:38","CSAC",null,null,"DO_CESARE","P8X,P8_Europe_VS_Fenetre : RADAR GÉN3 (P8X) : Livraison BE CESARE EL0","2016-01-18","Attente GO",null,null,"2016-01-18","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-8161-L-99303","AIT - MCSI - SMEG","2015-11-19T11:38:36","IDEV",null,null,"OF_PIECE","_F09/2016 : SMEG+_I_V2 : Reconduction  HW pour le projet A9x AEE2010 sur PRS7 en 6.3","2016-01-18","Attente GO",null,null,"2016-01-18","OTD","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-7821-L-99485","EST - MCSI","2015-11-24T14:32:29","EACC",null,null,"OF_PIECE","A88 : AVE (A88) : Officialisation d'une pièce","2016-01-18","Attente GO","2016-01-15",null,"2016-01-18","OTD","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-3540-L-99835","AIT - MCSI","2015-12-03T04:50:14","CSAC",null,null,"DO_CESARE","P8X,P8_Europe_VS_Fenetre : RADAR GÉN3 (P8X) : Livraison BE D5.1b CESARE VRS2 DV (TMC 4 selon FSP V14)","2016-01-18","Attente GO",null,null,"2016-01-18","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7363-L-96377","AIT - MCSI","2015-09-07T18:43:32","CSAC",null,null,"RT_CDCI","C84_Chine : CVM (C84) : Revue technique de CDCI","2016-01-29","Attente GO",null,null,"2016-01-18","OTD","2016-08-23","RR"]
["MCSH-7482-L-99868","EST - MCSI","2015-12-07T14:00:11","ELPS",null,null,"OF_PIECE","K9 : SIRENE_LIN_SSCAS,RUPTEUR_CAPOT,MUS2 : Officialisation d'une pièce fixation SIRENE K9","2016-02-26","Attente GO",null,null,"2016-01-18","OTD","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-8055-L-95234","EST - MCSI","2015-07-28T18:28:54","EACC",null,null,"OF_PIECE","A88_Chine : JDV (CHINE-A88) : Rec Antivol Méca + vis fixation","2016-03-04","Attente GO",null,null,"2016-01-18","OTD","2016-06-23","ACCEPTE_DEFAUT"]
["MCSH-3745-L-101203","AIT - MCSI","2016-01-08T01:20:45","SWES",null,null,"SYN_A3_QUAL_ORG","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_A3-COM2008 Premium KOSTAL","2016-01-20","Attente GO",null,null,"2016-01-20","DR","2016-04-01","FTR"]
["MCSH-3745-L-101215","AIT - MCSI","2016-01-08T01:21:42","SWES",null,null,"SYN_A3_QUAL_ORG","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_A3-COM2008 KOSTAL","2016-01-20","Attente GO",null,null,"2016-01-20","DR","2016-04-01","FTR"]
["MCSH-3540-L-99492","AIT - MCSI","2015-11-25T09:54:47","CSAC",null,null,"OF_PIECE","P8X : RADAR GÉN3 (P8X) : REC : BOITIER ELECTRONIQUE RADAR AV ASS D5.2 : OCM","2016-01-22","Attente GO",null,null,"2016-01-20","OTD","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-4199-L-99495","AIT - MCSI","2015-11-25T10:43:46","CSAC",null,null,"OF_PIECE","X81_Chine : RADAR GÉN3 (X81C) : Reconduction Assemblé Radar Gen 3 sur X81_CH : OCM D5.2","2016-01-22","Attente GO",null,null,"2016-01-20","OTD","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-7147-L-99500","AIT - MCSI","2015-11-25T11:56:25","CSAC",null,null,"OF_PIECE","G95_PH2 : RADAR GÉN3 (G95Ph2) : REC BOITIER ELECTRONIQUE RADAR AV ASS D5.2","2016-01-22","Attente GO",null,null,"2016-01-20","OTD","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-6825-L-99734","AIT - MCSI","2015-12-01T01:15:29","CSAC",null,null,"OF_PIECE","B78_mi_vie : RADAR GÉN3 (B78 MV) : REC : BOITIER ELECTRONIQUE RADAR AV ASS D5.2","2016-01-22","Attente GO",null,null,"2016-01-20","OTD","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-7482-L-80704","EST - MCSI","2014-12-16T15:24:57","ELPS",null,null,"DO_CDCI_BILAN","K9 : SIRENE_LIN_SSCAS,RUPTEUR_CAPOT,MUS2 : CDCI validé pour DFNu","2016-01-25","Attente GO",null,null,"2016-01-21","OTD","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-3540-L-93850","AIT - MCSI","2015-07-02T14:35:38","CSAC",null,null,"OF_CAL","P8X : RADAR GÉN3 (P8X) : CAL EL0","2016-01-25","Attente GO",null,null,"2016-01-21","OTD","2016-01-27","FTR"]
["MCSH-5893-L-99412","AIT - MCSI","2015-11-23T10:37:11","CSAC",null,null,"OF_PIECE","P1MO : CVM (A88,P1MO) : Reconduction CVM niv1 D5.1 pour PPV (VRSUT)","2016-01-29","Attente GO",null,null,"2016-01-21","OTD","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-5893-L-99413","AIT - MCSI","2015-11-23T10:37:24","CSAC",null,null,"OF_PIECE","P1MO : CVM (A88,P1MO) : Reconduction CVM VAEB SW4 pour PPV (VRSUT)","2016-01-29","Attente GO",null,null,"2016-01-21","OTD","2016-01-21","FTR"]
["MCSH-5893-L-99414","AIT - MCSI","2015-11-23T10:37:42","CSAC",null,null,"OF_PIECE","A88 : CVM (A88,P1MO) : Reconduction CVM niv1 D5.1 pour PPV (VRSUT)","2016-01-29","Attente GO",null,null,"2016-01-21","OTD","2016-01-21","FTR"]
["MCSH-5893-L-99415","AIT - MCSI","2015-11-23T10:38:55","CSAC",null,null,"OF_PIECE","A88 : CVM (A88,P1MO) : Reconduction CVM VAEB SW4 pour PPV (VRSUT)","2016-01-29","Attente GO",null,null,"2016-01-21","OTD","2016-01-21","FTR"]
["MCSH-6604-L-99503","AIT - MCSI","2015-11-25T01:28:27","CSAC",null,null,"OF_PIECE","P1UO : RADAR GÉN3 (P1UO) : REC : BOITIER ELECTRONIQUE RADAR AV ASS D5.2","2016-01-29","Attente GO",null,null,"2016-01-21","OTD","2016-09-08","RBA"]
["MCSH-6555-L-77411","EST - MCSI","2014-10-17T11:26:52","ELAC",null,null,"RT_CALIB","A88,MODULE_HAB05,P1MO : GRPE_CLIM : RT robustesse calibration BCC ->CAL 3 pour VRS1/VRSDV","2016-01-22","Attente GO","2015-12-04","Retard fournisseur","2016-01-22","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-3042-L-99423","AIT - MCSI","2015-11-23T12:48:26","CSAC",null,null,"OF_PIECE","K0 : RADAR GÉN3 (K0) : REC Assemblé Radar Gen 3 D5.2 sur K0 : OCM","2016-01-22","Attente GO",null,null,"2016-01-22","OTD","2016-01-27","FTR"]
["MCSH-3745-L-101257","AIT - MCSI","2016-01-08T03:21:08","SWES",null,null,"SYN_DC_ORGANE","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_SR-CSV RADIO et RVV/LVV VALEO","2016-01-22","Attente GO",null,null,"2016-01-22","DR","2016-04-01","FTR"]
["MCSH-3745-L-101506","AIT - MCSI","2016-01-13T08:00:14","SWES",null,null,"SYN_DC_ORGANE","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_SR-CSV RADIO et RVV/LVV DELPHI","2016-01-22","Attente GO",null,null,"2016-01-22","DR","2016-04-01","FTR"]
["MCSH-3540-L-99834","AIT - MCSI","2015-12-03T04:42:21","CSAC",null,null,"OF_CAL","P8X : RADAR GÉN3 (P8X) : CAL D5.1b VRS2 DV P87 (TMC4 selon FSP V14)","2016-01-25","Attente GO",null,null,"2016-01-22","OTD","2016-01-27","FTR"]
["MCSH-8064-L-99696","EST - MCSI","2015-11-27T04:08:41","ELAC",null,null,"OF_PIECE","R83E : SONDE : Officialisation faisceau pour sonde AQS DMTRLESS\r\n","2016-01-31","Attente GO",null,null,"2016-01-22","OTD","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-7415-L-101925","EST - MCSI","2016-01-20T13:59:10","ELAC",null,null,"OF_PIECE","X74E : GRPE_CLIM : Officialisation d'une pièce OPF pour la sonde OHIZUMI-X74","2016-01-31","Attente GO",null,null,"2016-01-22","DR","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-7816-L-101584","AIT - MCSI","2016-01-13T11:58:36","SWES",null,null,"OF_PIECE","MODULE_HAB10 : COM2008X (KOSTAL: ECOPRF CAV) : Officialisation d'une pièce suite au passage en PEPP - MDT ref com2008 Kostal Premium","2016-01-22","Attente GO",null,null,"2016-01-25","NDR","2016-04-01","FTR"]
["MCSH-8064-L-99695","EST - MCSI","2015-11-27T16:07:16","ELAC",null,null,"OF_PIECE","R83E : SONDE : Officialisation sonde AQS DMTRLESS\r\n","2016-01-31","Attente GO",null,null,"2016-01-25","OTD","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-2937-L-55443","EST - MCSI","2013-09-23T16:39:20","ELPS",null,null,"DO_D3E_CLOT","K0 : PROJ : Cloture Fiche D3E","2015-09-30","Attente GO","2016-01-26","Retard fournisseur","2016-01-26","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-8069-L-95752","EST - MCSI","2015-08-17T15:18:06","EACC",null,null,"OF_PIECE","X7RR : ANTENNE_BACKUP (X7RR) : Officialisation d'une pièce","2016-01-22","Attente GO",null,null,"2016-01-26","OTD","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-7479-L-92319","AIT - MCSI","2015-06-08T10:45:43","CSAC",null,null,"DO_CDCI_BILAN","B751_3_4_MV : CVM (B753_4  MV) : Bilan des retours des CDCI (B753)","2016-01-28","Attente GO",null,null,"2016-01-26","OTD","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-7479-L-92320","AIT - MCSI","2015-06-08T10:45:43","CSAC",null,null,"RT_CDCI","B751_3_4_MV : CVM (B753_4  MV) : B753: Revue technique de CDCI","2016-01-28","Attente GO",null,null,"2016-01-26","OTD","2016-03-16","ACCEPTE_DEFAUT"]
["MCSH-7479-L-97462","AIT - MCSI","2015-10-05T09:43:22","CSAC",null,null,"DO_CDCI_BILAN","B751_3_4_MV : CVM (B753_4  MV) : Bilan des retours des CDCI (B754)","2016-01-28","Attente GO",null,null,"2016-01-26","OTD","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-7479-L-97541","AIT - MCSI","2015-10-05T14:26:08","CSAC",null,null,"RT_CDCI","B751_3_4_MV : CVM (B753_4  MV) : B754: Revue technique de CDCI","2016-01-28","Attente GO",null,null,"2016-01-26","OTD","2016-02-26","ACCEPTE_DEFAUT"]
["MCSH-7831-L-87852","EST - MCSI","2015-04-07T18:41:29","EACC",null,null,"OF_PIECE","K9 : ANTENNE_BACKUP (REC K9) : Reconduction de l'antenne passive pour K9\r\nDAG","2016-02-19","Attente GO",null,null,"2016-01-26","OTD","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-7075-L-99498","AIT - MCSI","2015-11-25T11:17:17","CSAC",null,null,"OF_PIECE","T9_MV : RADAR GÉN3 (T9MV) : REC Assemblé Radar Gen 3 D5.2","2016-01-22","Attente GO",null,null,"2016-01-27","OTD","2016-09-08","RBA"]
["MCSH-6973-L-86968","EST - MCSI","2015-03-23T11:07:50","ELAC",null,null,"RP_DFNU","R82E,R83E : GRPE_CLIM : Synthèse des Revues de Projet DFNU","2016-01-27","Attente GO","2015-10-30","Retard fournisseur","2016-01-27","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-3745-L-101147","AIT - MCSI","2016-01-08T12:02:45","SWES",null,null,"SYN_A3_QUAL_DOM","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_METIER_A3-EMCD","2016-01-27","Attente GO",null,null,"2016-01-27","DR","2016-04-01","FTR"]
["MCSH-4158-L-102227","EST - MCSI","2016-01-21T16:14:51","EEMS",null,null,"SYN_DC_ORGANE","_RITUELS : _RITUEL_EEMS_Qualité : Extraction DC CLIM A9/B78/T9/EEE","2016-01-27","Attente GO",null,null,"2016-01-27","DR","2016-02-03","FTR"]
["MCSH-3745-L-101227","AIT - MCSI","2016-01-08T01:31:57","SWES",null,null,"SYN_A3_QUAL_ORG","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_A3-COM2005 EV2-EV3 Delphi","2016-01-28","Attente GO",null,null,"2016-01-28","DR","2016-04-01","FTR"]
["MCSH-4158-L-102221","EST - MCSI","2016-01-21T16:14:51","EEMS",null,null,"SYN_A3_QUAL_DOM","_RITUELS : _RITUEL_EEMS_Qualité : IQC_METIER_A3 Pole-SVAC","2016-01-28","Attente GO",null,null,"2016-01-28","DR","2016-02-03","FTR"]
["MCSH-4158-L-102222","EST - MCSI","2016-01-21T16:14:51","EEMS",null,null,"SYN_A3_QUAL_ORG","_RITUELS : _RITUEL_EEMS_Qualité : IQC_ORGANE_A3-EVAV","2016-01-28","Attente GO",null,null,"2016-01-28","DR","2016-02-03","FTR"]
["MCSH-4158-L-102223","EST - MCSI","2016-01-21T16:14:51","EEMS",null,null,"SYN_A3_QUAL_DOM","_RITUELS : _RITUEL_EEMS_Qualité : IQC_METIER_A3 Pole-EACH","2016-01-28","Attente GO",null,null,"2016-01-28","DR","2016-02-03","FTR"]
["MCSH-4158-L-102224","EST - MCSI","2016-01-21T16:14:51","EEMS",null,null,"SYN_A3_QUAL_ORG","_RITUELS : _RITUEL_EEMS_Qualité : IQC_ORGANE_A3-LVE/LVEAP","2016-01-28","Attente GO",null,null,"2016-01-28","DR","2016-02-03","FTR"]
["MCSH-4158-L-102225","EST - MCSI","2016-01-21T16:14:51","EEMS",null,null,"SYN_A3_QUAL_ORG","_RITUELS : _RITUEL_EEMS_Qualité : IQC_ORGANE_A3-RETROS","2016-01-28","Attente GO",null,null,"2016-01-28","DR","2016-02-03","FTR"]
["MCSH-4158-L-102228","EST - MCSI","2016-01-21T16:14:51","EEMS",null,null,"SYN_A3_QUAL_ORG","_RITUELS : _RITUEL_EEMS_Qualité : IQC_ORGANE_A3-SERRURES","2016-01-28","Attente GO",null,null,"2016-01-28","DR","2016-02-03","FTR"]
["MCSH-4158-L-102229","EST - MCSI","2016-01-21T16:14:51","EEMS",null,null,"SYN_A3_QUAL_ORG","_RITUELS : _RITUEL_EEMS_Qualité : IQC_ORGANE_A3-SIEGES","2016-01-28","Attente GO",null,null,"2016-01-28","DR","2016-02-03","FTR"]
["MCSH-7817-L-98896","AIT - MCSI","2015-11-10T16:55:05","SWES",null,null,"OF_PIECE","MODULE_HAB10 : COM2008X (BVH2 VALEO : ECOPRF CAV) : Officialisation d'une pièce ECOPRF CAV A9","2016-01-29","Attente GO",null,null,"2016-01-28","OTD","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-8124-L-87273","EST - MCSI","2015-03-26T15:46:28","EACC",null,null,"OF_PIECE","K9 : JDV (Var Rec K9) : Rec Antivol Méca + vis fixation","2016-02-12","Attente GO","2015-06-19",null,"2016-01-28","OTD","2016-02-02","FTR"]
["MCSH-7821-L-98281","EST - MCSI","2015-10-20T14:41:20","EACC",null,null,"OF_PIECE","A88 : AVE (A88) : Officialisation d'une pièce","2016-03-04","Attente GO",null,null,"2016-01-28","OTD","2016-06-23","ACCEPTE_DEFAUT"]
["MCSH-5562-L-64948","EST - MCSI","2014-02-21T13:46:22","ELAC",null,null,"DO_ETAT_ACCEPT","B618 : GRPE_CLIM : Etat d'acceptation Produit (pièce R2)\r\nRégulateur Pulseur VLCL","2015-08-16","Attente GO","2016-01-29","Retard fournisseur","2016-01-29","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-5562-L-64957","EST - MCSI","2014-02-21T13:46:22","ELAC",null,null,"DO_ETAT_ACCEPT","B618 : GRPE_CLIM : Etat d'acceptation Produit (pièce R2)","2016-01-11","Attente GO","2016-01-29","Retard fournisseur","2016-01-29","OTD","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-8063-L-99694","EST - MCSI","2015-11-27T16:04:55","ELAC",null,null,"OF_PIECE","R83E : CTP : Officialisation CTP 1090W","2016-01-29","Attente GO",null,null,"2016-01-29","OTD","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-3036-L-105321","AIT - MCSI","2016-03-25T11:53:12","CSAC",null,null,"SYN_ALTIS ","B751_3_4_MV,B78_mi_vie,B81_Chine_Fenêtre_VS,C84_Chine,G95_PH2,K0,MODULE_EE02,P1UO,P84_Chine,P87_Chine,P8X,T9_MV,X81_Chine : RADAR GÉN3 : Gestion Hebdomadaire Altis\r\n","2016-01-29","Attente GO",null,null,"2016-01-29","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-8073-L-95756","EST - MCSI","2015-08-17T15:32:00","EACC",null,null,"OF_PIECE","B753_Chine : ANTENNE_BACKUP (B753C) : Officialisation d'une pièce","2016-02-04","Attente GO",null,null,"2016-01-29","OTD","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-6825-L-76671","AIT - MCSI","2014-10-09T14:06:05","CSAC",null,null,"DO_CESARE","B78_mi_vie : RADAR GÉN3 (B78 MV) : Livraison BE CESARE pour EL1","2016-02-01","Attente GO",null,null,"2016-02-01","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-6825-L-76672","AIT - MCSI","2014-10-09T14:06:05","CSAC",null,null,"OF_CAL","B78_mi_vie : RADAR GÉN3 (B78 MV) : Calibration pour EL1","2016-02-01","Attente GO",null,null,"2016-02-01","OTD","2016-02-08","FTR"]
["MCSH-7164-L-77083","AIT - MCSI","2014-10-15T10:49:19","CSAC",null,null,"DO_CESARE","P84_Chine : RADAR GÉN3 (P84_C) : Livraison BE CESARE VRS UT2","2016-02-01","Attente GO",null,null,"2016-02-01","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7164-L-77084","AIT - MCSI","2014-10-15T10:49:19","CSAC",null,null,"OF_CAL","P84_Chine : RADAR GÉN3 (P84_C) : CAL VRS UT2","2016-02-01","Attente GO",null,null,"2016-02-01","OTD","2016-02-08","FTR"]
["MCSH-4199-L-76656","AIT - MCSI","2014-10-09T13:56:08","CSAC",null,null,"DO_CESARE","X81_Chine : RADAR GÉN3 (X81C) : Création de Référence / Maj CESARE pour EL1","2016-02-08","Attente GO",null,null,"2016-02-01","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7817-L-98895","AIT - MCSI","2015-11-10T16:54:52","SWES",null,null,"OF_PIECE","MODULE_HAB10 : COM2008X (BVH2 VALEO : ECOPRF CAV) : Officialisation d'une pièce ECOPRF CAV pour T9","2016-01-29","Attente GO","2016-02-12","Retard fournisseur","2016-02-02","OTD","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-7486-L-80764","EST - MCSI","2014-12-16T17:48:52","ELPS",null,null,"OF_DOTE","X74E : SIRENE_LIN_SSCAS,RUPTEUR_CAPOT,MUS2 : DOTE pour TI","2016-02-05","Attente GO",null,null,"2016-02-02","OTD","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-7467-L-81031","EST - MCSI","2014-12-18T22:18:01","ELPS",null,null,"OF_PIECE","R83E : SIRENE_LIN_SSCAS,RUPTEUR_CAPOT,MUS2 : REC SIRENE avec implantation définitive","2016-02-05","Attente GO",null,null,"2016-02-02","OTD","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-4199-L-76657","AIT - MCSI","2014-10-09T13:56:08","CSAC",null,null,"OF_CAL","X81_Chine : RADAR GÉN3 (X81C) : Calibration pour EL1","2016-02-08","Attente GO",null,null,"2016-02-02","OTD","2016-02-08","FTR"]
["MCSH-7415-L-97958","EST - MCSI","2015-10-12T14:56:43","ELAC",null,null,"OF_PIECE","X74E : GRPE_CLIM : Officialisation du plan fonctionnel (FM DIL MECA) pour un bisourcing","2016-02-28","Attente GO","2016-01-29",null,"2016-02-02","OTD","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-6863-L-94020","EST - MCSI","2015-07-03T10:14:59","EACC",null,null,"VAL_MOYEN","P1UO : VELUM : Création/Modification de moyen (outil de test, Chaine Organique (CO), maquette ICR ou homologation…)\r\n","2015-10-15","Attente GO","2016-01-29","Retard fournisseur","2016-02-03","OTD","2016-02-04","FTR"]
["MCSH-7467-L-102307","EST - MCSI","2016-01-25T15:07:49","ELPS",null,null,"OF_PIECE","R83E : SIRENE_LIN_SSCAS,RUPTEUR_CAPOT,MUS2 : Officialisation d'une pièce. Fixations sirène","2016-02-05","Attente GO",null,null,"2016-02-03","DR","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-7482-L-80706","EST - MCSI","2014-12-16T15:24:57","ELPS",null,null,"OF_PIECE","K9 : SIRENE_LIN_SSCAS,RUPTEUR_CAPOT,MUS2 : DEF Cheminement faisceau pour DFNu","2016-02-05","Attente GO","2016-04-06",null,"2016-02-05","OTD","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-7482-L-80669","EST - MCSI","2014-12-16T12:04:14","ELPS",null,null,"OF_DOTE","K9 : SIRENE_LIN_SSCAS,RUPTEUR_CAPOT,MUS2 : DOTE pour TI","2016-02-12","Attente GO",null,null,"2016-02-05","OTD","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-4158-L-103477","EST - MCSI","2016-02-17T09:55:54","EEMS",null,null,"SYN_DC_ORGANE","_RITUELS : _RITUEL_EEMS_Qualité : Extraction DC CLIM A9/B78/T9/EEE","2016-02-24","Attente GO",null,null,"2016-02-05","DR","2016-03-02","FTR"]
["MCSH-7121-L-78390","AIT - MCSI","2014-11-19T16:56:48","CSAC",null,null,"DO_CESARE","T9_MV : CVM (T9MV) : Création de référence/Mise à jour CESARE\r\nBE CVM Gen 2 Niveau 2 pour stade VRS1 (C4) T9MV","2016-02-12","Attente GO",null,null,"2016-02-08","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7154-L-76343","AIT - MCSI","2014-10-06T13:01:03","CSAC",null,null,"DO_CESARE","P1UO : CVM (P1UO) : Création de référence/Mise à jour CESARE\r\nBE CVM Gen 2 Niveau 1 pour stade VRSDV (C4)","2016-04-15","Attente GO",null,null,"2016-02-08","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7154-L-97458","AIT - MCSI","2015-10-05T09:14:50","CSAC",null,null,"DO_CESARE","P1UO : CVM (P1UO) : Création de référence/Mise à jour CESARE\r\nBE CVM Gen 2 Niveau 2 pour stade VRSDV (C4)","2016-04-15","Attente GO",null,null,"2016-02-08","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7819-L-87774","AIT - MCSI","2015-04-02T13:07:15","SWES",null,null,"OF_PIECE","MODULE_HAB10 : COM2005_EV3 (DELPHI : ECOPRF CAV) : Officialisation d'une pièce suite au passage en PEPP - MDT","2016-01-29","Attente GO","2016-02-15","Retard fournisseur","2016-02-09","OTD","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-7816-L-87747","AIT - MCSI","2015-04-02T13:03:11","SWES",null,null,"OF_PIECE","MODULE_HAB10 : COM2008X (KOSTAL: ECOPRF CAV) : Officialisation d'une pièce suite au passage en PEPP - MDT ref com2008P","2016-02-01","Attente GO","2016-02-15","Retard fournisseur","2016-02-09","OTD","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-7366-L-99870","EST - MCSI","2015-12-07T14:09:59","ELPS",null,null,"OF_PIECE","P1UO : SIRENE_LIN_SSCAS,RUPTEUR_CAPOT,MUS2 : Officialisation d'une pièce MUS2 - Cheminement FSX MUS2 VRS","2016-02-10","Attente GO",null,null,"2016-02-10","OTD","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-2985-L-85527","EST - MCSI","2015-03-02T15:13:31","EACC",null,null,"DO_CCA_VAL","K0,MODULE_CPE09 : RETRO_EXT : Fiche CCA phase 3 (validation et process)\r\n","2015-08-28","Attente GO","2016-02-19","Retard fournisseur","2016-02-11","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-2985-L-85524","EST - MCSI","2015-03-02T15:11:50","EACC",null,null,"DO_INC_VALID","K0,MODULE_CPE09 : RETRO_EXT : Incontournables partie validation","2015-08-31","Attente GO","2016-02-19","Retard fournisseur","2016-02-11","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-4127-L-85630","EST - MCSI","2015-03-02T16:05:37","EACC",null,null,"DO_INC_CONCEPT","C84_Export,MODULE_CPE09,P1UO,P8X,X74E : RETRO_EXT : Incontournables partie conception P1UO","2015-10-19","Attente GO","2016-02-19","Retard fournisseur","2016-02-11","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7819-L-95415","AIT - MCSI","2015-08-04T11:00:23","SWES",null,null,"OF_PIECE","MODULE_HAB10 : COM2005_EV3 (DELPHI : ECOPRF CAV) : Officialisation d'une pièce suite au passage en PEPP - REC B9","2016-01-29","Attente GO","2016-02-15","Retard fournisseur","2016-02-11","OTD","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-3745-L-101255","AIT - MCSI","2016-01-08T03:18:16","SWES",null,null,"SYN_DC_ORGANE","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_SR-Push FSE Marquardt","2016-02-11","Attente GO",null,null,"2016-02-11","DR","2016-04-01","FTR"]
["MCSH-7154-L-95663","AIT - MCSI","2015-08-12T14:16:47","CSAC",null,null,"OF_CAL","P1UO : CVM (P1UO) : Calibration CVM Gen 2 Niveau 1 (D5.1) pour VRS0","2016-02-15","Attente GO",null,null,"2016-02-11","OTD","2016-02-15","FTR"]
["MCSH-7154-L-97457","AIT - MCSI","2015-10-05T09:11:32","CSAC",null,null,"OF_CAL","P1UO : CVM (P1UO) : Calibration CVM Gen 2 Niveau 2 (D5.1) pour VRS0","2016-02-15","Attente GO",null,null,"2016-02-11","OTD","2016-02-15","FTR"]
["MCSH-3745-L-101233","AIT - MCSI","2016-01-08T01:47:36","SWES",null,null,"SYN_DC_ORGANE","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_SR-Volant équipé","2016-02-15","Attente GO",null,null,"2016-02-11","DR","2016-04-01","FTR"]
["MCSH-7415-L-102263","EST - MCSI","2016-01-22T14:39:00","ELAC",null,null,"OF_PIECE","X74E : GRPE_CLIM : Officialisation faisceau groupe","2016-02-29","Attente GO",null,null,"2016-02-11","DR","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-7819-L-102256","AIT - MCSI","2016-01-22T11:57:34","SWES",null,null,"OF_PIECE","MODULE_HAB10 : COM2005_EV3 (DELPHI : ECOPRF CAV) : Officialisation d'une pièce suite au passage en PEPP - REC T73Russie","2016-01-29","Attente GO","2016-02-15",null,"2016-02-12","DR","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-7486-L-80762","EST - MCSI","2014-12-16T17:48:52","ELPS",null,null,"DO_CESARE","X74E : SIRENE_LIN_SSCAS,RUPTEUR_CAPOT,MUS2 : Livraison BE Cesare pour TI (B2)","2016-02-12","Attente GO",null,null,"2016-02-12","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-3745-L-101181","AIT - MCSI","2016-01-08T01:11:30","SWES",null,null,"SYN_A3_QUAL_DOM","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_METIER_A3-EMCD","2016-02-12","Attente GO",null,null,"2016-02-12","DR","2016-04-01","FTR"]
["MCSH-7121-L-78395","AIT - MCSI","2014-11-19T16:56:48","CSAC",null,null,"OF_CAL","T9_MV : CVM (T9MV) : Calibration CVM Gen 2 Niveau 2 pour VRS1 (C4)","2016-02-15","Attente GO",null,null,"2016-02-12","OTD","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-3741-L-101135","AIT - MCSI","2016-01-08T11:57:49","SWES",null,null,"SYN_A3_ALTIS_REAC","_QUALITE : IND_QUAL (Indicateurs EQP et Réactivité) : A3 Synthèse Altis Réactivité","2016-02-28","Attente GO",null,null,"2016-02-12","OTD","2016-04-01","FTR"]
["MCSH-3540-L-99702","AIT - MCSI","2015-11-27T05:52:35","CSAC",null,null,"DO_CESARE","P8X,P8_Europe_VS_Fenetre : RADAR GÉN3 (P8X) : Livraison BE CESARE D5.2 (0.3G) EL1","2016-02-15","Attente GO",null,null,"2016-02-15","OTD","2016-02-16","FTR"]
["MCSH-3042-L-101115","AIT - MCSI","2016-01-07T11:43:07","CSAC",null,null,"OF_CAL","K0 : RADAR GÉN3 (K0) : CAL D5.2 EL2 (TMC 18 selon FSP 14_2)","2016-02-15","Attente GO",null,null,"2016-02-15","DR","2016-02-16","FTR"]
["MCSH-3745-L-101192","AIT - MCSI","2016-01-08T01:19:50","SWES",null,null,"SYN_A3_QUAL_ORG","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_A3-COM2008 Premium Valeo","2016-02-15","Attente GO",null,null,"2016-02-15","DR","2016-04-01","FTR"]
["MCSH-3042-L-102214","AIT - MCSI","2016-01-21T03:10:55","CSAC",null,null,"DO_CESARE","K0 : RADAR GÉN3 (K0) : Livraison BEs CESARE D5.2 pour MAJ EL2 (TMC 18 selon FSP 14_2)","2016-02-15","Attente GO",null,null,"2016-02-15","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-3540-L-99703","AIT - MCSI","2015-11-27T05:52:58","CSAC",null,null,"OF_CAL","P8X : RADAR GÉN3 (P8X) : CAL D5.2 (0.3G) EL1","2016-02-15","Attente GO","2016-02-16","Retard fournisseur","2016-02-16","OTD","2016-02-16","FTR"]
["MCSH-7363-L-100671","AIT - MCSI","2015-12-21T09:23:37","CSAC",null,null,"OF_PIECE","C84_Chine : CVM (C84) : Officialisation Plan et 3D Fournisseur - Sans déviation\r\n CVM Gen 2 Niveau 3","2016-02-29","Attente GO",null,null,"2016-02-16","OTD","2016-03-16","FTR"]
["MCSH-7816-L-95414","AIT - MCSI","2015-08-04T10:58:44","SWES",null,null,"OF_PIECE","MODULE_HAB10 : COM2008X (KOSTAL: ECOPRF CAV) : Officialisation d'une pièce suite au passage en PEPP - REC ref com2008","2016-03-11","Attente GO","2016-02-15",null,"2016-02-16","OTD","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-6863-L-84709","EST - MCSI","2015-02-19T11:22:18","EACC",null,null,"VAL_VALID","P1UO : VELUM : Passe de Validation Fonctionnelle B3","2015-12-09","Attente GO","2016-04-25","Retard fournisseur","2016-02-17","OTD","2016-04-25","FTR"]
["MCSH-3540-L-102373","AIT - MCSI","2016-01-27T06:50:58","CSAC",null,null,"OF_PIECE","P8X : RADAR GÉN3 (P8X) : REC : BOITIER ELECTRONIQUE RADAR AV ASS D5.3 : OCM","2016-02-18","Attente GO",null,null,"2016-02-17","DR","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-6825-L-76673","AIT - MCSI","2014-10-09T14:06:05","CSAC",null,null,"DO_CESARE","B78_mi_vie : RADAR GÉN3 (B78 MV) : Livraison BE CESARE D5.2 pour EL2","2016-02-29","Attente GO",null,null,"2016-02-17","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-3745-L-101261","AIT - MCSI","2016-01-08T03:26:57","SWES",null,null,"SYN_DC_ORGANE","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_SR-Ecran tactile","2016-02-18","Attente GO",null,null,"2016-02-18","DR","2016-04-01","FTR"]
["MCSH-3745-L-101272","AIT - MCSI","2016-01-08T03:28:02","SWES",null,null,"SYN_DC_ORGANE","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_SR-Combiné","2016-02-18","Attente GO",null,null,"2016-02-18","DR","2016-04-01","FTR"]
["MCSH-3540-L-102985","AIT - MCSI","2016-02-11T01:52:36","CSAC",null,null,"DO_CESARE","P8X,P8_Europe_VS_Fenetre : RADAR GÉN3 (P8X) : Livraison BE D5.2 CESARE VRS2 DV","2016-02-22","Attente GO",null,null,"2016-02-18","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-5562-L-99871","EST - MCSI","2015-12-07T14:10:21","ELAC",null,null,"OF_PIECE","B618 : GRPE_CLIM : Officialisation des faisceaux CH et RF  du projet B618.","2016-02-28","Attente GO",null,null,"2016-02-18","OTD","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-6604-L-102070","AIT - MCSI","2016-01-20T05:52:51","CSAC",null,null,"OF_PIECE","P1UO : RADAR GÉN3 (P1UO) : REC : BOITIER ELECTRONIQUE RADAR AV ASS D5.3","2016-03-04","Attente GO",null,null,"2016-02-18","OTD","2016-09-08","RBA"]
["MCSH-8063-L-95685","EST - MCSI","2015-08-14T10:43:36","ELAC",null,null,"DO_CCA_TOPHW","R83E : CTP : Fiche CCA phase 2 (conception)","2016-01-22","Attente GO","2016-02-19","Retard fournisseur","2016-02-19","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-6608-L-103560","EST - MCSI","2016-02-18T15:07:44","ELPS",null,null,"OF_DOTE","A88 : SIRENE_LIN_SSCAS,MUS2,RUPTEUR_CAPOT : Officialisation de DOTE MUS2","2016-02-12","Attente GO","2016-02-19",null,"2016-02-19","DR","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-6611-L-103572","EST - MCSI","2016-02-18T16:25:08","ELPS",null,null,"OF_DOTE","P1MO : RUPTEUR_CAPOT,SIRENE_LIN_SSCAS,MUS2 (Rec. P1MO) : Officialisation de DOTE MUS2 ","2016-02-12","Attente GO","2016-02-19",null,"2016-02-19","DR","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-3745-L-101204","AIT - MCSI","2016-01-08T01:21:31","SWES",null,null,"SYN_A3_QUAL_ORG","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_A3-COM2008 Premium KOSTAL","2016-02-20","Attente GO",null,null,"2016-02-19","OTD","2016-04-01","FTR"]
["MCSH-3745-L-101216","AIT - MCSI","2016-01-08T01:22:18","SWES",null,null,"SYN_A3_QUAL_ORG","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_A3-COM2008 KOSTAL","2016-02-20","Attente GO",null,null,"2016-02-19","OTD","2016-04-01","FTR"]
["MCSH-7075-L-85635","AIT - MCSI","2015-03-02T17:18:27","CSAC",null,null,"OF_CAL","T9_MV : RADAR GÉN3 (T9MV) : CALs D5.2 pour VRS1 pour T91&T92 (Sans ACC & ACC BVM 30 DV5RC ML6C)","2016-02-22","Attente GO",null,null,"2016-02-19","OTD","2016-03-10","FTR"]
["MCSH-5891-L-102349","AIT - MCSI","2016-01-27T09:44:26","CSAC",null,null,"OF_PIECE","B618 : CVM (B618) : EL1 (F09.2016): Officialisation d'une CVM Gen 2 Niveau 1 (D5.2)","2016-02-22","Attente GO",null,null,"2016-02-19","DR","2016-02-23","FTR"]
["MCSH-7075-L-102300","AIT - MCSI","2016-01-25T01:25:38","CSAC",null,null,"OF_PIECE","T9_MV : RADAR GÉN3 (T9MV) : REC Assemblé Radar Gen 3 D5.3","2016-03-04","Attente GO",null,null,"2016-02-19","DR","2016-09-08","RBA"]
["MCSH-8161-L-99302","AIT - MCSI - SMEG","2015-11-19T11:33:58","IDEV",null,null,"OF_PIECE","_F09/2016 : SMEG+_I_V2 : Reconduction HW pour le projet B81 en AEE2010 sur PRS7 en 6.3","2016-06-30","Attente GO",null,null,"2016-02-19","OTD","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-7362-L-96410","AIT - MCSI","2015-09-08T09:54:00","CSAC",null,null,"OF_DOTE","C84_Chine : RADAR GÉN3 (C84) : Pour Stade OCM VRS1 (C4)","2016-07-15","Attente GO",null,null,"2016-02-19","OTD","2016-07-25","ACCEPTE_DEFAUT"]
["MCSH-3540-L-102982","AIT - MCSI","2016-02-11T01:43:31","CSAC",null,null,"OF_CAL","P8X : RADAR GÉN3 (P8X) : CAL D5.2 VRS2 DV P87","2016-02-22","Attente GO",null,null,"2016-02-22","DR","2016-02-24","FTR"]
["MCSH-7154-L-103197","AIT - MCSI","2016-02-15T10:35:16","CSAC",null,null,"OF_PIECE","P1UO : CVM (P1UO) : VRSDV: Reconduction CVM niv1 D5.2","2016-02-22","Attente GO","2016-02-23",null,"2016-02-22","DR","2016-02-26","FTR"]
["MCSH-7683-L-109971","AIT - MCSI","2016-07-21T19:32:51","CSAC",null,null,"OF_PIECE","R83E : VISIO_PARK (R83E) : REC référence ECU VP2 ADAS V2","2016-02-25","Attente GO",null,null,"2016-02-22","DR","2016-07-25","ACCEPTE_DEFAUT"]
["MCSH-7034-L-103271","AIT - MCSI","2016-02-15T15:44:00","CSAC",null,null,"OF_DOTE","B78_mi_vie : CVM (B78_mi_vie) : Officialisation de DOTE PRSEL2","2016-02-26","Attente GO",null,null,"2016-02-22","DR","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-6825-L-76674","AIT - MCSI","2014-10-09T14:06:05","CSAC",null,null,"OF_CAL","B78_mi_vie : RADAR GÉN3 (B78 MV) : CAL D5.2 EL2","2016-02-29","Attente GO",null,null,"2016-02-22","OTD","2016-02-24","FTR"]
["MCSH-4199-L-102938","AIT - MCSI","2016-02-09T05:59:27","CSAC",null,null,"OF_PIECE","X81_Chine : RADAR GÉN3 (X81C) : Reconduction Assemblé Radar Gen 3 sur X81_CH : OCM D5.3","2016-03-04","Attente GO",null,null,"2016-02-22","DR","2016-09-08","RBA"]
["MCSH-7154-L-103198","AIT - MCSI","2016-02-15T10:49:29","CSAC",null,null,"OF_PIECE","P1UO : CVM (P1UO) : VRSDV: Reconduction CVM niv2 D5.2","2016-02-22","Attente GO","2016-02-23",null,"2016-02-23","DR","2016-02-26","FTR"]
["MCSH-7154-L-103201","AIT - MCSI","2016-02-15T10:55:36","CSAC",null,null,"OF_PIECE","P1UO : CVM (P1UO) : VRSDV: Reconduction CVM niv3 V-AEB SW4","2016-02-22","Attente GO","2016-02-23",null,"2016-02-23","DR","2016-02-26","FTR"]
["MCSH-5893-L-103179","AIT - MCSI","2016-02-15T08:21:27","CSAC",null,null,"OF_CAL","P1MO : CVM (A88,P1MO) : Calibration CVM Gen 2 Niveau 1 pour stade IV(80%) P1MO","2016-02-26","Attente GO",null,null,"2016-02-23","DR","2016-02-26","FTR"]
["MCSH-5893-L-103180","AIT - MCSI","2016-02-15T08:32:55","CSAC",null,null,"OF_CAL","P1MO : CVM (A88,P1MO) : Calibration CVM Gen 2 Niveau 3 pour stade IV(80%) P1MO","2016-02-26","Attente GO",null,null,"2016-02-23","DR","2016-02-26","FTR"]
["MCSH-5893-L-103181","AIT - MCSI","2016-02-15T08:39:49","CSAC",null,null,"OF_CAL","A88 : CVM (A88,P1MO) : Calibration CVM Gen 2 Niveau 1 pour stade IV (80%) A88","2016-02-26","Attente GO",null,null,"2016-02-23","DR","2016-02-26","FTR"]
["MCSH-5893-L-103182","AIT - MCSI","2016-02-15T08:46:00","CSAC",null,null,"OF_CAL","A88 : CVM (A88,P1MO) : Calibration CVM Gen 2 Niveau 3 pour stade IV (80%) A88","2016-02-26","Attente GO",null,null,"2016-02-23","DR","2016-02-26","FTR"]
["MCSH-4158-L-103471","EST - MCSI","2016-02-17T09:55:54","EEMS",null,null,"SYN_A3_QUAL_DOM","_RITUELS : _RITUEL_EEMS_Qualité : IQC_METIER_A3 Pole-EEMS","2016-02-24","Attente GO",null,null,"2016-02-24","DR","2016-03-02","FTR"]
["MCSH-6825-L-103387","AIT - MCSI","2016-02-16T10:20:00","CSAC",null,null,"OF_PIECE","B78_mi_vie : RADAR GÉN3 (B78 MV) : REC : BOITIER ELECTRONIQUE RADAR AV ASS D5.3","2016-02-26","Attente GO",null,null,"2016-02-24","DR","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-7034-L-103266","AIT - MCSI","2016-02-15T14:07:33","CSAC",null,null,"OF_PIECE","B78_mi_vie : CVM (B78_mi_vie) : Reconduction CVM niv2 D5.2 pour EL2","2016-02-29","Attente GO",null,null,"2016-02-24","DR","2016-02-26","FTR"]
["MCSH-3934-L-102868","EST - MCSI","2016-02-05T15:20:42","ELAC",null,null,"OF_PIECE","P8X : PULSEUR_AR : Officialisation d'une pièce : moteur CHAOLI stade OCM.","2016-02-29","Attente GO",null,null,"2016-02-25","DR","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-3934-L-102869","EST - MCSI","2016-02-05T15:25:30","ELAC",null,null,"OF_PIECE","P8X : PULSEUR_AR : Officialisation d'uneplan fonctionnel pulseur AR. (Bisourcing YDK/CHAOLI)","2016-02-29","Attente GO",null,null,"2016-02-25","DR","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-7034-L-103268","AIT - MCSI","2016-02-15T14:58:54","CSAC",null,null,"DO_CESARE","B78_mi_vie : CVM (B78_mi_vie) : BE CVM Gen 2 niv2 SW D5.2 pour stade PRSEL2","2016-03-04","Attente GO",null,null,"2016-02-25","DR","2016-02-26","FTR"]
["MCSH-7363-L-96369","AIT - MCSI","2015-09-07T18:43:32","CSAC",null,null,"OF_PIECE","C84_Chine : CVM (C84) : Officialisation Plan et 3D Fournisseur - Sans déviation\r\nCVM Gen 2 Niveau 2","2016-03-11","Attente GO",null,null,"2016-02-25","OTD","2016-03-16","FTR"]
["MCSH-3745-L-101518","AIT - MCSI","2016-01-13T08:03:41","SWES",null,null,"SYN_DC_ORGANE","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_SR-CSV RADIO et RVV/LVV VALEO","2016-02-22","Attente GO",null,null,"2016-02-26","NDR","2016-04-01","FTR"]
["MCSH-3745-L-101529","AIT - MCSI","2016-01-13T08:04:04","SWES",null,null,"SYN_DC_ORGANE","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_SR-CSV RADIO et RVV/LVV DELPHI","2016-02-22","Attente GO",null,null,"2016-02-26","NDR","2016-04-01","FTR"]
["MCSH-7415-L-102344","EST - MCSI","2016-01-26T02:58:40","ELAC",null,null,"OF_PIECE","X74E : GRPE_CLIM : Officialisation faisceau groupe","2016-02-29","Attente GO",null,null,"2016-02-26","DR","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-7034-L-103267","AIT - MCSI","2016-02-15T14:23:41","CSAC",null,null,"OF_CAL","B78_mi_vie : CVM (B78_mi_vie) : Calibration CVM Gen 2 (D5.2) Niveau 2 pour stade EL2 B78mv","2016-02-29","Attente GO",null,null,"2016-02-26","DR","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-5891-L-75350","AIT - MCSI","2014-09-10T16:07:39","CSAC",null,null,"DO_CESARE","B618 : CVM (B618) : EL1 (F09.2016): Création BE CVM Gen 2 Niveau 1 (D5.2)","2016-03-18","Attente GO",null,null,"2016-02-26","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-3745-L-101171","AIT - MCSI","2016-01-08T01:08:47","SWES",null,null,"SYN_DC_ORGANE","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_SR-VCI DELPHI","2016-02-28","Attente GO",null,null,"2016-02-28","OTD","2016-04-01","FTR"]
["MCSH-3745-L-101503","AIT - MCSI","2016-01-13T07:58:39","SWES",null,null,"SYN_DC_ORGANE","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_SR-VCI Marquardt","2016-02-28","Attente GO",null,null,"2016-02-28","OTD","2016-04-01","FTR"]
["MCSH-3741-L-74814","AIT - MCSI","2014-08-25T13:00:12","SWES",null,null,"SYN_A3_TRAJ_QUAL_DOM","_QUALITE : IND_QUAL (Indicateurs EQP et Réactivité) : A3 Synthèse Trajectoire Qualité Domaine ","2015-10-28","Attente GO","2016-02-29","Retard fournisseur","2016-02-29","OTD","2016-04-01","FTR"]
["MCSH-4158-L-103472","EST - MCSI","2016-02-17T09:55:54","EEMS",null,null,"SYN_A3_QUAL_ORG","_RITUELS : _RITUEL_EEMS_Qualité : IQC_ORGANE_A3-EVAV","2016-02-24","Attente GO",null,null,"2016-02-29","NDR","2016-03-02","FTR"]
["MCSH-4158-L-103473","EST - MCSI","2016-02-17T09:55:54","EEMS",null,null,"SYN_A3_QUAL_DOM","_RITUELS : _RITUEL_EEMS_Qualité : IQC_METIER_A3 Pole-EACH","2016-02-24","Attente GO",null,null,"2016-02-29","NDR","2016-03-02","FTR"]
["MCSH-4158-L-103474","EST - MCSI","2016-02-17T09:55:54","EEMS",null,null,"SYN_A3_QUAL_ORG","_RITUELS : _RITUEL_EEMS_Qualité : IQC_ORGANE_A3-LVE/LVEAP","2016-02-24","Attente GO",null,null,"2016-02-29","NDR","2016-03-02","FTR"]
["MCSH-4158-L-103475","EST - MCSI","2016-02-17T09:55:54","EEMS",null,null,"SYN_A3_QUAL_ORG","_RITUELS : _RITUEL_EEMS_Qualité : IQC_ORGANE_A3-RETROS","2016-02-24","Attente GO",null,null,"2016-02-29","NDR","2016-03-02","FTR"]
["MCSH-4158-L-103476","EST - MCSI","2016-02-17T09:55:54","EEMS",null,null,"SYN_A3_QUAL_ORG","_RITUELS : _RITUEL_EEMS_Qualité : IQC_ORGANE_A3-ADML","2016-02-24","Attente GO",null,null,"2016-02-29","NDR","2016-03-02","FTR"]
["MCSH-4158-L-103478","EST - MCSI","2016-02-17T09:55:54","EEMS",null,null,"SYN_A3_QUAL_ORG","_RITUELS : _RITUEL_EEMS_Qualité : IQC_ORGANE_A3-SERRURES","2016-02-24","Attente GO",null,null,"2016-02-29","NDR","2016-03-02","FTR"]
["MCSH-4158-L-103479","EST - MCSI","2016-02-17T09:55:54","EEMS",null,null,"SYN_A3_QUAL_ORG","_RITUELS : _RITUEL_EEMS_Qualité : IQC_ORGANE_A3-SIEGES","2016-02-24","Attente GO",null,null,"2016-02-29","NDR","2016-03-02","FTR"]
["MCSH-3036-L-105322","AIT - MCSI","2016-03-25T11:53:12","CSAC",null,null,"SYN_ALTIS ","B751_3_4_MV,B78_mi_vie,B81_Chine_Fenêtre_VS,C84_Chine,G95_PH2,K0,MODULE_EE02,P1UO,P84_Chine,P87_Chine,P8X,T9_MV,X81_Chine : RADAR GÉN3 : Gestion Hebdomadaire Altis\r\n","2016-02-29","Attente GO",null,null,"2016-02-29","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-7400-L-102705","EST - MCSI","2016-02-02T10:38:41","ELPS",null,null,"DO_EDS","X74E : FEU_AV : Renseigner OPHELIE EDS Tool: stade robuste","2016-02-29","Attente GO",null,null,"2016-02-29","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-7121-L-103566","AIT - MCSI","2016-02-18T15:24:52","CSAC",null,null,"OF_PIECE","T9_MV : CVM (T9MV) : Reconduction CVM niv2 D5.2 pour VRS","2016-03-11","Attente GO",null,null,"2016-02-29","DR","2016-03-02","FTR"]
["MCSH-5891-L-75351","AIT - MCSI","2014-09-10T16:07:39","CSAC",null,null,"OF_CAL","B618 : CVM (B618) : EL1 (F09.2016): Officialisation d'une calibration CVM Gen 2 Niveau 1 (D5.2)","2016-03-18","Attente GO",null,null,"2016-02-29","OTD","2016-03-16","FTR"]
["MCSH-7064-L-103818","AIT - MCSI","2016-02-26T10:29:27","CSAC",null,null,"DO_CESARE","P84_Chine : CVM (P84_C) : Création de référence/Mise à jour CESARE\r\nBE CVM niv1 D5.2 pour VRS UT2","2016-03-11","Attente GO",null,null,"2016-03-01","DR","2016-03-02","FTR"]
["MCSH-7064-L-103824","AIT - MCSI","2016-02-26T10:51:48","CSAC",null,null,"DO_CESARE","P84_Chine : CVM (P84_C) : Création de référence/Mise à jour CESARE\r\nBE CVM niv2 D5.2 pour VRS UT2","2016-03-11","Attente GO",null,null,"2016-03-01","DR","2016-03-02","FTR"]
["MCSH-7066-L-102898","AIT - MCSI","2016-02-08T11:06:44","CSAC",null,null,"OF_PIECE","G95_PH2 : CVM (G95 Ph2) : G95ph2 (VRS2): Reconduction CVM niv2 D5.2","2016-03-31","Attente GO",null,null,"2016-03-01","OTD","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-7480-L-100331","AIT - MCSI","2015-12-14T11:22:09","CSAC",null,null,"RT_CDCI","B751_3_4_MV : RADAR GÉN3 (B753_4  MV) : Revue technique de CDCI","2016-03-02","Attente GO",null,null,"2016-03-02","OTD","2016-08-23","ACCEPTE_DEFAUT"]
["MCSH-4192-L-103554","AIT - MCSI","2016-02-18T14:20:32","CSAC",null,null,"OF_PIECE","X81_Chine : CVM (X81_Chine) : Reconduction CVM niv2 D5.2 pour PRSEL2","2016-03-04","Attente GO",null,null,"2016-03-02","DR","2016-03-17","FTR"]
["MCSH-3533-L-103464","AIT - MCSI","2016-02-17T08:13:45","CSAC",null,null,"OF_CAL","P8X : CVM (P8) : P87: Officialisation des calibrations D5.2 (niv1 & 2) pour VRS2 DV","2016-03-11","Attente GO",null,null,"2016-03-02","DR","2016-03-16","FTR"]
["MCSH-7064-L-103468","AIT - MCSI","2016-02-17T08:27:50","CSAC",null,null,"OF_CAL","P84_Chine : CVM (P84_C) : Calibration CVM D5.2 niv 1 pour VRS UT2","2016-03-11","Attente GO",null,null,"2016-03-02","DR","2016-03-16","FTR"]
["MCSH-7064-L-103469","AIT - MCSI","2016-02-17T08:33:00","CSAC",null,null,"OF_CAL","P84_Chine : CVM (P84_C) : Calibration CVM D5.2 niv 2 pour VRS UT2","2016-03-11","Attente GO",null,null,"2016-03-02","DR","2016-03-16","FTR"]
["MCSH-3533-L-103828","AIT - MCSI","2016-02-26T11:16:42","CSAC",null,null,"DO_BE_CESARE","P8X : CVM (P8) : P87:BE CVM2 D5.2 Niv1 VRS DV2","2016-03-11","Attente GO",null,null,"2016-03-02","DR","2016-03-17","FTR"]
["MCSH-3533-L-103829","AIT - MCSI","2016-02-26T11:17:00","CSAC",null,null,"DO_BE_CESARE","P8X : CVM (P8) : P87:BE CVM2 D5.2 Niv2 VRS DV2","2016-03-11","Attente GO",null,null,"2016-03-02","DR","2016-03-17","FTR"]
["MCSH-7338-L-85873","EST - MCSI","2015-03-05T08:50:39","EACC",null,null,"DO_FC_VRS","K9,MODULE_CPE09 : RETRO_EXT : Fiches composants pour SDP VRS","2016-03-07","Attente GO",null,null,"2016-03-03","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7830-L-92117","EST - MCSI","2015-06-05T11:37:46","EACC",null,null,"DO_FC_VRS","K9 : PARE_BRISE_CHAUFFANT : Fiches composants pour SDP VRS (vérification des données)","2016-03-14","Attente GO",null,null,"2016-03-03","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7971-L-92294","EST - MCSI","2015-06-08T09:54:23","EACC",null,null,"DO_FC_VRS","K9 : LUCH : Fiches composants pour SDP VRS","2016-03-14","Attente GO",null,null,"2016-03-03","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-8161-L-101767","AIT - MCSI - SMEG","2016-01-15T14:32:02","IDEV",null,null,"OF_PIECE","_F09/2016 : SMEG+_I_V2 : Reconduction HW pour le projet A94 AEE2010 sur PRS7 en 6.3","2016-02-01","Attente GO",null,null,"2016-03-04","NDR","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-7400-L-89708","EST - MCSI","2015-04-22T16:58:35","ELPS",null,null,"RT_BILAN_MECA","X74E : FEU_AV : Revue Technique de bilan de Conception Mécanique","2016-02-01","Attente GO","2016-03-04","Retard fournisseur","2016-03-04","OTD","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-7121-L-104300","AIT - MCSI","2016-03-04T15:30:33","CSAC",null,null,"DO_CESARE","T9_MV : CVM (T9MV) : Création de référence/Mise à jour CESARE\r\nBE CVM Gen2 Niveau 2 pour stade VRS T9MV","2016-03-14","Attente GO",null,null,"2016-03-04","DR","2016-03-17","FTR"]
["MCSH-2698-L-103158","EST - MCSI","2016-02-12T14:28:59","ELAC",null,null,"OF_PIECE","K0 : GRPE_CLIM : Officialisation d'une faisceau allongement du brin pour la sonde ensolleillement","2016-03-30","Attente GO",null,null,"2016-03-04","OTD","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-6822-L-104722","EST - MCSI","2016-03-16T15:46:56","EACC",null,null,"RT_STD","D34E,MODULE_CE_MDT,P21,X74_Chine : LVEAP,LVE : Revue Technique des Spécifications et Normes avec le fournisseur","2016-04-29","Attente GO","2016-05-13","Retard fournisseur","2016-03-04","OTD","2016-05-24","ACCEPTE_DEFAUT"]
["MCSH-7121-L-103567","AIT - MCSI","2016-02-18T15:34:54","CSAC",null,null,"OF_CAL","T9_MV : CVM (T9MV) : Calibration CVM Gen 2 D5.2 Niveau 2 pour VRS","2016-03-11","Attente GO",null,null,"2016-03-07","DR","2016-03-17","FTR"]
["MCSH-3741-L-101047","AIT - MCSI","2016-01-06T15:01:04","SWES",null,null,"SYN_A3_EQP","_QUALITE : IND_QUAL (Indicateurs EQP et Réactivité) : A3 Synthèse EQP","2016-03-29","Attente GO",null,null,"2016-03-07","OTD","2016-04-01","FTR"]
["MCSH-7415-L-90788","EST - MCSI","2015-04-30T10:03:48","ELAC",null,null,"RT_SDP","X74E : GRPE_CLIM : Robustesse DFE pour TI","2015-12-11","Attente GO","2016-03-11","Retard fournisseur","2016-03-08","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-3934-L-98935","EST - MCSI","2015-11-12T16:32:38","ELAC",null,null,"RT_SDP","X74E : PULSEUR_AR : Contribution à la Revue Technique de schéma de principe","2015-12-18","Attente GO","2016-03-11","Retard fournisseur","2016-03-08","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-7363-L-96372","AIT - MCSI","2015-09-07T18:43:32","CSAC",null,null,"DO_CESARE","C84_Chine : CVM (C84) : Création de référence/Mise à jour CESARE BE CVM Gen 2 Niveau 2 pour stade TI (B2)","2016-03-08","Attente GO",null,null,"2016-03-08","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-3745-L-101256","AIT - MCSI","2016-01-08T03:18:16","SWES",null,null,"SYN_DC_ORGANE","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_SR-Push FSE Marquardt","2016-03-12","Attente GO",null,null,"2016-03-08","OTD","2016-04-01","FTR"]
["MCSH-7147-L-104035","AIT - MCSI","2016-03-01T13:14:32","CSAC",null,null,"OF_PIECE","G95_PH2 : RADAR GÉN3 (G95Ph2) : REC BOITIER ELECTRONIQUE RADAR AV ASS D5.3","2016-03-11","Attente GO",null,null,"2016-03-09","DR","2016-03-10","FTR"]
["MCSH-5891-L-93005","AIT - MCSI","2015-06-19T14:24:48","CSAC",null,null,"OF_PIECE","B618 : CVM (B618) : EL1 (F05.2017): Officialisation d'une pièce CVM2 Niveau3 (V-AEB SW5)","2016-03-15","Attente GO",null,null,"2016-03-10","OTD","2016-03-17","FTR"]
["MCSH-4192-L-76475","AIT - MCSI","2014-10-06T18:30:13","CSAC",null,null,"DO_CESARE","X81_Chine : CVM (X81_Chine) : Création de Référence / Maj CESARE pour EL2","2016-03-25","Attente GO",null,null,"2016-03-10","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7366-L-79423","EST - MCSI","2014-12-05T10:57:40","ELPS",null,null,"OF_DOTE","P1UO : SIRENE_LIN_SSCAS,RUPTEUR_CAPOT,MUS2 : DOTE pour EL2","2017-02-09","Attente GO",null,null,"2016-03-10","OTD","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-8161-L-104551","AIT - MCSI - SMEG","2016-03-11T15:02:16","IDEV",null,null,"OF_PIECE","_F09/2016 : SMEG+_I_V2 : Reconduction HW pour le projet A9x AEE2010 sur PRS7 en 6.3","2016-03-08","Attente GO",null,null,"2016-03-11","NDR","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-7467-L-81040","EST - MCSI","2014-12-18T22:18:58","ELPS",null,null,"DO_CDCI_BILAN","R82E,R83E : SIRENE_LIN_SSCAS,RUPTEUR_CAPOT,MUS2 : CDCI validé pour VRS1","2016-03-11","Attente GO",null,null,"2016-03-11","OTD","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-3745-L-104691","AIT - MCSI","2016-03-15T06:02:38","SWES",null,null,"SYN_DC_ORGANE","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_SR-BAE VALEO","2016-03-11","Attente GO",null,null,"2016-03-11","DR","2016-04-01","FTR"]
["MCSH-7366-L-103558","EST - MCSI","2016-02-18T03:04:10","ELPS",null,null,"OF_DOTE","P1UO : SIRENE_LIN_SSCAS,RUPTEUR_CAPOT,MUS2 : Officialisation de DOTE SIRENE","2016-03-15","Attente GO",null,null,"2016-03-11","DR","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-7366-L-103557","EST - MCSI","2016-02-18T15:03:37","ELPS",null,null,"OF_DOTE","P1UO : SIRENE_LIN_SSCAS,RUPTEUR_CAPOT,MUS2 : Officialisation de DOTE MUS2","2017-01-15","Attente GO",null,null,"2016-03-11","OTD","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-6604-L-76701","AIT - MCSI","2014-10-09T14:26:25","CSAC",null,null,"OF_DOTE","P1UO : RADAR GÉN3 (P1UO) : OCM VRS DV","2016-03-14","Attente GO",null,null,"2016-03-14","OTD","2016-03-18","FTR"]
["MCSH-8350-L-100739","EST - MCSI","2015-12-21T15:52:15","EACC",null,null,"OF_PIECE","A88_Chine : ANTENNE_BACKUP (A88_Chine) : Officialisation d'une pièce","2016-03-14","Attente GO","2016-03-04",null,"2016-03-14","OTD","2016-07-01","ACCEPTE_DEFAUT"]
["MCSH-5893-L-75554","AIT - MCSI","2014-09-16T09:00:33","CSAC",null,null,"DO_CESARE","P1MO : CVM (A88,P1MO) : Création de Référence / Maj CESARE BE CVM Gen 2 Niveau 1 pour stade PPV P1MO","2016-03-15","Attente GO",null,null,"2016-03-14","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-5893-L-86517","AIT - MCSI","2015-03-18T01:17:14","CSAC",null,null,"DO_CESARE","A88 : CVM (A88,P1MO) : Création de Référence / Maj CESARE BE CVM Gen 2 Niveau 1 pour stade PPV A88","2016-03-15","Attente GO",null,null,"2016-03-14","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-5893-L-103559","AIT - MCSI","2016-02-18T15:04:16","CSAC",null,null,"OF_PIECE","P1MO : CVM (A88,P1MO) : P1MO: Reconduction CVM niv1 D5.2 pour PPV","2016-03-15","Attente GO",null,null,"2016-03-14","DR","2016-03-17","FTR"]
["MCSH-7824-L-103272","EST - MCSI","2016-02-15T15:44:58","EACC",null,null,"DO_BE_CESARE","X74E,X74_Chine : AVE (X74E,X74_Chine) : Création /Mise à jour BE CESARE","2016-03-16","Attente GO",null,null,"2016-03-14","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-3745-L-101205","AIT - MCSI","2016-01-08T01:21:31","SWES",null,null,"SYN_A3_QUAL_ORG","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_A3-COM2008 Premium KOSTAL","2016-03-21","Attente GO",null,null,"2016-03-14","OTD","2016-04-01","FTR"]
["MCSH-3745-L-101217","AIT - MCSI","2016-01-08T01:22:18","SWES",null,null,"SYN_A3_QUAL_ORG","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_A3-COM2008 KOSTAL","2016-03-21","Attente GO",null,null,"2016-03-14","OTD","2016-04-01","FTR"]
["MCSH-5849-L-72761","EST - MCSI","2014-06-27T23:33:02","ELPS",null,null,"DO_CCA_VRS1","X81_Chine : FEU_AV : Fiche CCA phase 3 (validation et process)\r\n","2015-12-25","Attente GO","2016-03-15","Retard fournisseur","2016-03-15","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-5562-L-77394","EST - MCSI","2014-10-17T10:51:24","ELAC",null,null,"LIV_PARAM_GRP_RG_1","B618,MODULE_HAB05 : GRPE_CLIM : Réception du Fichier paramètrage  ADTH validé pour calibration 4 VRS2/VRSUT","2016-02-19","Attente GO","2016-03-18","Retard fournisseur","2016-03-15","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-5893-L-75555","AIT - MCSI","2014-09-16T09:00:33","CSAC",null,null,"OF_CAL","P1MO : CVM (A88,P1MO) : Calibration CVM Gen 2 Niveau 1 (D5.2) pour stade PPV P1MO","2016-03-15","Attente GO","2016-03-16",null,"2016-03-15","OTD","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-5893-L-75569","AIT - MCSI","2014-09-16T11:02:39","CSAC",null,null,"OF_CAL","A88 : CVM (A88,P1MO) : Calibration CVM Gen 2 (D5.2) Niveau 1 pour stade PPV A88","2016-03-15","Attente GO","2016-03-16",null,"2016-03-15","OTD","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-7266-L-103379","EST - MCSI","2016-02-16T08:39:35","EACC",null,null,"DO_CESARE","R83E,R83_Chine : AVE (R83E,R83_Chine) : Création de référence/Mise à jour CESARE","2016-03-15","Attente GO","2016-03-31","Retard fournisseur","2016-03-15","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-5893-L-103562","AIT - MCSI","2016-02-18T15:08:42","CSAC",null,null,"OF_PIECE","A88 : CVM (A88,P1MO) : A88: Reconduction CVM niv1 D5.2 pour PPV","2016-03-15","Attente GO",null,null,"2016-03-15","DR","2016-03-17","FTR"]
["MCSH-5849-L-72764","EST - MCSI","2014-06-27T23:33:02","ELPS",null,null,"DO_INC_VALID","X81_Chine : FEU_AV : Incontournables partie validation","2015-12-25","Attente GO","2016-03-30","Retard fournisseur","2016-03-16","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-5849-L-72767","EST - MCSI","2014-06-27T23:33:02","ELPS",null,null,"VAL_BILAN","X81_Chine : FEU_AV : Bilan Validation - Archvage des données","2016-01-10","Attente GO","2016-03-16","Retard fournisseur","2016-03-16","OTD","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-8063-L-95699","EST - MCSI","2015-08-14T10:43:36","ELAC",null,null,"RT_INIT_DOSSIER_DEV","R83E : CTP : Initi dossier DEV - Prise en compte des dossiers techniques Fnr - Appropriation des scénarios Pilote","2016-01-15","Attente GO","2016-03-18","Retard fournisseur","2016-03-17","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7480-L-92345","AIT - MCSI","2015-06-08T12:00:35","CSAC",null,null,"OF_PIECE","B751_3_4_MV : RADAR GÉN3 (B753_4  MV) : REC Assemblé Radar et ses fixations sur B753/1. (D5.3)","2016-03-18","Attente GO",null,null,"2016-03-17","OTD","2016-03-18","FTR"]
["MCSH-3540-L-93851","AIT - MCSI","2015-07-02T14:35:38","CSAC",null,null,"DO_CESARE","P8X,P8_Europe_VS_Fenetre : RADAR GÉN3 (P8X) : Livraison BE CESARE EL2","2016-03-18","Attente GO",null,null,"2016-03-17","OTD","2016-03-23","FTR"]
["MCSH-3540-L-95637","AIT - MCSI","2015-08-10T11:56:13","CSAC",null,null,"OF_CAL","P8X : RADAR GÉN3 (P8X) : CAL D5.3 EL2","2016-03-18","Attente GO",null,null,"2016-03-17","OTD","2016-03-18","FTR"]
["MCSH-7480-L-100328","AIT - MCSI","2015-12-14T11:22:09","CSAC",null,null,"OF_PIECE","B751_3_4_MV : RADAR GÉN3 (B753_4  MV) : REC Assemblé Radar et ses fixations sur B754. (D5.3)","2016-03-18","Attente GO",null,null,"2016-03-17","OTD","2016-03-18","FTR"]
["MCSH-7479-L-104843","AIT - MCSI","2016-03-17T15:05:43","CSAC",null,null,"DO_CESARE","B751_3_4_MV : CVM (B753_4  MV) : B753: Création de référence/Mise à jour CESARE - \r\nBE pour phase mulet","2016-03-18","Attente GO",null,null,"2016-03-17","DR","2016-03-17","FTR"]
["MCSH-7479-L-104844","AIT - MCSI","2016-03-17T15:05:57","CSAC",null,null,"DO_CESARE","B751_3_4_MV : CVM (B753_4  MV) : B754: Création de référence/Mise à jour CESARE - \r\nBE pour phase mulet","2016-03-18","Attente GO",null,null,"2016-03-17","DR","2016-03-17","FTR"]
["MCSH-7479-L-104651","AIT - MCSI","2016-03-15T11:37:18","CSAC",null,null,"OF_CAL","B751_3_4_MV : CVM (B753_4  MV) : B753: CAL CVM niv2 D5.1 pour mulet","2016-03-25","Attente GO",null,null,"2016-03-17","DR","2016-03-17","FTR"]
["MCSH-7479-L-104652","AIT - MCSI","2016-03-15T11:37:33","CSAC",null,null,"OF_CAL","B751_3_4_MV : CVM (B753_4  MV) : B754: CAL CVM niv2 D5.1 pour mulet","2016-03-25","Attente GO",null,null,"2016-03-17","DR","2016-03-17","FTR"]
["MCSH-5562-L-76933","EST - MCSI","2014-10-14T15:30:13","ELAC",null,null,"RT_CALIB","B618,MODULE_HAB05 : GRPE_CLIM : RT robustesse calibration BCC ->CAL 4 pour VRS2/VRSUT","2016-02-19","Attente GO","2016-03-18","Retard fournisseur","2016-03-18","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-3745-L-101182","AIT - MCSI","2016-01-08T01:11:30","SWES",null,null,"SYN_A3_QUAL_DOM","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_METIER_A3-EMCD","2016-03-16","Attente GO",null,null,"2016-03-18","OTD","2016-04-01","FTR"]
["MCSH-3745-L-101234","AIT - MCSI","2016-01-08T01:47:36","SWES",null,null,"SYN_DC_ORGANE","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_SR-Volant équipé","2016-03-16","Attente GO",null,null,"2016-03-18","OTD","2016-04-01","FTR"]
["MCSH-7480-L-92348","AIT - MCSI","2015-06-08T12:00:35","CSAC",null,null,"DO_CDCI_BILAN","B751_3_4_MV : RADAR GÉN3 (B753_4  MV) : Bilan des retours des CDCI","2016-03-18","Attente GO",null,null,"2016-03-18","OTD","2016-08-23","NOT FTR"]
["MCSH-7362-L-96398","AIT - MCSI","2015-09-08T09:54:00","CSAC",null,null,"OF_PIECE","C84_Chine : RADAR GÉN3 (C84) : REC : BOITIER ELECTRONIQUE RADAR AV ASS D5.3","2016-03-18","Attente GO",null,null,"2016-03-18","OTD","2016-03-18","FTR"]
["MCSH-7480-L-100330","AIT - MCSI","2015-12-14T11:22:09","CSAC",null,null,"DO_CDCI_BILAN","B751_3_4_MV : RADAR GÉN3 (B753_4  MV) : Bilan des retours des CDCI","2016-03-18","Attente GO",null,null,"2016-03-18","OTD","2016-08-23","NOT FTR"]
["MCSH-6604-L-102003","AIT - MCSI","2016-01-20T14:37:12","CSAC",null,null,"DO_CESARE","P1UO : RADAR GÉN3 (P1UO) : Livraison BE CESARE VRS0 (TMC0 au 20/01/16) ","2016-03-25","Attente GO",null,null,"2016-03-21","OTD","2016-03-31","FTR"]
["MCSH-7066-L-86458","AIT - MCSI","2015-03-18T11:19:55","CSAC",null,null,"OF_CAL","G95_PH2 : CVM (G95 Ph2) : CVM niv2 D5.2: Calibration pour VRS2","2016-03-31","Attente GO",null,null,"2016-03-21","OTD","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-7066-L-86457","AIT - MCSI","2015-03-18T11:19:55","CSAC",null,null,"DO_CESARE","G95_PH2 : CVM (G95 Ph2) : Création de référence/Mise à jour CESARE C5:\r\nCVM niv2 D5.2 pour VRS2","2016-04-15","Attente GO",null,null,"2016-03-21","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-4199-L-76658","AIT - MCSI","2014-10-09T13:56:08","CSAC",null,null,"DO_CESARE","X81_Chine : RADAR GÉN3 (X81C) : Livraison BE CESARE EL2","2016-03-25","Attente GO",null,null,"2016-03-22","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-3741-L-101136","AIT - MCSI","2016-01-08T11:57:49","SWES",null,null,"SYN_A3_ALTIS_REAC","_QUALITE : IND_QUAL (Indicateurs EQP et Réactivité) : A3 Synthèse Altis Réactivité","2016-03-29","Attente GO",null,null,"2016-03-22","OTD","2016-04-01","FTR"]
["MCSH-4199-L-76659","AIT - MCSI","2014-10-09T13:56:08","CSAC",null,null,"OF_CAL","X81_Chine : RADAR GÉN3 (X81C) : Calibration pour EL2","2016-03-25","Attente GO",null,null,"2016-03-23","OTD","2016-03-23","FTR"]
["MCSH-7479-L-92311","AIT - MCSI","2015-06-08T10:45:43","CSAC",null,null,"OF_PIECE","B751_3_4_MV : CVM (B753_4  MV) : B753: Officialisation Plan et 3D Fournisseur - Sans déviation","2016-03-25","Attente GO","2016-03-18",null,"2016-03-23","OTD","2016-04-26","ACCEPTE_DEFAUT"]
["MCSH-7479-L-97540","AIT - MCSI","2015-10-05T14:23:34","CSAC",null,null,"OF_PIECE","B751_3_4_MV : CVM (B753_4  MV) : B754: Officialisation Plan et 3D Fournisseur - Sans déviation","2016-03-25","Attente GO","2016-03-18",null,"2016-03-23","OTD","2016-03-24","FTR"]
["MCSH-6604-L-102002","AIT - MCSI","2016-01-20T14:12:17","CSAC",null,null,"OF_CAL","P1UO : RADAR GÉN3 (P1UO) : CALs VRS0 (TMC0 au 20/01/16) 'Non ACC","2016-03-25","Attente GO",null,null,"2016-03-23","OTD","2016-03-31","FTR"]
["MCSH-3745-L-101193","AIT - MCSI","2016-01-08T01:19:50","SWES",null,null,"SYN_A3_QUAL_ORG","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_A3-COM2008 Premium Valeo","2016-03-16","Attente GO",null,null,"2016-03-24","Retard","2016-04-01","FTR"]
["MCSH-7154-L-103242","AIT - MCSI","2016-02-15T11:28:51","CSAC",null,null,"OF_CAL","P1UO : CVM (P1UO) : Calibration CVM Gen 2 Niveau 1 (D5.2) pour VRS0/VRSDV","2016-03-25","Attente GO",null,null,"2016-03-24","DR","2016-04-12","FTR"]
["MCSH-7154-L-103254","AIT - MCSI","2016-02-15T11:31:39","CSAC",null,null,"OF_CAL","P1UO : CVM (P1UO) : Calibration CVM Gen 2 Niveau 2 (D5.2) pour VRS0/VRSDV","2016-03-25","Attente GO",null,null,"2016-03-24","DR","2016-04-12","FTR"]
["MCSH-7154-L-103256","AIT - MCSI","2016-02-15T11:33:39","CSAC",null,null,"OF_CAL","P1UO : CVM (P1UO) : Calibration CVM Gen 2 Niveau 3 V-AEB (SW4) pour VRS0/VRSDV","2016-03-25","Attente GO",null,null,"2016-03-24","DR","2016-04-12","FTR"]
["MCSH-7154-L-103262","AIT - MCSI","2016-02-15T11:41:56","CSAC",null,null,"DO_CESARE","P1UO : CVM (P1UO) : Création BE CVM Gen 2 niveau 2 pour stade VRSDV (update D5.2)","2016-03-25","Attente GO",null,null,"2016-03-24","DR","2016-04-12","FTR"]
["MCSH-8450-L-103792","AIT - MCSI","2016-02-25T08:35:40","CSAC",null,null,"DO_BE_CESARE","A88_Chine : CVM (A88Chine) : Création et livraison BE CESARE pour TI/DFNU","2016-03-25","Attente GO",null,null,"2016-03-24","DR","2016-04-12","FTR"]
["MCSH-3745-L-101262","AIT - MCSI","2016-01-08T03:26:57","SWES",null,null,"SYN_DC_ORGANE","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_SR-Ecran tactile","2016-03-18","Attente GO",null,null,"2016-03-25","Retard","2016-04-01","FTR"]
["MCSH-3745-L-101273","AIT - MCSI","2016-01-08T03:28:02","SWES",null,null,"SYN_DC_ORGANE","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_SR-Combiné","2016-03-19","Attente GO",null,null,"2016-03-25","Retard","2016-04-01","FTR"]
["MCSH-7154-L-103261","AIT - MCSI","2016-02-15T11:39:39","CSAC",null,null,"DO_CESARE","P1UO : CVM (P1UO) : Création BE CVM Gen 2 niveau 1 pour stade VRSDV (update D5.2)","2016-03-25","Attente GO",null,null,"2016-03-25","DR","2016-04-12","FTR"]
["MCSH-7154-L-103263","AIT - MCSI","2016-02-15T11:43:06","CSAC",null,null,"DO_CESARE","P1UO : CVM (P1UO) : Création BE CVM Gen 2 niveau 3 pour stade VRSDV (SW4)","2016-03-25","Attente GO",null,null,"2016-03-25","DR","2016-04-12","FTR"]
["MCSH-8450-L-103671","AIT - MCSI","2016-02-19T15:55:25","CSAC",null,null,"DO_CDCI_BILAN","A88_Chine : CVM (A88Chine) : Bilan des retours des CDCI","2016-03-25","Attente GO",null,null,"2016-03-25","DR","2016-04-12","FTR"]
["MCSH-4158-L-105022","EST - MCSI","2016-03-22T14:13:31","EEMS",null,null,"SYN_A3_QUAL_DOM","_RITUELS : _RITUEL_EEMS_Qualité : IQC_METIER_A3 Pole-EEMS","2016-04-01","Attente GO",null,null,"2016-03-25","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-4158-L-105476","EST - MCSI","2016-03-30T11:15:48","EEMS",null,null,"SYN_A3_QUAL_DOM","_RITUELS : _RITUEL_EEMS_Qualité : IQC_METIER_A3 Pole-EACH","2016-04-01","Attente GO",null,null,"2016-03-25","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-3036-L-105327","AIT - MCSI","2016-03-25T12:01:35","CSAC",null,null,"DO_CDCI_BILAN","B751_3_4_MV,B78_mi_vie,B81_Chine_Fenêtre_VS,C84_Chine,G95_PH2,K0,MODULE_EE02,P1UO,P84_Chine,P87_Chine,P8X,T9_MV,X81_Chine : RADAR GÉN3 : Synthèses d'avancement de toutes les implantation Radar / Fichier de pilotage interne et avec fournisseur.","2016-01-30","Attente GO","2016-03-29","Retard fournisseur","2016-03-28","DR","2016-04-29","ACCEPTE_DEFAUT"]
["MCSH-7482-L-80707","EST - MCSI","2014-12-16T15:24:57","ELPS",null,null,"OF_PIECE","K9 : SIRENE_LIN_SSCAS,RUPTEUR_CAPOT,MUS2 : DEF Rupteur Capot pour DFNu","2016-02-05","Attente GO","2016-04-05","Retard fournisseur","2016-03-28","OTD","2016-04-29","ACCEPTE_DEFAUT"]
["MCSH-7266-L-104120","EST - MCSI","2016-03-01T17:45:15","EACC",null,null,"RT_CDCI","R83E,R83_Chine : AVE (R83E,R83_Chine) : Revue technique de CDCI","2016-02-12","Attente GO","2016-03-28","Retard fournisseur","2016-03-28","DR","2016-04-29","ACCEPTE_DEFAUT"]
["MCSH-3745-L-101519","AIT - MCSI","2016-01-13T08:03:41","SWES",null,null,"SYN_DC_ORGANE","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_SR-CSV RADIO et RVV/LVV VALEO","2016-03-23","Attente GO",null,null,"2016-03-28","OTD","2016-04-01","FTR"]
["MCSH-3745-L-101530","AIT - MCSI","2016-01-13T08:04:04","SWES",null,null,"SYN_DC_ORGANE","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_SR-CSV RADIO et RVV/LVV DELPHI","2016-03-23","Attente GO",null,null,"2016-03-28","OTD","2016-04-01","FTR"]
["MCSH-7467-L-99531","EST - MCSI","2015-11-25T16:17:05","ELPS",null,null,"OF_PIECE","R83E : SIRENE_LIN_SSCAS,RUPTEUR_CAPOT,MUS2 : Officialisation d'une pièce Module\r\nRUPTEUR CAPOT","2016-03-28","Attente GO",null,null,"2016-03-28","OTD","2016-04-29","ACCEPTE_DEFAUT"]
["MCSH-3745-L-101228","AIT - MCSI","2016-01-08T01:38:45","SWES",null,null,"SYN_A3_QUAL_ORG","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_A3-COM2005 EV2-EV3 Delphi","2016-03-28","Attente GO",null,null,"2016-03-28","OTD","2016-04-01","FTR"]
["MCSH-3745-L-101172","AIT - MCSI","2016-01-08T01:08:47","SWES",null,null,"SYN_DC_ORGANE","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_SR-VCI DELPHI","2016-03-29","Attente GO",null,null,"2016-03-29","OTD","2016-04-01","FTR"]
["MCSH-3745-L-101504","AIT - MCSI","2016-01-13T07:58:39","SWES",null,null,"SYN_DC_ORGANE","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_SR-VCI Marquardt","2016-03-29","Attente GO",null,null,"2016-03-29","OTD","2016-04-01","FTR"]
["MCSH-2937-L-55481","EST - MCSI","2013-09-23T16:39:20","ELPS",null,null,"VAL_ANA_RAPP_ESSAIS","K0 : PROJ : Analyse rapport d'essai PV FNR","2015-12-31","Attente GO","2016-03-31","Retard fournisseur","2016-03-30","OTD","2016-04-26","FTR"]
["MCSH-3036-L-105323","AIT - MCSI","2016-03-25T11:53:12","CSAC",null,null,"SYN_ALTIS ","B751_3_4_MV,B78_mi_vie,B81_Chine_Fenêtre_VS,C84_Chine,G95_PH2,K0,MODULE_EE02,P1UO,P84_Chine,P87_Chine,P8X,T9_MV,X81_Chine : RADAR GÉN3 : Gestion Hebdomadaire Altis\r\n","2016-03-30","Attente GO",null,null,"2016-03-30","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-7400-L-89703","EST - MCSI","2015-04-22T16:58:35","ELPS",null,null,"VAL_ANA_PT_FNR","X74E : FEU_AV : Analyse Plan De Test FNR","2016-03-31","Attente GO","2016-03-31","Retard fournisseur","2016-03-31","OTD","2016-05-02","ACCEPTE_DEFAUT"]
["MCSH-7075-L-99736","AIT - MCSI","2015-12-01T03:25:15","CSAC",null,null,"OF_CAL","T9_MV : RADAR GÉN3 (T9MV) : CALs D5.3 pour VRS1 pour T91&T92 (Sans ACC & ACC BVM 30 DV5RC ML6C & ACC STOP DW10FC;AMN8 & ACC_STOP DW10FCD;AM6III)","2016-03-31","Attente GO","2016-04-01",null,"2016-03-31","OTD","2016-04-11","FTR"]
["MCSH-7075-L-99737","AIT - MCSI","2015-12-01T03:30:51","CSAC",null,null,"DO_CESARE","T9_MV : RADAR GÉN3 (T9MV) : livraison BEs D5.3 VRS1 pour T91&T92 (Sans ACC & ACC BVM 30 DV5RC ML6C & ACC STOP DW10FC;AMN8 & ACC_STOP DW10FCD;AM6III)","2016-03-31","Attente GO",null,null,"2016-03-31","OTD","2016-04-11","FTR"]
["MCSH-7814-L-102039","AIT - MCSI","2016-01-20T17:23:00","SWES",null,null,"VAL_DEMANDE_ESSAI","_QUALITE,MODULE_HAB10 : CSV DELPHI (dérive qualité - modif produit) : Si besoin demande essai interne PSA (VFME/PMXP). Lien demande essai PMXP : http://dsc.pcinfo.inetpsa.com/doc/3/0/0/9/7/2/5/0/8/portail_20241.htm. Lien vers demande essai VFME : http://docinfogroupe.inetpsa.com/ead/doc/ref.02015_11_00628/v.vc/fiche","2016-03-31","Attente GO",null,null,"2016-03-31","OTD","2016-04-29","FTR"]
["MCSH-7266-L-103380","EST - MCSI","2016-02-16T08:40:44","EACC",null,null,"OF_PIECE","R83_Chine : AVE (R83E,R83_Chine) : Officialisation d'une pièce","2016-02-29","Attente GO",null,null,"2016-04-01","NDR","2016-06-23","ACCEPTE_DEFAUT"]
["MCSH-3036-L-105328","AIT - MCSI","2016-03-25T12:01:35","CSAC",null,null,"DO_CDCI_BILAN","B751_3_4_MV,B78_mi_vie,B81_Chine_Fenêtre_VS,C84_Chine,G95_PH2,K0,MODULE_EE02,P1UO,P84_Chine,P87_Chine,P8X,T9_MV,X81_Chine : RADAR GÉN3 : Synthèses d'avancement de toutes les implantation Radar / Fichier de pilotage interne et avec fournisseur.","2016-02-29","Attente GO","2016-04-01","Retard fournisseur","2016-04-01","DR","2016-05-02","ACCEPTE_DEFAUT"]
["MCSH-8464-L-103574","EST - MCSI","2016-02-18T16:30:16","ELAC",null,null,"DO_FETE","_DMTRless_ELAC : RCP : FETE transmise au fournisseur","2016-03-10","Attente GO","2016-04-01","Retard fournisseur","2016-04-01","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-8480-L-103579","EST - MCSI","2016-02-18T16:43:18","ELAC",null,null,"DO_FETE","_DMTRless_ELAC : PULSEUR : FETE transmise au fournisseur","2016-03-15","Attente GO","2016-04-01","Retard fournisseur","2016-04-01","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-8481-L-103589","EST - MCSI","2016-02-18T17:03:44","ELAC",null,null,"DO_FETE","_DMTRless_ELAC : TDC_RF2 : FETE transmise au fournisseur","2016-03-15","Attente GO","2016-04-01","Retard fournisseur","2016-04-01","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-8482-L-103661","EST - MCSI","2016-02-19T14:51:24","ELAC",null,null,"DO_FETE","_DMTRless_ELAC : TDC_RFTA_CH/RF  : FETE transmise au fournisseur","2016-03-15","Attente GO","2016-04-01","Retard fournisseur","2016-04-01","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-7486-L-80754","EST - MCSI","2014-12-16T17:48:27","ELPS",null,null,"OF_PIECE","X74E : SIRENE_LIN_SSCAS,RUPTEUR_CAPOT,MUS2 : DEF Cheminement faisceau pour VRS1","2016-04-01","Attente GO",null,null,"2016-04-01","OTD","2016-05-02","ACCEPTE_DEFAUT"]
["MCSH-7486-L-80755","EST - MCSI","2014-12-16T17:48:27","ELPS",null,null,"OF_PIECE","X74E : SIRENE_LIN_SSCAS,RUPTEUR_CAPOT,MUS2 : DEF Rupteur Capot avec implantation définitive","2016-04-01","Attente GO",null,null,"2016-04-01","OTD","2016-05-02","ACCEPTE_DEFAUT"]
["MCSH-7266-L-104301","EST - MCSI","2016-03-04T15:50:11","EACC",null,null,"OF_PIECE","R83_Chine : AVE (R83E,R83_Chine) : Reconduction VIS FIXATION AVE Chine","2016-04-01","Attente GO",null,null,"2016-04-01","DR","2016-06-23","ACCEPTE_DEFAUT"]
["MCSH-4158-L-105023","EST - MCSI","2016-03-22T14:13:31","EEMS",null,null,"SYN_A3_QUAL_ORG","_RITUELS : _RITUEL_EEMS_Qualité : IQC_ORGANE_A3-ADML","2016-04-01","Attente GO",null,null,"2016-04-04","NDR",null,"ACCEPTE_DEFAUT"]
["MCSH-4158-L-105471","EST - MCSI","2016-03-30T11:09:34","EEMS",null,null,"SYN_A3_QUAL_ORG","_RITUELS : _RITUEL_EEMS_Qualité : IQC_ORGANE_A3-LVE/LVEAP","2016-04-01","Attente GO",null,null,"2016-04-04","NDR",null,"ACCEPTE_DEFAUT"]
["MCSH-4158-L-105472","EST - MCSI","2016-03-30T11:09:34","EEMS",null,null,"SYN_A3_QUAL_ORG","_RITUELS : _RITUEL_EEMS_Qualité : IQC_ORGANE_A3-RETROS","2016-04-01","Attente GO",null,null,"2016-04-04","NDR",null,"ACCEPTE_DEFAUT"]
["MCSH-4158-L-105473","EST - MCSI","2016-03-30T11:09:34","EEMS",null,null,"SYN_A3_QUAL_ORG","_RITUELS : _RITUEL_EEMS_Qualité : IQC_ORGANE_A3-SERRURES","2016-04-01","Attente GO",null,null,"2016-04-04","NDR",null,"ACCEPTE_DEFAUT"]
["MCSH-4158-L-105474","EST - MCSI","2016-03-30T11:09:34","EEMS",null,null,"SYN_A3_QUAL_ORG","_RITUELS : _RITUEL_EEMS_Qualité : IQC_ORGANE_A3-SIEGES","2016-04-01","Attente GO",null,null,"2016-04-04","NDR",null,"ACCEPTE_DEFAUT"]
["MCSH-4158-L-105475","EST - MCSI","2016-03-30T11:15:48","EEMS",null,null,"SYN_A3_QUAL_ORG","_RITUELS : _RITUEL_EEMS_Qualité : IQC_ORGANE_A3-EVAV","2016-04-01","Attente GO",null,null,"2016-04-04","NDR",null,"ACCEPTE_DEFAUT"]
["MCSH-4158-L-105913","EST - MCSI","2016-04-05T16:59:17","EEMS",null,null,"SYN_A3_QUAL_DOM","_RITUELS : _RITUEL_EEMS_Qualité : Extraction DC CLIM A9/B78/T9/EEE\t\r\n","2016-04-01","Attente GO",null,null,"2016-04-04","NDR",null,"ACCEPTE_DEFAUT"]
["MCSH-7400-L-89711","EST - MCSI","2015-04-22T16:58:35","ELPS",null,null,"RT_BILAN_HW","X74E : FEU_AV : Revue Technique de bilan de conception électronique","2016-04-04","Attente GO",null,null,"2016-04-04","OTD","2016-05-05","ACCEPTE_DEFAUT"]
["MCSH-7266-L-103376","EST - MCSI","2016-02-16T08:36:21","EACC",null,null,"OF_PIECE","R83E : AVE (R83E,R83_Chine) : Officialisation d'une pièce","2016-03-25","Attente GO","2016-04-05","Retard fournisseur","2016-04-05","DR","2016-07-18","ACCEPTE_DEFAUT"]
["MCSH-7773-L-104290","EST - MCSI","2016-03-04T09:21:08","EACC",null,null,"DO_CDCI_BILAN","X74E : ANTENNE_BACKUP (X74E) : Bilan des retours des CDCI\r\nANTENNE SECOURS ADML \r\n","2016-03-25","Attente GO","2016-04-06","Retard fournisseur","2016-04-06","DR","2016-05-09","ACCEPTE_DEFAUT"]
["MCSH-5891-L-104624","AIT - MCSI","2016-03-14T17:25:54","CSAC",null,null,"OF_CAL","B618 : CVM (B618) : PRSEL1 (F09.2016):\r\nOfficialisation d'une calibration CVM Gen 2 Niveau 1 (D5.2 post validation fnr)","2016-04-04","Attente GO","2016-04-07",null,"2016-04-06","DR","2016-05-09","ACCEPTE_DEFAUT"]
["MCSH-7366-L-80226","EST - MCSI","2014-12-15T15:05:55","ELPS",null,null,"DO_CESARE","P1UO : SIRENE_LIN_SSCAS,RUPTEUR_CAPOT,MUS2 : Livraison BE Cesare pour VRS1 (C4)","2016-04-07","Attente GO",null,null,"2016-04-06","OTD","2016-06-09","FTR"]
["MCSH-7773-L-86904","EST - MCSI","2015-03-23T10:08:03","EACC",null,null,"OF_PIECE","X74E : ANTENNE_BACKUP (X74E) : Reconduction de l'antenne passive sur X74€\r\nPhase OCM\r\npour la DAG","2016-04-29","Attente GO","2016-04-05",null,"2016-04-06","OTD","2016-07-01","ACCEPTE_DEFAUT"]
["MCSH-5891-L-106059","AIT - MCSI","2016-04-07T09:55:47","CSAC",null,null,"DO_CESARE","B618 : CVM (B618) : PRS EL1 (F09.2016): Création BE CVM Gen 2 Niveau 1 (D5.2d)","2016-04-08","Attente GO",null,null,"2016-04-07","DR","2016-04-12","FTR"]
["MCSH-7147-L-86494","AIT - MCSI","2015-03-18T13:08:58","CSAC",null,null,"DO_CESARE","G95_PH2 : RADAR GÉN3 (G95Ph2) : Livraison BE D5.3 VRS UT","2016-04-18","Attente GO",null,null,"2016-04-07","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-8450-L-103668","AIT - MCSI","2016-02-19T15:25:58","CSAC",null,null,"OF_PIECE","A88_Chine : CVM (A88Chine) : TI/DFNU: Reconduction CVM V-AEB SW4","2016-03-25","Attente GO","2016-04-15","Retard fournisseur","2016-04-08","DR","2016-04-12","FTR"]
["MCSH-7144-L-105905","EST - MCSI","2016-04-05T15:25:44","EACC",null,null,"OF_PIECE","R83C : ANTENNE_BACKUP (R8) : Officialisation d'une pièce : antenne passive R83Chine","2016-04-08","Attente GO",null,null,"2016-04-08","DR","2016-07-01","ACCEPTE_DEFAUT"]
["MCSH-8464-L-103576","EST - MCSI","2016-02-18T16:30:57","ELAC",null,null,"VAL_ANA_RAPP_ESSAIS","_DMTRless_ELAC : RCP : Analyse rapports d'essais FNR ou PSA.","2016-04-08","Attente GO","2016-04-29","Retard fournisseur","2016-04-08","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7147-L-86495","AIT - MCSI","2015-03-18T13:08:58","CSAC",null,null,"OF_CAL","G95_PH2 : RADAR GÉN3 (G95Ph2) : CAL D5.3 VRS UT","2016-04-18","Attente GO",null,null,"2016-04-08","OTD","2016-04-11","FTR"]
["MCSH-7989-L-94539","AIT - MCSI","2015-07-17T15:21:19","CSAC",null,null,"OF_CAL","P87_Chine : CVM (P87C) : Officialisation des calibrations CVM niv1 (VRS1)","2016-04-30","Attente GO",null,null,"2016-04-08","OTD","2016-04-12","FTR"]
["MCSH-7989-L-97454","AIT - MCSI","2015-10-05T08:39:32","CSAC",null,null,"OF_CAL","P87_Chine : CVM (P87C) : Officialisation des calibrations CVM niv2 (VRS1)","2016-04-30","Attente GO",null,null,"2016-04-08","OTD","2016-04-12","FTR"]
["MCSH-8161-L-105864","AIT - MCSI - SMEG","2016-04-04T10:48:39","IDEV",null,null,"OF_PIECE","_F09/2016 : SMEG+_I_V2 : Officialisation Module Hardware PRS 7.1 pour SW 6.30.C en AEE2010","2016-04-08","Attente GO",null,null,"2016-04-11","NDR","2016-05-12","ACCEPTE_DEFAUT"]
["MCSH-8161-L-105879","AIT - MCSI - SMEG","2016-04-04T17:36:16","IDEV",null,null,"OF_PIECE","_F09/2016 : SMEG+_I_V2 : Officialisation module Hardware en PRS 7.1 SW 6.30.C en AEE2004 1 ISO","2016-04-08","Attente GO",null,null,"2016-04-11","NDR","2016-05-12","ACCEPTE_DEFAUT"]
["MCSH-8161-L-105880","AIT - MCSI - SMEG","2016-04-04T17:38:58","IDEV",null,null,"OF_PIECE","_F09/2016 : SMEG+_I_V2 : Officialisation HW PRS 7.1 SW 6.30.C en AEE2004 2ISO","2016-04-08","Attente GO",null,null,"2016-04-11","NDR","2016-05-12","ACCEPTE_DEFAUT"]
["MCSH-3540-L-93857","AIT - MCSI","2015-07-02T14:38:07","CSAC",null,null,"DO_CESARE","P8X : RADAR GÉN3 (P8X) : Livraison BE D5.3 CESARE EL 0 (TMC 7 selon FSP V16)","2016-04-12","Attente GO",null,null,"2016-04-12","OTD","2016-04-13","FTR"]
["MCSH-3540-L-93858","AIT - MCSI","2015-07-02T14:38:07","CSAC",null,null,"OF_CAL","P8X : RADAR GÉN3 (P8X) : CAL D5.3 EL 0 (TMC 7 selon FSP V16) ","2016-04-12","Attente GO",null,null,"2016-04-12","OTD","2016-04-13","FTR"]
["MCSH-3036-L-105329","AIT - MCSI","2016-03-25T12:01:35","CSAC",null,null,"DO_CDCI_BILAN","B751_3_4_MV,B78_mi_vie,B81_Chine_Fenêtre_VS,C84_Chine,G95_PH2,K0,MODULE_EE02,P1UO,P84_Chine,P87_Chine,P8X,T9_MV,X81_Chine : RADAR GÉN3 : Synthèses d'avancement de toutes les implantation Radar / Fichier de pilotage interne et avec fournisseur.","2016-03-31","Attente GO","2016-04-15","Retard fournisseur","2016-04-13","DR","2016-05-16","ACCEPTE_DEFAUT"]
["MCSH-7156-L-92384","EST - MCSI","2015-06-08T14:47:25","EACC",null,null,"VAL_ANA_PV_FNR","D34E,R82E,R83E,R83_Chine,X83_Chine,MODULE_CPE09 : RETRO_EXT : Analyse du planning de validation fournisseur","2015-09-01","Attente GO","2016-02-19","Retard fournisseur","2016-04-14","Retard","2016-04-14","NOT FTR"]
["MCSH-8567-L-105463","AIT - MCSI","2016-03-30T10:48:40","CSAC",null,null,"OF_PIECE","R83_Chine : NIGHT VISION (R83 Chine) : Offi CAMERA VISION INFRAROUGE pour phase DFNu","2016-04-15","Attente GO",null,null,"2016-04-14","DR","2016-05-16","ACCEPTE_DEFAUT"]
["MCSH-8224-L-98884","AIT - MCSI","2015-11-10T10:24:19","SWES",null,null,"DO_FETE","MODULE_HAB10,M33_Iran_Full_Speed : COM2005_EV3 (DELPHI: REC M3 Iran) : FETE transmise au fournisseur","2015-11-27","Attente GO","2016-04-15","Retard fournisseur","2016-04-15","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-926-L-87584","EST - MCSI","2015-03-31T07:03:49","ELAC",null,null,"DO_DIVERS","_PLANEE,_PM0500_Connaissance,_METIER : _ANALYSE_CONCURRENCE : Solutions de chauffage / refroidissement sur vhl HY et VE : Dossier d'analyse concurrence  préliminaire pour Juillet 2015, finalisé pour Novembre 2015","2015-11-30","Attente GO","2016-04-23","Retard fournisseur","2016-04-15","OTD","2016-04-21","FTR"]
["MCSH-7156-L-92392","EST - MCSI","2015-06-08T14:47:25","EACC",null,null,"DO_CCA_TOPHW","D34E,R82E,R83E,R83_Chine,X83_Chine,MODULE_CPE09 : RETRO_EXT : Fiche CCA phase 2 (conception)","2016-03-14","Attente GO","2016-04-15","Retard fournisseur","2016-04-15","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-8481-L-103591","EST - MCSI","2016-02-18T17:03:44","ELAC",null,null,"DO_PLAN_DEV_FNR","_DMTRless_ELAC : TDC_RF2 : Planning FNR de développement organe","2016-03-15","Attente GO","2016-04-22","Retard fournisseur","2016-04-15","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-8481-L-103595","EST - MCSI","2016-02-18T17:03:44","ELAC",null,null,"VAL_ANA_PV_FNR","_DMTRless_ELAC : TDC_RF2 : Analyse du planning de validation fournisseur","2016-03-15","Attente GO","2016-04-22","Retard fournisseur","2016-04-15","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-6555-L-65054","EST - MCSI","2014-02-21T14:19:28","ELAC",null,null,"LIV_ORG","A88,MODULE_HAB05,P1MO : GRPE_CLIM : Livraison organe pour recette C4","2016-04-15","Attente GO",null,null,"2016-04-15","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-3745-L-101183","AIT - MCSI","2016-01-08T01:11:30","SWES",null,null,"SYN_A3_QUAL_DOM","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_METIER_A3-EMCD","2016-04-15","Attente GO",null,null,"2016-04-15","OTD","2016-04-15","FTR"]
["MCSH-3745-L-101235","AIT - MCSI","2016-01-08T01:47:36","SWES",null,null,"SYN_DC_ORGANE","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_SR-Volant équipé","2016-04-15","Attente GO",null,null,"2016-04-15","OTD","2016-04-29","FTR"]
["MCSH-6206-L-81188","EST - MCSI","2014-12-19T13:42:16","EACC",null,null,"VAL_ANA_PT_FNR","B618,B81,B8_Mi_Vie,MODULE_CPE09,W2_VS : RETRO_EXT : Analyse Plan De Test FNR","2015-09-01","Attente GO","2016-03-11","Retard fournisseur","2016-04-18","Retard","2016-04-25","FTR"]
["MCSH-7824-L-103530","EST - MCSI","2016-02-18T09:55:46","EACC",null,null,"DO_CDCI_BILAN","X74E,X74_Chine : AVE (X74E,X74_Chine) : Bilan des retours des CDCI\r\nANTIVOL ELECTRIQUE DIRECTION (AVE)","2016-03-25","Attente GO","2016-04-18","Retard fournisseur","2016-04-18","DR","2016-05-19","ACCEPTE_DEFAUT"]
["MCSH-3745-L-101194","AIT - MCSI","2016-01-08T01:19:50","SWES",null,null,"SYN_A3_QUAL_ORG","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_A3-COM2008 Premium Valeo","2016-04-15","Attente GO",null,null,"2016-04-18","OTD","2016-04-29","FTR"]
["MCSH-3745-L-101263","AIT - MCSI","2016-01-08T03:26:57","SWES",null,null,"SYN_DC_ORGANE","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_SR-Ecran tactile","2016-04-17","Attente GO",null,null,"2016-04-18","OTD","2016-04-29","FTR"]
["MCSH-3745-L-101274","AIT - MCSI","2016-01-08T03:28:02","SWES",null,null,"SYN_DC_ORGANE","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_SR-Combiné","2016-04-18","Attente GO",null,null,"2016-04-18","OTD","2016-04-29","FTR"]
["MCSH-7479-L-92340","AIT - MCSI","2015-06-08T10:45:43","CSAC",null,null,"OF_CAL","B751_3_4_MV : CVM (B753_4  MV) : B751-3: Pour VRS0","2016-04-25","Attente GO",null,null,"2016-04-18","OTD","2016-05-13","FTR"]
["MCSH-7467-L-81042","EST - MCSI","2014-12-18T22:18:58","ELPS",null,null,"OF_PIECE","R83E : SIRENE_LIN_SSCAS,RUPTEUR_CAPOT,MUS2 : DEF Cheminement faisceau pour VRS1","2016-03-20","Attente GO","2016-04-19","Retard fournisseur","2016-04-19","OTD","2016-05-20","ACCEPTE_DEFAUT"]
["MCSH-7467-L-81043","EST - MCSI","2014-12-18T22:18:58","ELPS",null,null,"OF_PIECE","R83E : SIRENE_LIN_SSCAS,RUPTEUR_CAPOT,MUS2 : DEF Rupteur Capot avec implantation définitive","2016-03-20","Attente GO","2016-04-19","Retard fournisseur","2016-04-19","OTD","2016-05-20","ACCEPTE_DEFAUT"]
["MCSH-4093-L-105724","AIT - MCSI","2016-03-31T17:57:20","SWES",null,null,"OF_PIECE","B753_Chine : BVMP (Rec B75x_Chine) : Officialisation d'une pièce - add paddle shift (BVMP) on B753 ML project","2016-04-15","Attente GO","2016-04-19",null,"2016-04-19","DR","2016-05-20","ACCEPTE_DEFAUT"]
["MCSH-5751-L-80288","EST - MCSI","2014-12-15T16:46:12","ELAC",null,null,"DO_INC_VALID","P8X : TDC AR : Incontournables partie validation","2016-04-22","Attente GO",null,null,"2016-04-19","OTD","2016-06-10","FTR"]
["MCSH-2937-L-55453","EST - MCSI","2013-09-23T16:39:20","ELPS",null,null,"RT_PASS_DEV_MET","K0 : PROJ : Revue de passation du développement vers le métier en fin de développement","2016-03-01","Attente GO","2016-04-20","Retard fournisseur","2016-04-20","OTD","2016-05-23","ACCEPTE_DEFAUT"]
["MCSH-8562-L-106401","AIT - MCSI","2016-04-11T14:14:50","SWES",null,null,"DO_DEROG","MODULE_HAB10 : COM200X_CSV (DELPHI: rupture appro flex) : Mettre le lien vers la dérogation/Statut. A valider avec les usines","2016-04-20","Attente GO",null,null,"2016-04-20","DR","2016-04-29","FTR"]
["MCSH-7824-L-103277","EST - MCSI","2016-02-15T04:04:59","EACC",null,null,"OF_PIECE","X74E : AVE (X74E,X74_Chine) : Officialisation d'une pièce ","2016-04-22","Attente GO",null,null,"2016-04-20","OTD","2016-07-18","ACCEPTE_DEFAUT"]
["MCSH-6825-L-103390","AIT - MCSI","2016-02-16T10:43:04","CSAC",null,null,"DO_CESARE","B78_mi_vie : RADAR GÉN3 (B78 MV) : Livraison BE CESARE D5.3 pour MDL","2016-04-22","Attente GO",null,null,"2016-04-20","OTD","2016-05-13","FTR"]
["MCSH-5849-L-72768","EST - MCSI","2014-06-27T23:33:02","ELPS",null,null,"RT_PASS_DEV_MET","X81_Chine : FEU_AV : Fin Développement ","2016-08-01","Attente GO",null,null,"2016-04-20","OTD","2016-05-23","ACCEPTE_DEFAUT"]
["MCSH-3745-L-101206","AIT - MCSI","2016-01-08T01:21:31","SWES",null,null,"SYN_A3_QUAL_ORG","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_A3-COM2008 Premium KOSTAL","2016-04-20","Attente GO",null,null,"2016-04-21","OTD","2016-04-29","FTR"]
["MCSH-3745-L-101218","AIT - MCSI","2016-01-08T01:22:18","SWES",null,null,"SYN_A3_QUAL_ORG","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_A3-COM2008 KOSTAL","2016-04-20","Attente GO",null,null,"2016-04-21","OTD","2016-04-29","FTR"]
["MCSH-7813-L-102076","AIT - MCSI","2016-01-20T17:53:32","SWES",null,null,"DO_PLAN_DEV_FNR","_QUALITE,HAB10 : CSV VALEO (dérive qualité - renouvellement outillage) : Planning FNR de développement organe","2016-04-22","Attente GO","2016-04-22","Retard fournisseur","2016-04-21","OTD","2016-04-29","FTR"]
["MCSH-5736-L-80443","EST - MCSI","2014-12-15T22:07:48","ELPS",null,null,"DO_CCA_VAL","X81_Chine : PROJ : Fiche CCA phase 3 (validation et process)\r\n","2016-02-08","Attente GO",null,null,"2016-04-22","Retard",null,"ACCEPTE_DEFAUT"]
["MCSH-7746-L-99184","EST - MCSI","2015-11-17T11:08:54","EACC",null,null,"DO_CCA_TOPHW","K9 : POMPES_LV_LP : Fiche CCA phase 2 (conception)","2016-04-18","Attente GO",null,null,"2016-04-22","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-3745-L-101520","AIT - MCSI","2016-01-13T08:03:41","SWES",null,null,"SYN_DC_ORGANE","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_SR-CSV RADIO et RVV/LVV VALEO","2016-04-22","Attente GO",null,null,"2016-04-25","OTD","2016-04-29","FTR"]
["MCSH-3745-L-101531","AIT - MCSI","2016-01-13T08:04:04","SWES",null,null,"SYN_DC_ORGANE","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_SR-CSV RADIO et RVV/LVV DELPHI","2016-04-22","Planifié",null,null,"2016-04-25","OTD","2016-04-29","FTR"]
["MCSH-6825-L-103389","AIT - MCSI","2016-02-16T10:41:27","CSAC",null,null,"OF_CAL","B78_mi_vie : RADAR GÉN3 (B78 MV) : CAL MDL D5.3","2016-04-22","Planifié","2016-04-25","Retard fournisseur","2016-04-25","OTD","2016-05-13","FTR"]
["MCSH-7479-L-96816","AIT - MCSI","2015-09-16T04:43:56","CSAC",null,null,"OF_CAL","B751_3_4_MV : CVM (B753_4  MV) : B754: Pour VRS1","2016-04-25","Planifié",null,null,"2016-04-25","OTD","2016-05-13","FTR"]
["MCSH-8464-L-103573","EST - MCSI","2016-02-18T16:30:16","ELAC",null,null,"DO_ALTIS","_DMTRless_ELAC : RCP : Mise à jour ALTIS (EE ou Qualité)","2016-04-25","Planifié","2016-04-29","Retard fournisseur","2016-04-25","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-3540-L-105315","AIT - MCSI","2016-03-25T11:00:52","CSAC",null,null,"OF_CAL","P8X : RADAR GÉN3 (P8X) : MAJ CALs pour EL2 MDL","2016-04-29","Planifié",null,null,"2016-04-25","DR","2016-05-13","FTR"]
["MCSH-7479-L-107744","AIT - MCSI","2016-05-13T14:11:26","CSAC",null,null,"OF_CAL","B751_3_4_MV : CVM (B753_4  MV) : Mise à jour cas d'emploi de la nomenclature CAL CVM B75MV","2016-05-04","Planifié",null,null,"2016-04-25","DR","2016-05-13","FTR"]
["MCSH-3540-L-105314","AIT - MCSI","2016-03-25T11:00:26","CSAC",null,null,"DO_CESARE","P8X,P8_Europe_VS_Fenetre : RADAR GÉN3 (P8X) : Livraison BE CESARE EL2 MDL","2016-04-29","Planifié",null,null,"2016-04-26","DR","2016-05-13","FTR"]
["MCSH-6611-L-101687","EST - MCSI","2016-01-13T15:51:35","ELPS",null,null,"OF_PIECE","P1MO : RUPTEUR_CAPOT,SIRENE_LIN_SSCAS,MUS2 (Rec. P1MO) : Officialisation d'une pièce RUPTEUR CAPOT 760mm","2016-02-03","Planifié","2016-03-28","Retard fournisseur","2016-04-27","NDR","2016-05-30","ACCEPTE_DEFAUT"]
["MCSH-6608-L-101690","EST - MCSI","2016-01-13T15:55:28","ELPS",null,null,"OF_PIECE","A88 : SIRENE_LIN_SSCAS,MUS2,RUPTEUR_CAPOT : Officialisation d'une pièce RUPTEUR CAPOT 760mm","2016-02-03","Planifié","2016-03-28","Retard fournisseur","2016-04-27","NDR","2016-05-30","ACCEPTE_DEFAUT"]
["MCSH-4158-L-106637","EST - MCSI","2016-04-15T15:55:02","EEMS",null,null,"SYN_A3_QUAL_DOM","_RITUELS : _RITUEL_EEMS_Qualité : IQC_METIER_A3 Pole-EEMS","2016-04-29","Planifié",null,null,"2016-04-28","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-6604-L-76697","AIT - MCSI","2014-10-09T14:26:25","CSAC",null,null,"OF_CAL","P1UO : RADAR GÉN3 (P1UO) : CALs VRS DV (VRS1/TMC1 selon planning du 20/01/16)","2016-05-02","Planifié",null,null,"2016-04-28","OTD","2016-05-13","FTR"]
["MCSH-6604-L-76700","AIT - MCSI","2014-10-09T14:26:25","CSAC",null,null,"DO_CESARE","P1UO : RADAR GÉN3 (P1UO) : Livraison BEs VRS DV (VRS1/TMC1 selon planning du 20/01/16)","2016-05-02","Planifié",null,null,"2016-04-28","OTD","2016-05-13","FTR"]
["MCSH-7186-L-92251","EST - MCSI","2015-06-08T09:28:39","EACC",null,null,"DO_CCA_TOPHW","B618,R82E,R83E : POMPES_LV_LP : Fiche CCA phase 2 (conception)","2016-03-14","Planifié","2016-04-29","Retard fournisseur","2016-04-29","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-925-L-106008","EST - MCSI","2016-04-06T02:53:01","ELAC",null,null,"DO_DIVERS","_METIER,_QUALITE : _QUALITE : Indicateurs qualité ELAC d'Avril(données de Mars)","2016-04-15","Planifié","2016-05-13","Retard fournisseur","2016-04-29","DR","2016-08-23","NOT FTR"]
["MCSH-3741-L-101137","AIT - MCSI","2016-01-08T11:57:49","SWES",null,null,"SYN_A3_ALTIS_REAC","_QUALITE : IND_QUAL (Indicateurs EQP et Réactivité) : A3 Synthèse Altis Réactivité","2016-04-28","Planifié",null,null,"2016-04-29","OTD","2016-05-27","FTR"]
["MCSH-3745-L-101173","AIT - MCSI","2016-01-08T01:08:47","SWES",null,null,"SYN_DC_ORGANE","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_SR-VCI Marquardt","2016-04-28","Planifié",null,null,"2016-04-29","OTD","2016-05-27","FTR"]
["MCSH-3745-L-101493","AIT - MCSI","2016-01-13T07:51:51","SWES",null,null,"SYN_DC_ORGANE","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_SR-VCI DELPHI","2016-04-28","Planifié",null,null,"2016-04-29","OTD","2016-05-27","FTR"]
["MCSH-3039-L-98394","AIT - MCSI","2015-10-21T05:42:10","CSAC",null,null,"SYN_ALTIS ","A88,A88_Chine,B618,B751_3_4_MV,B78_mi_vie,B81_Chine_Fenêtre_VS,C84_Chine,F3,G95_PH2,K0,K0_Russie,MODULE_EE02,P1MO,P1UO,P84_Chine,P87_Chine,P8X,T9_MV,X81_Chine : CVM : Synthèse Altis","2016-04-29","Planifié",null,null,"2016-04-29","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-3036-L-105324","AIT - MCSI","2016-03-25T11:53:12","CSAC",null,null,"SYN_ALTIS ","B751_3_4_MV,B78_mi_vie,B81_Chine_Fenêtre_VS,C84_Chine,G95_PH2,K0,MODULE_EE02,P1UO,P84_Chine,P87_Chine,P8X,T9_MV,X81_Chine : RADAR GÉN3 : Gestion Hebdomadaire Altis\r\n","2016-04-29","Planifié",null,null,"2016-04-29","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-7479-L-105384","AIT - MCSI","2016-03-29T16:43:01","CSAC",null,null,"OF_PIECE","B751_3_4_MV : CVM (B753_4  MV) : B751-3MV: Modification de la position CVM","2016-04-29","Planifié","2016-04-29",null,"2016-04-29","DR","2016-05-13","FTR"]
["MCSH-7479-L-105385","AIT - MCSI","2016-03-29T16:43:12","CSAC",null,null,"OF_PIECE","B751_3_4_MV : CVM (B753_4  MV) : B754MV: Modification de la position CVM","2016-04-29","Planifié","2016-04-29",null,"2016-04-29","DR","2016-05-13","FTR"]
["MCSH-8464-L-103575","EST - MCSI","2016-02-18T16:30:16","ELAC",null,null,"DO_PEPP","_DMTRless_ELAC : RCP : PEPP 2 Industrialisation","2016-04-29","Planifié",null,null,"2016-04-29","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7989-L-94538","AIT - MCSI","2015-07-17T15:21:09","CSAC",null,null,"OF_DOTE","P87_Chine : CVM (P87C) : Officialisation de DOTE (VRS DV)","2016-04-30","Planifié",null,null,"2016-04-29","OTD","2016-05-13","FTR"]
["MCSH-7989-L-94540","AIT - MCSI","2015-07-17T15:21:32","CSAC",null,null,"DO_CESARE","P87_Chine : CVM (P87C) : Création de référence/Mise à jour CESARE BE CVM Gen 2 Niveau 1 pour (VRS-DV)","2016-04-30","Planifié",null,null,"2016-04-29","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7989-L-97455","AIT - MCSI","2015-10-05T08:46:26","CSAC",null,null,"DO_CESARE","P87_Chine : CVM (P87C) : Création de référence/Mise à jour CESARE BE CVM Gen 2 Niveau 2 pour (VRS-DV)","2016-04-30","Planifié",null,null,"2016-04-29","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-3036-L-105330","AIT - MCSI","2016-03-25T12:01:35","CSAC",null,null,"DO_CDCI_BILAN","B751_3_4_MV,B78_mi_vie,B81_Chine_Fenêtre_VS,C84_Chine,G95_PH2,K0,MODULE_EE02,P1UO,P84_Chine,P87_Chine,P8X,T9_MV,X81_Chine : RADAR GÉN3 : Synthèses d'avancement de toutes les implantation Radar / Fichier de pilotage interne et avec fournisseur.","2016-04-30","Planifié",null,null,"2016-04-29","DR","2016-05-30","ACCEPTE_DEFAUT"]
["MCSH-6555-L-105345","EST - MCSI","2016-03-25T02:51:12","ELAC",null,null,"OF_PIECE","P1MO : GRPE_CLIM : Officialisation du faisceau CH","2016-04-30","Planifié",null,null,"2016-04-29","DR","2016-05-30","ACCEPTE_DEFAUT"]
["MCSH-6555-L-105346","EST - MCSI","2016-03-25T02:51:29","ELAC",null,null,"OF_PIECE","P1MO : GRPE_CLIM : Officialisation du faisceau RF","2016-04-30","Planifié",null,null,"2016-04-29","DR","2016-05-30","ACCEPTE_DEFAUT"]
["MCSH-3536-L-61684","AIT - MCSI","2014-01-09T04:38:57","CSAC",null,null,"OF_CAL","P8X : VISIO_PARK (P8) : Officialisation d'une calibration : CAL VP2 pour P84","2016-05-09","Planifié",null,null,"2016-04-29","OTD","2016-05-30","ACCEPTE_DEFAUT"]
["MCSH-6206-L-81189","EST - MCSI","2014-12-19T13:42:16","EACC",null,null,"VAL_ANA_PV_FNR","B618,B81,B8_Mi_Vie,MODULE_CPE09,W2_VS : RETRO_EXT : Analyse du planning de validation fournisseur","2015-08-14","Planifié","2016-05-06","Retard fournisseur","2016-05-02","OTD","2016-05-02","FTR"]
["MCSH-7746-L-99185","EST - MCSI","2015-11-17T11:08:54","EACC",null,null,"DO_INC_CONCEPT","K9 : POMPES_LV_LP : Incontournables partie conception","2016-03-01","Planifié","2016-05-06","Retard fournisseur","2016-05-02","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7186-L-92252","EST - MCSI","2015-06-08T09:28:39","EACC",null,null,"DO_INC_CONCEPT","B618,R82E,R83E : POMPES_LV_LP : Incontournables partie conception","2016-03-14","Planifié","2016-05-06","Retard fournisseur","2016-05-02","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7156-L-92393","EST - MCSI","2015-06-08T14:47:25","EACC",null,null,"DO_INC_CONCEPT","D34E,R82E,R83E,R83_Chine,X83_Chine,MODULE_CPE09 : RETRO_EXT : Incontournables partie conception","2016-03-14","Planifié","2016-05-06","Retard fournisseur","2016-05-02","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-4127-L-85645","EST - MCSI","2015-03-03T10:40:18","EACC",null,null,"DO_CCA_VAL","C84_Export,MODULE_CPE09,P1UO,P8X,X74E : RETRO_EXT : Fiche CCA phase 3 (validation et process)\r\n","2016-03-21","Planifié","2016-05-06","Retard fournisseur","2016-05-02","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-8246-L-106470","AIT - MCDV","2016-04-12","HDTC",null,null,"OF_PIECE","_TOUS : _TRAVAUX_CAO : Officialisation d'une pièce","2016-04-29","Planifié",null,null,"2016-05-02","NDR","2016-06-03","ACCEPTE_DEFAUT"]
["MCSH-8246-L-106471","AIT - MCDV","2016-04-12","HDTC",null,null,"OF_PIECE","_TOUS : _TRAVAUX_CAO : Officialisation d'une pièce","2016-04-29","Planifié",null,null,"2016-05-02","NDR","2016-06-03","ACCEPTE_DEFAUT"]
["MCSH-3745-L-106750","AIT - MCSI","2016-04-19T11:38:35","SWES",null,null,"SYN_A3_QUAL_ORG","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_bilan requètes","2016-05-02","Planifié",null,null,"2016-05-02","DR","2016-05-27","FTR"]
["MCSH-6643-L-84047","AIT - MCSI","2015-02-12T09:18:01","CSAC",null,null,"OF_DOTE","P1UO : AAS,CPK,SAM (P1UO) : Pour Stade OCM VRS1 (C4)","2016-05-02","Planifié",null,null,"2016-05-02","OTD","2016-05-18","FTR"]
["MCSH-3536-L-84778","AIT - MCSI","2015-02-19T13:17:05","CSAC",null,null,"DO_CESARE","P8X : VISIO_PARK (P8) : Création de Référence / Maj CESARE pour EL2","2016-05-09","Planifié",null,null,"2016-05-03","OTD","2016-06-29","FTR"]
["MCSH-6641-L-80523","EST - MCSI","2014-12-15T22:43:47","ELPS",null,null,"SDF_NS","P1UO : FEUX_AR : Avis et Synthèse SDF sur organe","2016-05-05","Planifié",null,null,"2016-05-05","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-3745-L-101264","AIT - MCSI","2016-01-08T03:26:57","SWES",null,null,"SYN_DC_ORGANE","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_SR-Ecran tactile","2016-05-17","Planifié",null,null,"2016-05-05","OTD","2016-05-27","FTR"]
["MCSH-3745-L-101275","AIT - MCSI","2016-01-08T03:28:02","SWES",null,null,"SYN_DC_ORGANE","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_SR-Combiné","2016-05-18","Planifié",null,null,"2016-05-05","OTD","2016-05-27","FTR"]
["MCSH-8246-L-104532","AIT - MCDV","2016-03-10","HDTC",null,null,"OF_PIECE","_TOUS : _TRAVAUX_CAO : création et officialisation de référence FNR support faisceau capteur Nox pour EMP2 DW dépoll €6.2 DAD, et rattachement au FCT 9813405180","2016-04-22","Planifié",null,null,"2016-05-09","Retard","2016-06-10","ACCEPTE_DEFAUT"]
["MCSH-7034-L-106770","AIT - MCSI","2016-04-20T09:18:04","CSAC",null,null,"OF_CAL","B78_mi_vie : CVM (B78_mi_vie) : Calibration D5.2d + corrections FOV pour MDL","2016-05-02","Planifié","2016-05-09",null,"2016-05-09","DR","2016-05-13","NOT FTR"]
["MCSH-7034-L-106771","AIT - MCSI","2016-04-20T09:35:50","CSAC",null,null,"DO_CESARE","B78_mi_vie : CVM (B78_mi_vie) : BE CVM niv2 en soft D5.2d (MDL)","2016-05-02","Planifié","2016-05-09","Retard fournisseur","2016-05-09","DR","2016-05-13","FTR"]
["MCSH-4192-L-106769","AIT - MCSI","2016-04-20T08:50:21","CSAC",null,null,"DO_CESARE","X81_Chine : CVM (X81_Chine) : BE CVM niv 2 en soft D5.2d (EL2)","2016-05-04","Planifié","2016-05-09","Retard fournisseur","2016-05-09","DR","2016-05-13","FTR"]
["MCSH-3533-L-106783","AIT - MCSI","2016-04-20T10:50:28","CSAC",null,null,"DO_CESARE","P8X : CVM (P8) : P84 (MDL): BE D5.2d niv1 & 2 incluant nouvelle CAL","2016-04-29","Planifié","2016-05-13","Retard fournisseur","2016-05-10","DR","2016-05-13","FTR"]
["MCSH-4192-L-106768","AIT - MCSI","2016-04-20T08:37:39","CSAC",null,null,"OF_CAL","X81_Chine : CVM (X81_Chine) : Calibration D5.2d + corrections FOV pour EL2","2016-05-04","Planifié","2016-05-13",null,"2016-05-10","DR","2016-05-13","FTR"]
["MCSH-3745-L-101236","AIT - MCSI","2016-01-08T01:47:36","SWES",null,null,"SYN_DC_ORGANE","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_SR-Volant équipé","2016-05-15","Planifié",null,null,"2016-05-10","OTD","2016-05-27","FTR"]
["MCSH-3533-L-106774","AIT - MCSI","2016-04-20T10:19:25","CSAC",null,null,"OF_CAL","P8X : CVM (P8) : P84 (MDL-TMC16): Officialisation CAL CVM niv1 et niv2 D5.2d + corrections FOV","2016-05-06","Planifié","2016-05-16",null,"2016-05-11","DR","2016-05-13","FTR"]
["MCSH-6555-L-105344","EST - MCSI","2016-03-25T14:50:51","ELAC",null,null,"OF_PIECE","P1MO : GRPE_CLIM : Officialisation faisceau RFTA","2016-05-20","Planifié",null,null,"2016-05-11","OTD","2016-05-12","FTR"]
["MCSH-3533-L-106785","AIT - MCSI","2016-04-20T10:53:07","CSAC",null,null,"DO_CESARE","P8X : CVM (P8) : P84 (EL2-Flotte): BE SW5c VAEB incluant nouvelle CAL","2016-05-27","Planifié",null,null,"2016-05-11","DR","2016-05-13","FTR"]
["MCSH-3540-L-107155","AIT - MCSI","2016-04-25T03:33:16","CSAC",null,null,"OF_CAL","P8X : RADAR GÉN3 (P8X) : Nouvelle MAJ CALs pour MDL (Correctif pour test NCAP pieton 10 km/h)","2016-05-12","Planifié",null,null,"2016-05-12","DR","2016-05-13","FTR"]
["MCSH-3540-L-107157","AIT - MCSI","2016-04-25T03:33:34","CSAC",null,null,"DO_CESARE","P8X,P8_Europe_VS_Fenetre : RADAR GÉN3 (P8X) : Nouvell Livraison BE CESARE MDL (Correctif pour test NCAP pieton 10 km/h)","2016-05-12","Planifié",null,null,"2016-05-12","DR","2016-05-13","FTR"]
["MCSH-7164-L-77086","AIT - MCSI","2014-10-15T10:49:19","CSAC",null,null,"DO_CESARE","P84_Chine : RADAR GÉN3 (P84_C) : Livraison BE CESARE EL1","2016-05-13","Planifié",null,null,"2016-05-12","OTD","2016-05-13","FTR"]
["MCSH-3132-L-107275","EST - MCSI","2016-04-29T08:22:36","ELPS",null,null,"OF_DOTE","K0 : CAPT_ALARME (Adapt K0) : Officialisation de DOTE MUS1 K0","2016-05-13","Planifié",null,null,"2016-05-12","DR","2016-05-30","FTR"]
["MCSH-3533-L-106775","AIT - MCSI","2016-04-20T10:24:27","CSAC",null,null,"OF_CAL","P8X : CVM (P8) : P84 (EL2-flotte): Officialisation CAL CVM VAEB SW5c + corrections FOV","2016-05-27","Planifié",null,null,"2016-05-12","DR","2016-05-13","FTR"]
["MCSH-5616-L-106211","EST - MCSI","2016-04-07T15:09:30","ELAC",null,null,"DO_DIVERS","_METIER : LDA / référentiel technique CLIM : MàJ checklist avis métier (lien ADO)","2016-05-06","Planifié",null,null,"2016-05-13","NDR","2016-05-17","FTR"]
["MCSH-7164-L-77087","AIT - MCSI","2014-10-15T10:49:19","CSAC",null,null,"OF_CAL","P84_Chine : RADAR GÉN3 (P84_C) : Calibration pour EL1","2016-05-13","Planifié",null,null,"2016-05-13","OTD","2016-05-13","FTR"]
["MCSH-3745-L-101184","AIT - MCSI","2016-01-08T01:11:30","SWES",null,null,"SYN_A3_QUAL_DOM","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_METIER_A3-EMCD","2016-05-13","Planifié",null,null,"2016-05-13","OTD","2016-07-04","FTR"]
["MCSH-925-L-106007","EST - MCSI","2016-04-06T02:52:05","ELAC",null,null,"DO_DIVERS","_METIER,_QUALITE : _QUALITE : Indicateurs qualité ELAC de Mai (données de Avril)","2016-05-13","Planifié",null,null,"2016-05-13","DR","2016-06-14","FTR"]
["MCSH-926-L-106206","EST - MCSI","2016-04-07T15:06:00","ELAC",null,null,"DO_DIVERS","_PLANEE,_PM0500_Connaissance,_METIER : _ANALYSE_CONCURRENCE : Analyse concurrence tableau de commande clim à câble (focus par marque, niveau de gamme et zone géographique).","2016-05-13","Planifié",null,null,"2016-05-13","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-8629-L-107743","EST - MCSI","2016-05-13T13:36:39","EACC",null,null,"RT_PASS_MET_DEV","B73_Russie,B73_Russie_Mi_Vie,T73_Russie_VS_MV : POMPES_LV_LP : Revue de passation métier->Développement","2016-05-13","Planifié",null,null,"2016-05-13","DR","2016-06-14","ACCEPTE_DEFAUT"]
["MCSH-7064-L-77067","AIT - MCSI","2014-10-15T10:44:44","CSAC",null,null,"DO_CESARE","P84_Chine : CVM (P84_C) : Création de référence/Mise à jour Cesare\r\nBE CVM Gen 2 Niveau 1 & 2 pour le stade EL1","2016-05-20","Planifié","2016-05-20","Retard fournisseur","2016-05-13","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7400-L-89712","EST - MCSI","2015-04-22T16:58:35","ELPS",null,null,"DO_CCA_TOPHW","X74E : FEU_AV : Fiche CCA phase 2 (conception)","2016-05-27","Planifié",null,null,"2016-05-13","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-5865-L-55390","EST - MCSI","2013-09-20T11:18:07","ELPS",null,null,"OF_DOTE","P8X : SIRENE_LIN_SSCAS (Adapt. P8) : Officialisation de DOTE SIR pour les EL1 de P87","2016-06-15","Planifié",null,null,"2016-05-13","OTD","2016-06-14","ACCEPTE_DEFAUT"]
["MCSH-8546-L-104797","EST - MCSI","2016-03-17T08:55:34","EACC",null,null,"OF_PIECE","A9x_Iran : AVM : Officialisation d'une pièce","2016-07-01","Planifié",null,null,"2016-05-13","OTD","2016-07-01","ACCEPTE_DEFAUT"]
["MCSH-7480-L-100354","AIT - MCSI","2015-12-14T02:25:02","CSAC",null,null,"DO_CESARE","B751_3_4_MV : RADAR GÉN3 (B753_4  MV) : Livraison BEs VRS 0","2016-05-20","Planifié",null,null,"2016-05-16","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7480-L-100353","AIT - MCSI","2015-12-14T02:23:56","CSAC",null,null,"OF_CAL","B751_3_4_MV : RADAR GÉN3 (B753_4  MV) : Calibration pour VRS0","2016-05-20","Planifié",null,null,"2016-05-17","OTD","2016-05-25","FTR"]
["MCSH-7590-L-107571","AIT - MCSI","2016-05-11T13:40:53","SWES",null,null,"OF_PIECE","T9_MV : CSV (VS_A5x_T9x_noir HZD et blanc sonic) : Officialisation d'une pièce - RVV T9","2016-05-20","Planifié",null,null,"2016-05-17","DR","2016-06-17","FTR"]
["MCSH-8562-L-106399","AIT - MCSI","2016-04-11T14:14:50","SWES",null,null,"DO_DDM","MODULE_HAB10 : COM200X_CSV (DELPHI: rupture appro flex) : Processus GDM + PEPP via altis TE","2016-04-15","Planifié","2016-05-18","Retard fournisseur","2016-05-18","DR","2016-06-17","FTR"]
["MCSH-8562-L-106402","AIT - MCSI","2016-04-11T14:14:50","SWES",null,null,"DO_PLAN_DEV_FNR","MODULE_HAB10 : COM200X_CSV (DELPHI: rupture appro flex) : Planning FNR de développement organe","2016-04-22","Planifié","2016-05-18","Retard fournisseur","2016-05-18","DR","2016-06-17","FTR"]
["MCSH-3533-L-106786","AIT - MCSI","2016-04-20T10:55:41","CSAC",null,null,"DO_CESARE","P8X : CVM (P8) : P87 (EL0): BE D5.2d niv1 & 2 incluant nouvelle CAL","2016-05-20","Planifié","2016-05-20","Retard fournisseur","2016-05-18","DR","2016-05-19","FTR"]
["MCSH-8480-L-103581","EST - MCSI","2016-02-18T16:43:18","ELAC",null,null,"DO_PLAN_DEV_FNR","_DMTRless_ELAC : PULSEUR : Planning FNR de développement organe","2016-03-15","Planifié","2016-05-20","Retard fournisseur","2016-05-19","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-7987-L-105821","EST - MCSI","2016-04-01T11:31:57","ELPS",null,null,"DO_EDS","D34E : FEU_AV : Renseigner OPHELIE EDS robuste","2016-04-15","Planifié","2016-05-20","Retard fournisseur","2016-05-19","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-3533-L-106776","AIT - MCSI","2016-04-20T10:41:12","CSAC",null,null,"OF_CAL","P8X : CVM (P8) : P87 (EL0 - TMC8): Officialisation CAL CVM niv1 et niv2 D5.2d + corrections FOV","2016-05-20","Planifié","2016-05-20",null,"2016-05-19","DR","2016-05-19","FTR"]
["MCSH-7064-L-77068","AIT - MCSI","2014-10-15T10:44:44","CSAC",null,null,"OF_CAL","P84_Chine : CVM (P84_C) : Calibration CVM Gen 2 Niveau 1 & 2 pour EL1","2016-05-13","Planifié","2016-05-20","Retard fournisseur","2016-05-20","OTD","2016-06-21","ACCEPTE_DEFAUT"]
["MCSH-7479-L-92324","AIT - MCSI","2015-06-08T10:45:43","CSAC",null,null,"DO_CESARE","B751_3_4_MV : CVM (B753_4  MV) : B751-3: Création de référence/Mise à jour CESARE pour VRS0","2016-05-20","Planifié",null,null,"2016-05-20","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7479-L-92325","AIT - MCSI","2015-06-08T10:45:43","CSAC",null,null,"OF_DOTE","B751_3_4_MV : CVM (B753_4  MV) : B75x: Pour VRS0","2016-05-20","Planifié",null,null,"2016-05-20","OTD","2016-06-21","ACCEPTE_DEFAUT"]
["MCSH-8050-L-95072","AIT - MCSI","2015-07-27T08:59:37","CSAC",null,null,"OF_PIECE","X74E : CVP (X74E) : Officialisation Plan et 3D Fournisseur - Sans déviation","2016-05-20","Planifié",null,null,"2016-05-20","OTD","2016-06-01","FTR"]
["MCSH-7479-L-96822","AIT - MCSI","2015-09-16T04:49:56","CSAC",null,null,"DO_CESARE","B751_3_4_MV : CVM (B753_4  MV) : B754: Création de référence/Mise à jour CESARE pour VRS1","2016-05-20","Planifié",null,null,"2016-05-20","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-3745-L-101219","AIT - MCSI","2016-01-08T01:22:18","SWES",null,null,"SYN_A3_QUAL_ORG","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_A3-COM2008 KOSTAL","2016-05-20","Planifié",null,null,"2016-05-20","OTD","2016-06-17","FTR"]
["MCSH-3745-L-101521","AIT - MCSI","2016-01-13T08:03:41","SWES",null,null,"SYN_DC_ORGANE","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_SR-CSV RADIO et RVV/LVV VALEO","2016-05-22","Planifié",null,null,"2016-05-20","OTD","2016-05-27","FTR"]
["MCSH-3745-L-101532","AIT - MCSI","2016-01-13T08:04:04","SWES",null,null,"SYN_DC_ORGANE","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_SR-CSV RADIO et RVV/LVV DELPHI","2016-05-22","Planifié",null,null,"2016-05-20","OTD","2016-05-27","FTR"]
["MCSH-5893-L-107405","AIT - MCSI","2016-05-03T09:03:38","CSAC",null,null,"DO_CESARE","P1MO : CVM (A88,P1MO) : BE CVM Gen 2 Niveau 1 pour stade PPV P1MO (DàG)","2016-05-23","Planifié","2016-05-16","Retard fournisseur","2016-05-20","DR","2016-06-14","FTR"]
["MCSH-5893-L-107406","AIT - MCSI","2016-05-03T09:05:10","CSAC",null,null,"DO_CESARE","P1MO : CVM (A88,P1MO) : BE CVM Gen 2 Niveau 1 pour stade PPV P1MO (DàD)","2016-05-23","Planifié","2016-05-16","Retard fournisseur","2016-05-20","DR","2016-06-14","FTR"]
["MCSH-5893-L-107407","AIT - MCSI","2016-05-03T09:06:39","CSAC",null,null,"DO_CESARE","A88 : CVM (A88,P1MO) : BE CVM Gen 2 Niveau 1 pour stade PPV A88 (DàG)","2016-05-23","Planifié","2016-05-20","Retard fournisseur","2016-05-20","DR","2016-06-14","FTR"]
["MCSH-5893-L-107409","AIT - MCSI","2016-05-03T09:14:28","CSAC",null,null,"DO_CESARE","A88 : CVM (A88,P1MO) : BE CVM Gen 2 Niveau 1 pour stade PPV A88 (DàD)","2016-05-23","Planifié","2016-05-16","Retard fournisseur","2016-05-20","DR","2016-06-14","FTR"]
["MCSH-7066-L-86464","AIT - MCSI","2015-03-18T11:19:55","CSAC",null,null,"OF_DOTE","G95_PH2 : CVM (G95 Ph2) : Pour Stade EL1","2016-06-13","Planifié",null,null,"2016-05-21","OTD","2016-06-22","ACCEPTE_DEFAUT"]
["MCSH-7253-L-87216","EST - MCSI","2015-03-25T15:45:15","EACC",null,null,"DO_FC_VRS","R82E,R83E : LUCH : Fiches composants pour SDP VRS","2016-01-29","Planifié","2016-05-27","Retard fournisseur","2016-05-23","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7001-L-92237","EST - MCSI","2015-06-08T09:20:17","EACC",null,null,"DO_FC_VRS","R82E,R83E : PARE_BRISE_CHAUFFANT : Fiches composants pour SDP VRS","2016-02-08","Planifié","2016-05-27","Retard fournisseur","2016-05-23","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-3745-L-101174","AIT - MCSI","2016-01-08T01:08:47","SWES",null,null,"SYN_DC_ORGANE","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_SR-VCI Marquardt","2016-05-28","Planifié",null,null,"2016-05-23","OTD","2016-05-27","FTR"]
["MCSH-3745-L-101494","AIT - MCSI","2016-01-13T07:52:54","SWES",null,null,"SYN_DC_ORGANE","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_SR-VCI DELPHI","2016-05-28","Planifié",null,null,"2016-05-23","OTD","2016-05-27","FTR"]
["MCSH-7366-L-107538","EST - MCSI","2016-05-09T13:40:04","ELPS",null,null,"OF_PIECE","P1UO : SIRENE_LIN_SSCAS,RUPTEUR_CAPOT,MUS2 : Officialisation d'une pièce Rupteur capot P1UO","2016-05-29","Planifié",null,null,"2016-05-23","DR","2016-05-30","FTR"]
["MCSH-8262-L-107370","EST - MCSI","2016-05-03T08:13:46","EACC",null,null,"DO_CESARE","P87_Chine : AVE (P8 et P8C) : Création de référence/Mise à jour CESARE","2016-05-30","Planifié",null,null,"2016-05-23","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-2985-L-34631","EST - MCSI","2012-12-17T17:44:32","EACC",null,null,"VAL_ANA_RAPP_ESSAIS","K0,MODULE_CPE09 : RETRO_EXT : Analyse rapports d'essais FNR ou PSA.","2015-11-13","Planifié","2016-06-30","Retard fournisseur","2016-05-25","OTD","2016-05-30","FTR"]
["MCSH-5893-L-107297","AIT - MCSI","2016-04-29T15:06:16","CSAC",null,null,"OF_CAL","P1MO : CVM (A88,P1MO) : Calibration CVM Gen 2 Niveau 1 (soft D5.2d) pour stade PPV P1MO version DàG (LHD)","2016-05-23","Planifié","2016-05-27",null,"2016-05-25","DR","2016-06-14","FTR"]
["MCSH-5893-L-107298","AIT - MCSI","2016-04-29T15:14:40","CSAC",null,null,"OF_CAL","P1MO : CVM (A88,P1MO) : Calibration CVM Gen 2 Niveau 1 (soft D5.2d) pour stade PPV P1MO version DàD (RHD)","2016-05-23","Planifié","2016-05-27",null,"2016-05-25","DR","2016-06-14","FTR"]
["MCSH-5893-L-107299","AIT - MCSI","2016-04-29T15:17:18","CSAC",null,null,"OF_CAL","A88 : CVM (A88,P1MO) : Calibration CVM Gen 2 Niveau 1 (soft D5.2d) pour stade PPV A88 version DàG (LHD)","2016-05-23","Planifié","2016-05-25",null,"2016-05-25","DR","2016-06-14","FTR"]
["MCSH-5893-L-107300","AIT - MCSI","2016-04-29T15:19:31","CSAC",null,null,"OF_CAL","A88 : CVM (A88,P1MO) : Calibration CVM Gen 2 Niveau 1 (soft D5.2d) pour stade PPV A88 version DàD (RHD)","2016-05-23","Planifié","2016-05-27",null,"2016-05-25","DR","2016-06-14","FTR"]
["MCSH-8480-L-103582","EST - MCSI","2016-02-18T16:43:18","ELAC",null,null,"VAL_ANA_PT_FNR","_DMTRless_ELAC : PULSEUR : Analyse Plan De Test FNR","2016-04-15","Planifié","2016-05-26","Retard fournisseur","2016-05-26","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-3934-L-76590","EST - MCSI","2014-10-08T11:54:21","ELAC",null,null,"LIV_ORG","MODULE_HAB06,P8X,X74E : PULSEUR_AR : Livraison organe pour recette  D5","2016-05-12","Planifié","2016-05-27","Retard fournisseur","2016-05-26","OTD","2016-06-10","FTR"]
["MCSH-3533-L-108449","AIT - MCSI","2016-06-03T11:23:28","CSAC",null,null,"DO_CESARE","P8X : CVM (P8) : P84 (EL2-Flotte): BE SW5d pour VAEB 0.3g","2016-05-26","Planifié",null,null,"2016-05-26","DR","2016-06-14","FTR"]
["MCSH-7990-L-94689","AIT - MCSI","2015-07-22T13:17:14","CSAC",null,null,"OF_DOTE","P87_Chine : RADAR GÉN3 (P87C) : DOTE VRS DV","2016-05-30","Planifié",null,null,"2016-05-26","OTD","2016-06-02","FTR"]
["MCSH-3533-L-104875","AIT - MCSI","2016-03-18T14:57:42","CSAC",null,null,"DO_CESARE","P8X : CVM (P8) : P87 (EL0): BE SW5.1 VAEB incluant nouvelle CAL","2016-06-13","Planifié","2016-05-20","Retard fournisseur","2016-05-26","OTD","2016-06-14","FTR"]
["MCSH-8064-L-98606","EST - MCSI","2015-11-02T15:19:34","ELAC",null,null,"VAL_ANA_PV_FNR","R83E,X74E : SONDE : Analyse du planning de validation fournisseur","2016-04-29","Planifié","2016-05-31","Retard fournisseur","2016-05-27","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-3745-L-101195","AIT - MCSI","2016-01-08T01:19:50","SWES",null,null,"SYN_A3_QUAL_ORG","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_A3-COM2008 Premium Valeo","2016-05-15","Planifié",null,null,"2016-05-27","Retard","2016-06-17","FTR"]
["MCSH-3745-L-101207","AIT - MCSI","2016-01-08T01:21:31","SWES",null,null,"SYN_A3_QUAL_ORG","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_A3-COM2008 Premium KOSTAL","2016-05-20","Planifié",null,null,"2016-05-27","Retard","2016-06-17","FTR"]
["MCSH-8490-L-106412","AIT - MCSI","2016-04-11T14:33:35","SWES",null,null,"DO_DDM","MODULE_HAB10,M3M4_MV : COM2005EV3 (DELPHI: gestion M3/M4-MV) : Processus GDM + PEPP via altis TE","2016-05-20","Planifié","2016-05-27","Retard fournisseur","2016-05-27","DR","2016-06-17","FTR"]
["MCSH-8657-L-108299","EST - MCSI","2016-05-26T13:40:14","ELAC",null,null,"VAL_MOYEN","P8X : RCP : Création/Modification de moyen (outil de test, Chaine Organique (CO), maquette ICR ou homologation…)","2016-05-26","Planifié",null,null,"2016-05-27","NDR",null,"ACCEPTE_DEFAUT"]
["MCSH-7520-L-104594","AIT - MCSI","2016-03-14T15:40:34","CSAC",null,null,"OF_PIECE","K9 : CVP (K9) : Officialisation d'une pièce : Caméras 130 et 180 pour véhicule L1","2016-05-27","Planifié",null,null,"2016-05-27","OTD","2016-06-28","ACCEPTE_DEFAUT"]
["MCSH-4158-L-108043","EST - MCSI","2016-05-23T14:44:27","EEMS",null,null,"SYN_A3_QUAL_DOM","_RITUELS : _RITUEL_EEMS_Qualité : Point DC_ELAC","2016-05-27","Planifié",null,null,"2016-05-27","DR","2016-07-04","NOT FTR"]
["MCSH-4158-L-108044","EST - MCSI","2016-05-23T14:44:27","EEMS",null,null,"SYN_A3_QUAL_ORG","_RITUELS : _RITUEL_EEMS_Qualité : Point DC_ELPS","2016-05-27","Planifié",null,null,"2016-05-27","DR","2016-07-04","NOT FTR"]
["MCSH-4158-L-108748","EST - MCSI","2016-06-10T15:39:10","EEMS",null,null,"SYN_DC_ORGANE","_RITUELS : _RITUEL_EEMS_Qualité : Extraction DC CLIM A9/B78/T9/EEE","2016-05-27","Planifié",null,null,"2016-05-27","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-3741-L-101138","AIT - MCSI","2016-01-08T11:57:49","SWES",null,null,"SYN_A3_ALTIS_REAC","_QUALITE : IND_QUAL (Indicateurs EQP et Réactivité) : A3 Synthèse Altis Réactivité","2016-05-28","Planifié",null,null,"2016-05-27","OTD","2016-06-17","FTR"]
["MCSH-3036-L-105325","AIT - MCSI","2016-03-25T11:53:12","CSAC",null,null,"SYN_ALTIS ","B751_3_4_MV,B78_mi_vie,B81_Chine_Fenêtre_VS,C84_Chine,G95_PH2,K0,MODULE_EE02,P1UO,P84_Chine,P87_Chine,P8X,T9_MV,X81_Chine : RADAR GÉN3 : Gestion Hebdomadaire Altis\r\n","2016-05-29","Planifié",null,null,"2016-05-27","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-5891-L-102347","AIT - MCSI","2016-01-27T09:17:33","CSAC",null,null,"OF_CAL","B618 : CVM (B618) : VRS UT (F05.2017): Officialisation d'une calibration CVM Gen 2 Niveau 3 (V-AEB SW5.1)","2016-06-03","Planifié","2016-05-16",null,"2016-05-27","OTD","2016-06-14","FTR"]
["MCSH-5891-L-102351","AIT - MCSI","2016-01-27T09:57:32","CSAC",null,null,"DO_CESARE","B618 : CVM (B618) : EL1 (F05.2017): Création BE CVM Gen 2 Niveau 3 (SW5)","2016-06-03","Planifié",null,null,"2016-05-27","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-5893-L-99171","AIT - MCSI","2015-11-16T18:46:19","CSAC",null,null,"OF_CAL","P1MO : CVM (A88,P1MO) : Calibration CVM Gen 2 Niveau 3 (SW4b) pour stade PPV1 P1MO version DàG (LHD)","2016-06-13","Planifié","2016-05-16",null,"2016-05-27","OTD","2016-06-14","FTR"]
["MCSH-5893-L-99172","AIT - MCSI","2015-11-16T18:54:27","CSAC",null,null,"OF_CAL","A88 : CVM (A88,P1MO) : Calibration CVM Gen 2 Niveau 3 (SW4b) pour stade PPV1 A88 version DàG (LHD)","2016-06-13","Planifié","2016-05-16",null,"2016-05-27","OTD","2016-06-14","FTR"]
["MCSH-5893-L-99173","AIT - MCSI","2015-11-16T19:06:02","CSAC",null,null,"DO_CESARE","P1MO : CVM (A88,P1MO) : BE CVM Gen 2 VAEB pour stade PPV P1MO (DàG)","2016-06-13","Planifié","2016-05-16","Retard fournisseur","2016-05-27","OTD","2016-06-14","FTR"]
["MCSH-5893-L-99174","AIT - MCSI","2015-11-16T19:08:17","CSAC",null,null,"DO_CESARE","A88 : CVM (A88,P1MO) : BE CVM Gen 2 VAEB pour stade PPV A88 (DàG)","2016-06-13","Planifié","2016-05-16","Retard fournisseur","2016-05-27","OTD","2016-06-14","FTR"]
["MCSH-5893-L-107301","AIT - MCSI","2016-04-29T15:26:22","CSAC",null,null,"OF_CAL","P1MO : CVM (A88,P1MO) : Calibration CVM Gen 2 Niveau 3 (SW4b) pour stade PPV1 P1MO version DàD (RHD)","2016-06-13","Planifié","2016-05-16",null,"2016-05-27","OTD","2016-06-14","FTR"]
["MCSH-5893-L-107302","AIT - MCSI","2016-04-29T15:28:55","CSAC",null,null,"OF_CAL","A88 : CVM (A88,P1MO) : Calibration CVM Gen 2 Niveau 3 (SW4b) pour stade PPV1 A88 version DàD (RHD)","2016-06-13","Planifié","2016-05-16",null,"2016-05-27","OTD","2016-06-14","FTR"]
["MCSH-5893-L-107403","AIT - MCSI","2016-05-03T08:59:00","CSAC",null,null,"DO_CESARE","A88 : CVM (A88,P1MO) : BE CVM Gen 2 VAEB pour stade PPV A88 (DàD)","2016-06-13","Planifié","2016-05-16","Retard fournisseur","2016-05-27","DR","2016-06-14","FTR"]
["MCSH-5893-L-107404","AIT - MCSI","2016-05-03T09:00:59","CSAC",null,null,"DO_CESARE","P1MO : CVM (A88,P1MO) : BE CVM Gen 2 VAEB pour stade PPV P1MO (DàD)","2016-06-13","Planifié","2016-05-16","Retard fournisseur","2016-05-27","DR","2016-06-14","FTR"]
["MCSH-7066-L-86460","AIT - MCSI","2015-03-18T11:19:55","CSAC",null,null,"DO_CESARE","G95_PH2 : CVM (G95 Ph2) : BE CVM niv2 D5.2d pour PRSEL1","2016-06-15","Planifié",null,null,"2016-05-27","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-4158-L-108042","EST - MCSI","2016-05-23T14:44:27","EEMS",null,null,"SYN_A3_QUAL_ORG","_RITUELS : _RITUEL_EEMS_Qualité : Point_DC_EACC","2016-05-28","Planifié",null,null,"2016-05-28","DR","2016-07-04","NOT FTR"]
["MCSH-1030-L-102969","EST - MCSI","2016-02-11T10:03:35","ECPC",null,null,"OF_PIECE","R83E : PDPC_4LVI_RE_RA_ME_MUX,PDPC_4LVI_RE_RA_MUX : Officialisation FNR(REC) BT PDPC 4LVI RE RA MEMO MUX et 4LVI RE RA MUX","2016-05-13","Planifié","2016-05-31","Retard fournisseur","2016-05-30","OTD","2016-07-01","ACCEPTE_DEFAUT"]
["MCSH-3533-L-107976","AIT - MCSI","2016-05-20T10:50:00","CSAC",null,null,"OF_CAL","P8X : CVM (P8) : P84 (flotte PRSEL2): Officialisation CAL CVM VAEB SW5d avec AEB 0,3g","2016-05-27","Planifié","2016-05-30",null,"2016-05-30","DR","2016-06-14","FTR"]
["MCSH-4226-L-108314","EST - MCSI","2016-05-27T13:37:53","EACC",null,null,"DO_CDCI_BILAN","A88,A88_Chine,B618,B78_mi_vie,C84_Chine,K0,K9,MODULE_EE11,P1MO,P1UO,P8X,R83E,T9_MV,X74E,X7RR,X81_Chine : ANTENNE_BACKUP : Bilan des retours des CDCI : CDCI Applicatifs D34","2016-06-06","Planifié",null,null,"2016-05-30","DR","2016-07-01","ACCEPTE_DEFAUT"]
["MCSH-7066-L-86461","AIT - MCSI","2015-03-18T11:19:55","CSAC",null,null,"OF_CAL","G95_PH2 : CVM (G95 Ph2) : CVM niv2: Calibration pour EL1","2016-06-10","Planifié",null,null,"2016-05-30","OTD","2016-07-01","ACCEPTE_DEFAUT"]
["MCSH-3533-L-99711","AIT - MCSI","2015-11-30T09:35:13","CSAC",null,null,"OF_CAL","P8X : CVM (P8) : P87 (EL0): Officialisation CAL CVM VAEB SW5c + corrections FOV","2016-06-13","Planifié","2016-05-20",null,"2016-05-30","OTD","2016-06-14","FTR"]
["MCSH-8161-L-103257","AIT - MCSI - SMEG","2016-02-15T11:35:06","IDEV",null,null,"OF_CAL","MODULE_EE07 : SMEG+_I_V2 : Officialisation des calibrations 6.3.B","2016-05-27","Planifié",null,null,"2016-05-31","OTD","2016-07-01","ACCEPTE_DEFAUT"]
["MCSH-3039-L-98395","AIT - MCSI","2015-10-21T05:42:10","CSAC",null,null,"SYN_ALTIS ","A88,A88_Chine,B618,B751_3_4_MV,B78_mi_vie,B81_Chine_Fenêtre_VS,C84_Chine,F3,G95_PH2,K0,K0_Russie,MODULE_EE02,P1MO,P1UO,P84_Chine,P87_Chine,P8X,T9_MV,X81_Chine : CVM : Synthèse Altis","2016-05-31","Planifié",null,null,"2016-05-31","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-3036-L-105331","AIT - MCSI","2016-03-25T12:01:35","CSAC",null,null,"DO_CDCI_BILAN","B751_3_4_MV,B78_mi_vie,B81_Chine_Fenêtre_VS,C84_Chine,G95_PH2,K0,MODULE_EE02,P1UO,P84_Chine,P87_Chine,P8X,T9_MV,X81_Chine : RADAR GÉN3 : Synthèses d'avancement de toutes les implantation Radar / Fichier de pilotage interne et avec fournisseur.","2016-05-31","Planifié",null,null,"2016-05-31","OTD","2016-06-02","FTR"]
["MCSH-2916-L-107234","AIT - MCSI","2016-04-27T15:18:52","CSAC",null,null,"DO_ACEE","A55_MV,A9MV,A5X_F_05_16,A94_MV,B9_Mi_Vie_2_F11/2015,F3,MODULE_EE02 : LIDAR : Grille ACEE pour réactivité 120j FT ALTIS 7239401","2016-05-31","Planifié","2016-05-18","Retard fournisseur","2016-05-31","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-3039-L-108012","AIT - MCSI","2016-05-20T16:49:53","CSAC",null,null,"OF_PIECE","MODULE_EE02 : CVM : Officialisation module de la CVM niv1 & 2 (D5.3)","2016-05-31","Planifié",null,null,"2016-05-31","DR","2016-07-01","ACCEPTE_DEFAUT"]
["MCSH-8050-L-102301","AIT - MCSI","2016-01-25T13:29:32","CSAC",null,null,"DO_CDCI_BILAN","X74E : CVP (X74E) : Bilan des retours des CDCI\r\nCAMERA AIDE VISUELLE PANORAMIQUE dans volet Ar","2016-05-31","Planifié","2016-05-25",null,"2016-05-31","OTD","2016-10-18","ACCEPTE_DEFAUT"]
["MCSH-2509-L-106479","AIT - MCSI","2016-04-13T11:45:36","SWES",null,null,"VAL_ANA_INDIC","MODULE_HAB10,A58VS,Ai51M,B9,B9E,G9,T1_Iran,T3,T3_Iran,T61_Chine,T7,T7xA,T73,T7x_Mercosur,T73_Chine,T73_Malaisie,T73_Russie,T75,T76,T7H : COM2005_EV3 (Delphi : Suivi Vie Série) : Vérifier les engagements qualité du FNR et prioriser en fonction des têtes de pareto. Objectif en début d'année, bilan à mi et fin d'année.","2016-04-29","Planifié","2016-06-01","Retard fournisseur","2016-06-01","DR","2016-06-17","FTR"]
["MCSH-5562-L-64965","EST - MCSI","2014-02-21T13:46:22","ELAC",null,null,"RT_PV","B618,MODULE_HAB05 : GRPE_CLIM : Revue fin de PV avec Fnr","2016-05-20","Planifié","2016-06-03","Retard fournisseur","2016-06-01","OTD","2016-06-10","FTR"]
["MCSH-5562-L-94133","EST - MCSI","2015-07-06T16:24:00","ELAC",null,null,"DO_ALTIS","B618,MODULE_HAB05 : GRPE_CLIM : Mise à jour ALTIS (EE ou Qualité)","2015-09-22","Planifié","2016-06-17","Retard fournisseur","2016-06-02","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-4158-L-108041","EST - MCSI","2016-05-23T14:44:27","EEMS",null,null,"SYN_A3_QUAL_DOM","_RITUELS : _RITUEL_EEMS_Qualité : IQC_METIER_A3 Pole-EEMS","2016-05-27","Planifié",null,null,"2016-06-02","NDR","2016-07-04","FTR"]
["MCSH-8071-L-106519","EST - MCSI","2016-04-14T17:16:48","EACC",null,null,"DO_BE_CESARE","C84_Export : AVE (C84_Chine,C84_Export) : Création /Mise à jour BE CESARE","2016-06-01","Planifié","2016-06-02","Retard fournisseur","2016-06-02","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-8246-L-106737","AIT - MCDV","2016-04-18","HDTC",null,null,"OF_PIECE","_TOUS : _TRAVAUX_CAO : Officialisation en contexte de l'EV CIRCUIT REFROIDIS PRINCIPAL TBT 1400488980\r\n","2016-04-15","Planifié",null,null,"2016-06-03","NDR","2016-10-14","ACCEPTE_DEFAUT"]
["MCSH-6825-L-107755","AIT - MCSI","2016-05-13T04:06:43","CSAC",null,null,"OF_CAL","B78_mi_vie : RADAR GÉN3 (B78 MV) : MAJ CALs MDL D5.3 (AEB tuning completed + full braking)","2016-06-03","Planifié",null,null,"2016-06-03","DR","2016-06-06","FTR"]
["MCSH-6825-L-107757","AIT - MCSI","2016-05-13T04:12:34","CSAC",null,null,"DO_CESARE","B78_mi_vie : RADAR GÉN3 (B78 MV) : Livraison BEs CESARE D5.3 pour MDLMAJ (AEB tuning completed + full braking)","2016-06-03","Planifié",null,null,"2016-06-03","DR","2016-06-06","FTR"]
["MCSH-3039-L-108013","AIT - MCSI","2016-05-20T16:50:11","CSAC",null,null,"OF_PIECE","MODULE_EE02 : CVM : Officialisation module de la CVM VAEB (SW5.1)","2016-06-30","Planifié",null,null,"2016-06-03","DR","2016-07-04","ACCEPTE_DEFAUT"]
["MCSH-1862-L-107531","EST - MCSI","2016-05-09T10:35:08","EACC",null,null,"DO_FC_VRS","A94_Chine,A94_Iran_CKD2,B78 : SECU_DML (Rec. A94_Chine,A94_Iran_CKD2,B78) : Fiches composants pour SDP VRS","2016-05-31","Planifié","2016-06-06","Retard fournisseur","2016-06-06","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-3533-L-107977","AIT - MCSI","2016-05-20T10:57:11","CSAC",null,null,"OF_CAL","P8X : CVM (P8) : P84 (flotte PRSEL2): Officialisation CAL CVM VAEB SW5.1 avec AEB 0,3g","2016-06-30","Planifié",null,null,"2016-06-06","DR","2016-06-14","FTR"]
["MCSH-6639-L-85786","EST - MCSI","2015-03-04T13:57:10","EACC",null,null,"VAL_ANA_RAPP_ESSAIS","K0 : SWITCH TRAPPE CARB : Analyse CR Essais PV","2015-08-10","Planifié","2016-06-13","Retard fournisseur","2016-06-08","OTD","2016-06-22","NOT FTR"]
["MCSH-6639-L-85787","EST - MCSI","2015-03-04T13:57:10","EACC",null,null,"VAL_BILAN","K0 : SWITCH TRAPPE CARB : Bilan Validation - Archvage des données","2015-08-24","Planifié","2016-06-13","Retard fournisseur","2016-06-08","OTD","2016-06-09","FTR"]
["MCSH-2178-L-104974","EST - MCSI","2016-03-21T10:24:47","ELPS",null,null,"OF_PIECE","MODULE_EE03 : MUS2 (Dev.MUS2) : Officialisation d'une pièce - PLAN FONCTIONNEL MUS2","2016-04-29","Planifié",null,null,"2016-06-08","NDR","2016-07-11","ACCEPTE_DEFAUT"]
["MCSH-7831-L-105732","EST - MCSI","2016-04-01T10:48:35","EACC",null,null,"OF_PIECE","K9 : ANTENNE_BACKUP (REC K9) : Officialisation d'une pièce : Antenne Backup","2016-05-27","Planifié","2016-06-08","Retard fournisseur","2016-06-08","OTD","2016-06-22","FTR"]
["MCSH-8562-L-106407","AIT - MCSI","2016-04-11T14:14:50","SWES",null,null,"DO_SUIVI_PROCESS","MODULE_HAB10 : COM200X_CSV (DELPHI: rupture appro flex) : Mise à jour du document de suivi produit/process","2016-05-27","Planifié","2016-06-08","Retard fournisseur","2016-06-08","OTD","2016-06-17","FTR"]
["MCSH-7987-L-105820","EST - MCSI","2016-04-01T11:31:03","ELPS",null,null,"RI_CONTRAINTES","D34E : FEU_AV : Revue technique d'interface HW avec BSLE et CA2E","2016-06-27","Planifié",null,null,"2016-06-09","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-3533-L-108450","AIT - MCSI","2016-06-03T11:37:52","CSAC",null,null,"DO_CESARE","P8X : CVM (P8) : P84 (EL2-Flotte): BE SW5.1 pour VAEB 0.3g","2016-06-10","Planifié","2016-06-13","Retard fournisseur","2016-06-13","DR","2016-06-14","FTR"]
["MCSH-7888-L-89736","AIT - MCSI","2015-04-23T07:52:12","CSAC",null,null,"DO_CESARE","X7RR : VISIO_PARK (X7RR) : Création de référence/Mise à jour CESARE C4","2016-06-13","Planifié","2016-06-13","Retard fournisseur","2016-06-13","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7888-L-89745","AIT - MCSI","2015-04-23T07:52:12","CSAC",null,null,"OF_CAL","X7RR : VISIO_PARK (X7RR) : Calibration pour VRS1","2016-06-13","Planifié",null,null,"2016-06-13","OTD","2016-06-29","FTR"]
["MCSH-7236-L-84815","AIT - MCSI","2015-02-19T13:33:53","CSAC",null,null,"DO_CESARE","P84_Chine : VISIO_PARK (P84 Chine) : Création de Référence / Maj CESARE pour EL2","2016-06-17","Planifié",null,null,"2016-06-13","OTD","2016-06-29","FTR"]
["MCSH-7236-L-84816","AIT - MCSI","2015-02-19T13:33:53","CSAC",null,null,"OF_CAL","P84_Chine : VISIO_PARK (P84 Chine) : Calibration pour EL2","2016-06-17","Planifié",null,null,"2016-06-13","OTD","2016-06-29","FTR"]
["MCSH-6611-L-108493","EST - MCSI","2016-06-06T14:19:36","ELPS",null,null,"OF_DOTE","P1MO : RUPTEUR_CAPOT,SIRENE_LIN_SSCAS,MUS2 (Rec. P1MO) : Officialisation de DOTE MUS2 P1MO","2016-06-20","Planifié",null,null,"2016-06-13","DR","2016-07-14","ACCEPTE_DEFAUT"]
["MCSH-6608-L-108494","EST - MCSI","2016-06-06T14:21:22","ELPS",null,null,"OF_DOTE","A88 : SIRENE_LIN_SSCAS,MUS2,RUPTEUR_CAPOT : Officialisation de DOTE MUS2 A88","2016-06-20","Planifié",null,null,"2016-06-13","DR","2016-06-22","FTR"]
["MCSH-1014-L-96649","EST - MCSI","2015-09-14T15:14:35","ECPC",null,null,"RI_TOP_RO","A55_PRO,K0,K9,MODULE_EE05,P1MO : PDPC_2LVI_RE,PDPC_2LVI_RE_RA : Revue Technique d'interface pour robustesse avant top RO\r\n(idem ARIS)","2016-05-23","Planifié","2016-06-24","Retard fournisseur","2016-06-14","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7059-L-108802","EST - MCSI","2016-06-14T13:44:19","EACC",null,null,"OF_PIECE","T9_MV : AVE (T9,T9_MV) : Officialisation d'une pièce","2016-05-23","Planifié","2016-06-14",null,"2016-06-14","DR","2016-06-22","FTR"]
["MCSH-8071-L-103447","EST - MCSI","2016-02-16T14:30:47","EACC",null,null,"OF_PIECE","C84_Chine : AVE (C84_Chine,C84_Export) : Officialisation d'une pièce REC AVE C84C","2016-05-30","Planifié","2016-06-14","Retard fournisseur","2016-06-14","OTD","2016-07-25","NOT FTR"]
["MCSH-3745-L-101196","AIT - MCSI","2016-01-08T01:19:50","SWES",null,null,"SYN_A3_QUAL_ORG","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_A3-COM2008 Premium Valeo","2016-06-14","Planifié",null,null,"2016-06-14","OTD","2016-08-23","NOT FTR"]
["MCSH-7482-L-80708","EST - MCSI","2014-12-16T15:24:57","ELPS",null,null,"DO_CDCI_BILAN","K9 : SIRENE_LIN_SSCAS,RUPTEUR_CAPOT,MUS2 : CDCI validé pour VRS1","2016-06-14","Planifié",null,null,"2016-06-14","OTD","2016-10-13","ACCEPTE_DEFAUT"]
["MCSH-1030-L-96641","EST - MCSI","2015-09-14T15:13:48","ECPC",null,null,"RI_TOP_RO","A88,B78,C84_Export,K9,MODULE_EE05,P1MO,P1UO,P21,P8X,R82E,R83E,_ECOTECH : PDPC_4LVI_RE_RA_ME_MUX,PDPC_4LVI_RE_RA_MUX : Revue Technique d'interface pour robustesse avant top RO\r\n(idem ARIS)","2016-07-04","Planifié",null,null,"2016-06-14","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7953-L-108254","AIT - MCSI - NAC","2016-05-24T18:17:49","IVI",null,null,"OF_PIECE","MODULE_EE07 : NAC Wave 3 : Officialisation d'une pièce","2016-04-30","Planifié","2016-06-30",null,"2016-06-15","DR","2016-07-18","ACCEPTE_DEFAUT"]
["MCSH-8161-L-107814","AIT - MCSI - SMEG","2016-05-18T10:50:25","IDEV",null,null,"OF_PIECE","_F09/2016 : SMEG+_I_V2 : Reconduction de la variante D1 en 2ISO projet B9 pour les PRS7.1","2016-06-15","Planifié",null,null,"2016-06-15","DR","2016-07-18","ACCEPTE_DEFAUT"]
["MCSH-7987-L-105801","EST - MCSI","2016-04-01T11:31:03","ELPS",null,null,"RT_STD","D34E : FEU_AV : Avec le Fournisseur - Vérif indice STD","2016-04-29","Planifié","2016-07-07","Retard fournisseur","2016-06-16","DR","2016-08-23","FTR"]
["MCSH-3745-L-101265","AIT - MCSI","2016-01-08T03:26:57","SWES",null,null,"SYN_DC_ORGANE","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_SR-Ecran tactile","2016-06-16","Planifié",null,null,"2016-06-16","OTD","2016-07-08","FTR"]
["MCSH-925-L-106006","EST - MCSI","2016-04-06T02:49:20","ELAC",null,null,"DO_DIVERS","_METIER,_QUALITE : _QUALITE : Indicateurs qualité ELAC de Juin (données de Mai)","2016-06-16","Planifié",null,null,"2016-06-16","OTD","2016-07-29","FTR"]
["MCSH-7831-L-88258","EST - MCSI","2015-04-10T10:37:41","EACC",null,null,"OF_PIECE","K9 : ANTENNE_BACKUP (REC K9) : Reconduction de l'antenne passive pour K9\r\nDAD","2016-07-22","Planifié","2016-05-13",null,"2016-06-16","OTD","2016-06-22","FTR"]
["MCSH-3745-L-101185","AIT - MCSI","2016-01-08T01:11:30","SWES",null,null,"SYN_A3_QUAL_DOM","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_METIER_A3-EMCD","2016-06-10","Planifié",null,null,"2016-06-17","Retard","2016-08-23","NOT FTR"]
["MCSH-3745-L-101237","AIT - MCSI","2016-01-08T01:47:36","SWES",null,null,"SYN_DC_ORGANE","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_SR-Volant équipé","2016-06-14","Planifié",null,null,"2016-06-17","OTD","2016-06-17","FTR"]
["MCSH-3745-L-101276","AIT - MCSI","2016-01-08T03:28:02","SWES",null,null,"SYN_DC_ORGANE","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_SR-Combiné","2016-06-17","Planifié",null,null,"2016-06-17","OTD","2016-07-08","FTR"]
["MCSH-3127-L-107592","AIT - MCSI","2016-05-12T13:42:10","CSAC",null,null,"DO_DIVERS","B78,MODULE_EE02,T9 : ARTIV_ARCOLL : Remontée clientèle VF73D5GZTGJ551004_DAT 7418782","2016-06-17","Planifié",null,null,"2016-06-17","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-8304-L-99949","EST - MCSI","2015-12-07T16:49:28","ELPS",null,null,"DO_CCA_TOPHW","A9X_F_05_17 : PROJ (_STT) : Fiche CCA phase 2 (conception)","2016-06-20","Planifié",null,null,"2016-06-17","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-8302-L-102584","EST - MCSI","2016-02-01T11:33:22","ELPS",null,null,"DO_CCA_TOPHW","A9X_F_05_17 : PROJ : Fiche CCA phase 2 (conception)","2016-06-20","Planifié",null,null,"2016-06-17","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-5893-L-108902","AIT - MCSI","2016-06-17T11:33:08","CSAC",null,null,"DO_CESARE","A88,P1MO : CVM (A88,P1MO) : BE CVM Gen 2 VAEB SW5d pour stade PPV2 P1MO (DàG)","2016-06-20","Planifié",null,null,"2016-06-17","DR","2016-06-17","FTR"]
["MCSH-5893-L-108915","AIT - MCSI","2016-06-17T15:41:08","CSAC",null,null,"DO_CESARE","A88,P1MO : CVM (A88,P1MO) : BE CVM Gen 2 VAEB SW5d pour stade PPV2 P1MO (DàD)","2016-06-20","Planifié",null,null,"2016-06-17","DR","2016-06-17","FTR"]
["MCSH-5893-L-108918","AIT - MCSI","2016-06-17T15:45:38","CSAC",null,null,"DO_CESARE","A88,P1MO : CVM (A88,P1MO) : BE CVM Gen 2 VAEB SW5d pour stade PPV1/2 A88 (DàG)","2016-06-20","Planifié",null,null,"2016-06-17","DR","2016-06-17","FTR"]
["MCSH-5893-L-108920","AIT - MCSI","2016-06-17T15:48:12","CSAC",null,null,"DO_CESARE","A88,P1MO : CVM (A88,P1MO) : BE CVM Gen 2 VAEB SW5d pour stade PPV1/2 A88 (DàD)","2016-06-20","Planifié",null,null,"2016-06-17","DR","2016-06-17","FTR"]
["MCSH-7373-L-99365","EST - MCSI","2015-11-20T09:19:19","EACC",null,null,"OF_PIECE","R83_Chine : BEM : Officialisation des fixations du BEM pour R83_Chine","2016-07-08","Planifié",null,null,"2016-06-17","OTD","2016-06-21","FTR"]
["MCSH-5893-L-108486","AIT - MCSI","2016-06-06T01:23:32","CSAC",null,null,"OF_CAL","P1MO : CVM (A88,P1MO) : Calibration CVM Gen 2 Niveau 3 (SW5d) pour stade PPV2 P1MO version DàG (LHD)","2016-06-15","Planifié","2016-06-17",null,"2016-06-20","NDR","2016-06-23","FTR"]
["MCSH-5893-L-108487","AIT - MCSI","2016-06-06T01:26:47","CSAC",null,null,"OF_CAL","P1MO : CVM (A88,P1MO) : Calibration CVM Gen 2 Niveau 3 (SW5d) pour stade PPV2 P1MO version DàD (RHD)","2016-06-15","Planifié","2016-06-17",null,"2016-06-20","NDR","2016-06-23","FTR"]
["MCSH-5893-L-108488","AIT - MCSI","2016-06-06T01:30:35","CSAC",null,null,"OF_CAL","A88 : CVM (A88,P1MO) : Calibration CVM Gen 2 Niveau 3 (SW5d) pour stade PPV1 A88 version DàG (LHD)","2016-06-15","Planifié","2016-06-17",null,"2016-06-20","NDR","2016-06-23","FTR"]
["MCSH-5893-L-108489","AIT - MCSI","2016-06-06T01:30:47","CSAC",null,null,"OF_CAL","A88 : CVM (A88,P1MO) : Calibration CVM Gen 2 Niveau 3 (SW5d) pour stade PPV1 A88 version DàD (RHD)","2016-06-15","Planifié","2016-06-17",null,"2016-06-20","NDR","2016-06-23","FTR"]
["MCSH-5616-L-108465","EST - MCSI","2016-06-06T08:38:32","ELAC",null,null,"DO_DIVERS","_METIER : LDA / référentiel technique CLIM : Mise à jour fichier roadmap ELAC","2016-06-20","Planifié",null,null,"2016-06-20","DR","2016-07-29","FTR"]
["MCSH-7373-L-105494","EST - MCSI","2016-03-30T15:19:53","EACC",null,null,"DO_BE_CESARE","R83_Chine : BEM : Création /Mise à jour BE CESARE","2016-06-24","Planifié",null,null,"2016-06-20","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-6555-L-65077","EST - MCSI","2014-02-21T14:19:28","ELAC",null,null,"DO_DIVERS","A88,MODULE_HAB05,P1MO : GRPE_CLIM : Mise en nomenclature des référence APV","2016-02-11","Planifié","2016-06-24","Retard fournisseur","2016-06-21","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-3745-L-101522","AIT - MCSI","2016-01-13T08:03:41","SWES",null,null,"SYN_DC_ORGANE","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_SR-CSV RADIO et RVV/LVV VALEO","2016-06-21","En cours",null,null,"2016-06-21","OTD","2016-07-08","FTR"]
["MCSH-3745-L-101533","AIT - MCSI","2016-01-13T08:04:04","SWES",null,null,"SYN_DC_ORGANE","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_SR-CSV RADIO et RVV/LVV DELPHI","2016-06-21","En cours",null,null,"2016-06-21","OTD","2016-07-08","FTR"]
["MCSH-3741-L-101139","AIT - MCSI","2016-01-08T11:57:49","SWES",null,null,"SYN_A3_ALTIS_REAC","_QUALITE : IND_QUAL (Indicateurs EQP et Réactivité) : A3 Synthèse Altis Réactivité","2016-06-27","En cours",null,null,"2016-06-21","OTD","2016-07-08","FTR"]
["MCSH-7773-L-95785","EST - MCSI","2015-08-18T16:04:47","EACC",null,null,"OF_PIECE","X74E : ANTENNE_BACKUP (X74E) : Reconduction de l'antenne passive sur X74€\r\npour la DAD","2016-07-15","En cours",null,null,"2016-06-21","OTD","2016-06-22","FTR"]
["MCSH-2509-L-106485","AIT - MCSI","2016-04-13T11:45:36","SWES",null,null,"ANI_MENSUELLE","MODULE_HAB10,A58VS,Ai51M,B9,B9E,G9,T1_Iran,T3,T3_Iran,T61_Chine,T7,T7xA,T73,T7x_Mercosur,T73_Chine,T73_Malaisie,T73_Russie,T75,T76,T7H : COM2005_EV3 (Delphi : Suivi Vie Série) : Trimestrielle FNR. En pièce jointe ODJ (1 semaine avant) + CR technique. Lien vers l'ODJ type : http://docinfogroupe.inetpsa.com/ead/doc/ref.00948_10_00977/v.vc/fiche. Lien vers le CR type : http://docinfo.inetpsa.com/ead00/doc/ref.00948_10_00984/v.vc/fic","2016-05-20","En cours","2016-06-22","Retard fournisseur","2016-06-22","DR","2016-07-08","NOT FTR"]
["MCSH-3745-L-101208","AIT - MCSI","2016-01-08T01:21:31","SWES",null,null,"SYN_A3_QUAL_ORG","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_A3-COM2008 Premium KOSTAL","2016-06-19","En cours",null,null,"2016-06-22","OTD","2016-08-23","NOT FTR"]
["MCSH-3745-L-101220","AIT - MCSI","2016-01-08T01:22:18","SWES",null,null,"SYN_A3_QUAL_ORG","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_A3-COM2008 KOSTAL","2016-06-19","En cours",null,null,"2016-06-22","OTD","2016-07-08","FTR"]
["MCSH-7990-L-94688","AIT - MCSI","2015-07-22T13:17:14","CSAC",null,null,"DO_CESARE","P87_Chine : RADAR GÉN3 (P87C) : Livraison BE VRS DV (UT1)","2016-06-22","En cours",null,null,"2016-06-22","OTD","2016-06-28","FTR"]
["MCSH-7990-L-94694","AIT - MCSI","2015-07-22T13:17:14","CSAC",null,null,"OF_CAL","P87_Chine : RADAR GÉN3 (P87C) : CAL VRS DV (UT1) D5.3b","2016-06-22","En cours",null,null,"2016-06-22","OTD","2016-06-28","FTR"]
["MCSH-3540-L-108330","AIT - MCSI","2016-05-30T11:19:47","CSAC",null,null,"DO_CESARE","P8X : RADAR GÉN3 (P8X) : Livraison BE CESARE D5.3b","2016-06-22","En cours",null,null,"2016-06-22","DR","2016-06-28","FTR"]
["MCSH-3540-L-108331","AIT - MCSI","2016-05-30T11:20:07","CSAC",null,null,"OF_CAL","P8X : RADAR GÉN3 (P8X) : CALs D5.3b","2016-06-22","En cours",null,null,"2016-06-22","DR","2016-06-28","FTR"]
["MCSH-4199-L-108332","AIT - MCSI","2016-05-30T11:26:12","CSAC",null,null,"DO_CESARE","X81_Chine : RADAR GÉN3 (X81C) : Livraison BE CESARE D5.3b","2016-06-22","En cours",null,null,"2016-06-22","DR","2016-06-23","FTR"]
["MCSH-4199-L-108333","AIT - MCSI","2016-05-30T11:26:25","CSAC",null,null,"OF_CAL","X81_Chine : RADAR GÉN3 (X81C) : CAL D5.3b","2016-06-22","En cours",null,null,"2016-06-22","DR","2016-06-23","FTR"]
["MCSH-5562-L-64962","EST - MCSI","2014-02-21T13:46:22","ELAC",null,null,"DO_ETAT_ACCEPT","B618 : GRPE_CLIM : Etat d'acceptation Produit (pièce R2)","2016-06-24","En cours",null,null,"2016-06-22","OTD","2016-06-30","FTR"]
["MCSH-7065-L-82278","AIT - MCSI","2015-01-14T13:01:09","CSAC",null,null,"OF_PIECE","R83E : CVM (R83E) : Officialisation Plan et 3D Fournisseur - Sans déviation","2016-05-13","En cours","2016-06-24","Retard fournisseur","2016-06-23","OTD","2016-07-25","ACCEPTE_DEFAUT"]
["MCSH-616-L-92734","EST - MCSI","2015-06-12T14:49:05","ECPC",null,null,"OF_PIECE","K9 : CMD_RETRO_RE : Officialisation DFNU - FNR\r\nJOYSTICK RE DAG","2016-05-27","En cours","2016-06-30","Retard fournisseur","2016-06-23","OTD","2016-07-25","ACCEPTE_DEFAUT"]
["MCSH-5891-L-109076","AIT - MCSI","2016-06-23T08:31:10","CSAC",null,null,"DO_CESARE","B618 : CVM (B618) : PRS EL2 (F09.2016): BE CVM Gen 2 Niveau 1 (D5.2d)","2016-06-24","En cours",null,null,"2016-06-23","DR","2016-06-23","FTR"]
["MCSH-8246-L-104529","AIT - MCDV","2016-03-10","HDTC",null,null,"OF_PIECE","_TOUS : _TRAVAUX_CAO : création et officialisation de référence FNR support capteur oxyde azote aval pour EMP2 motorisation DV5R et DW10 €6.2, et rattachement au FCT 9813404280","2016-04-01","En cours","2016-07-15","Retard fournisseur","2016-06-24","DR","2016-07-25","ACCEPTE_DEFAUT"]
["MCSH-7358-L-106690","EST - MCSI","2016-04-18T09:50:41","ELPS",null,null,"VAL_ANA_PV_FNR","D34E : FEUX_AR : Analyse du planning de validation fournisseur","2016-05-15","En cours",null,null,"2016-06-24","NDR",null,"ACCEPTE_DEFAUT"]
["MCSH-8657-L-108295","EST - MCSI","2016-05-26T13:40:14","ELAC",null,null,"RT_STD","P8X : RCP : Revue Technique des Spécifications et Normes avec le fournisseur","2016-06-03","En cours","2016-06-30","Retard fournisseur","2016-06-24","DR","2016-07-25","ACCEPTE_DEFAUT"]
["MCSH-2958-L-107605","EST - MCSI","2016-05-13T11:21:56","ELAC",null,null,"OF_PIECE","K0 : GRPE_CLIM_AR : Officialisation d'une pièce","2016-06-24","En cours",null,null,"2016-06-24","OTD","2016-07-25","ACCEPTE_DEFAUT"]
["MCSH-5891-L-108960","AIT - MCSI","2016-06-20T15:28:06","CSAC",null,null,"OF_CAL","B618 : CVM (B618) : PRSEL2 (F09.2016):\r\nOfficialisation Calibration CVM Gen2 niveau 1 (D5.2d)","2016-06-24","En cours",null,null,"2016-06-24","DR","2016-06-27","FTR"]
["MCSH-7480-L-108388","AIT - MCSI","2016-06-01T05:50:43","CSAC",null,null,"OF_PIECE","B751_3_4_MV : RADAR GÉN3 (B753_4  MV) : REC Assemblé Radar et ses fixations sur B753/1. (D5.4)","2016-06-30","En cours",null,null,"2016-06-24","DR","2016-06-28","FTR"]
["MCSH-3745-L-101229","AIT - MCSI","2016-01-08T01:38:45","SWES",null,null,"SYN_A3_QUAL_ORG","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_A3-COM2005 EV2-EV3 Delphi","2016-06-26","En cours",null,null,"2016-06-26","OTD","2016-07-08","FTR"]
["MCSH-7953-L-108839","AIT - MCSI - NAC","2016-06-15T15:49:08","IVI",null,null,"OF_PIECE","X74E : NAC Wave 3 : REC var B4HD SW V2 sur X74","2016-05-13","En cours",null,null,"2016-06-27","NDR","2016-07-28","ACCEPTE_DEFAUT"]
["MCSH-6825-L-108413","AIT - MCSI","2016-06-02T02:03:32","CSAC",null,null,"OF_PIECE","B78_mi_vie : RADAR GÉN3 (B78 MV) : REC : BOITIER ELECTRONIQUE RADAR AV ASS D5.4","2016-06-30","En cours",null,null,"2016-06-27","DR","2016-07-28","ACCEPTE_DEFAUT"]
["MCSH-7075-L-108414","AIT - MCSI","2016-06-02T02:06:20","CSAC",null,null,"OF_PIECE","T9_MV : RADAR GÉN3 (T9MV) : REC Assemblé Radar Gen 3 D5.4 pour EL1.","2016-06-30","En cours",null,null,"2016-06-27","DR","2016-09-08","RBA"]
["MCSH-7147-L-108415","AIT - MCSI","2016-06-02T02:12:03","CSAC",null,null,"OF_PIECE","G95_PH2 : RADAR GÉN3 (G95Ph2) : REC BOITIER ELECTRONIQUE RADAR AV ASS D5.4 ","2016-06-30","En cours",null,null,"2016-06-27","DR","2016-06-28","FTR"]
["MCSH-7144-L-108800","EST - MCSI","2016-06-14T13:31:32","EACC",null,null,"OF_PIECE","R83E : ANTENNE_BACKUP (R8) : Officialisation d'une pièce","2016-07-13","En cours",null,null,"2016-06-27","DR","2016-07-01","FTR"]
["MCSH-7800-L-108395","EST - MCSI","2016-06-02","ECPC",null,null,"OF_PIECE","K9 : PUSH_LVE_AV : Officialisation OCM - FNR",null,"En cours",null,null,"2016-06-27","NDR",null,"ACCEPTE_DEFAUT"]
["MCSH-5751-L-103669","EST - MCSI","2016-02-19T15:44:39","ELAC",null,null,"DO_FETE","P8X : TDC AR : FETE transmise au fournisseur LCD White.","2016-03-04","En cours","2016-06-30","Retard fournisseur","2016-06-28","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-1014-L-96648","EST - MCSI","2015-09-14T15:14:35","ECPC",null,null,"OF_PIECE","K9 : PDPC_2LVI_RE,PDPC_2LVI_RE_RA : Officialisation d'une pièce","2016-05-27","En cours","2016-06-30","Retard fournisseur","2016-06-28","OTD","2016-07-29","ACCEPTE_DEFAUT"]
["MCSH-1632-L-96630","EST - MCSI","2015-09-14T15:11:30","ECPC",null,null,"OF_PIECE","K9 : MODULE_DOUBLE_LVE : Officialisation d'une pièce","2016-05-27","En cours","2016-06-30","Retard fournisseur","2016-06-28","OTD","2016-10-13","ACCEPTE_DEFAUT"]
["MCSH-1030-L-96643","EST - MCSI","2015-09-14T15:13:48","ECPC",null,null,"OF_OCM_RO","K9 : PDPC_4LVI_RE_RA_ME_MUX,PDPC_4LVI_RE_RA_MUX : OCM pour RO","2016-06-27","En cours",null,null,"2016-06-28","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-4199-L-108357","AIT - MCSI","2016-05-31T09:17:26","CSAC",null,null,"OF_PIECE","X81_Chine : RADAR GÉN3 (X81C) : Reconduction Assemblé Radar Gen 3 sur X81_CH : OCM D5.4","2016-06-30","En cours",null,null,"2016-06-28","DR","2016-09-08","FTR"]
["MCSH-7480-L-108409","AIT - MCSI","2016-06-02T11:38:22","CSAC",null,null,"OF_PIECE","B751_3_4_MV : RADAR GÉN3 (B753_4  MV) : REC Assemblé Radar et ses fixations sur B754. (D5.4)","2016-06-30","En cours",null,null,"2016-06-28","DR","2016-06-30","FTR"]
["MCSH-3533-L-108923","AIT - MCSI","2016-06-17T16:39:28","CSAC",null,null,"OF_PIECE","P8X : CVM (P8) : P84/P87: Reconduction CVM VAEB SW6","2016-06-30","En cours",null,null,"2016-06-28","DR","2016-06-29","FTR"]
["MCSH-7953-L-108252","AIT - MCSI - NAC","2016-05-24T17:45:36","IVI",null,null,"OF_PIECE","MODULE_EE07 : NAC Wave 3 : Officialisation d'une pièce","2016-04-30","En cours","2016-06-30",null,"2016-06-29","DR","2016-08-01","ACCEPTE_DEFAUT"]
["MCSH-4158-L-108051","EST - MCSI","2016-05-23T15:11:49","EEMS",null,null,"SYN_A3_QUAL_DOM","_RITUELS : _RITUEL_EEMS_Qualité : IQC_METIER_A3 Pole-EEMS","2016-06-24","En cours",null,null,"2016-06-29","NDR",null,"ACCEPTE_DEFAUT"]
["MCSH-4158-L-108052","EST - MCSI","2016-05-23T15:11:49","EEMS",null,null,"SYN_A3_QUAL_ORG","_RITUELS : _RITUEL_EEMS_Qualité : Point_DC_EACC","2016-06-24","En cours",null,null,"2016-06-29","NDR",null,"ACCEPTE_DEFAUT"]
["MCSH-4158-L-108054","EST - MCSI","2016-05-23T15:11:49","EEMS",null,null,"SYN_A3_QUAL_ORG","_RITUELS : _RITUEL_EEMS_Qualité : Point_DC_ELPS","2016-06-24","En cours",null,null,"2016-06-29","NDR",null,"ACCEPTE_DEFAUT"]
["MCSH-6959-L-109015","EST - MCSI","2016-06-22T10:23:28","EACC",null,null,"RT_STD","C4X,D34E,MODULE_HAB01,P24E : LUMBAFLEX : Revue Technique des Spécifications et Normes avec le fournisseur","2016-06-29","En cours","2016-07-11","Retard fournisseur","2016-06-29","DR","2016-08-03","ACCEPTE_DEFAUT"]
["MCSH-6604-L-108384","AIT - MCSI","2016-06-01T05:11:34","CSAC",null,null,"OF_PIECE","P1UO : RADAR GÉN3 (P1UO) : REC : BOITIER ELECTRONIQUE RADAR AV ASS D5.4 sur EL0.","2016-06-30","En cours",null,null,"2016-06-29","DR","2016-09-08","RBA"]
["MCSH-7990-L-108411","AIT - MCSI","2016-06-02T12:51:51","CSAC",null,null,"OF_PIECE","P87_Chine : RADAR GÉN3 (P87C) : REC Assemblé Radar D5.4 pour EL1","2016-06-30","En cours",null,null,"2016-06-29","DR","2016-06-30","FTR"]
["MCSH-3039-L-109158","AIT - MCSI","2016-06-24T14:23:54","CSAC",null,null,"OF_PIECE","MODULE_EE02 : CVM : Officialisation module de la CVM VAEB (SW6)","2016-07-06","En cours",null,null,"2016-06-29","DR","2016-06-30","FTR"]
["MCSH-7415-L-99876","EST - MCSI","2015-12-07T02:20:12","ELAC",null,null,"OF_PIECE","X74E : GRPE_CLIM : Officialisation faisceau groupe ref 4. (RFTA avec AQS)","2016-07-15","En cours",null,null,"2016-06-29","OTD","2016-08-01","ACCEPTE_DEFAUT"]
["MCSH-6825-L-107758","AIT - MCSI","2016-05-13T04:12:34","CSAC",null,null,"DO_CESARE","B78_mi_vie : RADAR GÉN3 (B78 MV) : Livraison BEs CESARE D5.3b pour MDL MAJ  (ACC tuning completed)","2016-07-18","En cours",null,null,"2016-06-29","OTD","2016-06-30","FTR"]
["MCSH-7311-L-77847","AIT - MCSI","2014-10-30T15:11:16","SWES",null,null,"VAL_BILAN","_QUALITE : COM2005_EV3 (Réactivité sans délai_DELPHI : pb son) : Bilan de validation Fournisseur et PSA","2016-05-31","En cours","2016-06-30","Retard fournisseur","2016-06-30","OTD","2016-08-04","ACCEPTE_DEFAUT"]
["MCSH-7787-L-101917","EST - MCSI","2016-01-20T09:44:38","ECPC",null,null,"OF_PIECE","R83E : PUSH_LVI_AR,PUSH_LVI_AV : Officialisation d'une pièce","2016-06-29","En cours","2016-06-30","Retard fournisseur","2016-06-30","OTD","2016-08-01","ACCEPTE_DEFAUT"]
["MCSH-5616-L-102802","EST - MCSI","2016-02-03T16:52:23","ELAC",null,null,"DO_DIVERS","_METIER : LDA / référentiel technique CLIM : MàJ checklist ELAC (partie RT STO)","2016-06-30","En cours","2016-04-29","Retard fournisseur","2016-06-30","OTD","2016-07-29","FTR"]
["MCSH-3036-L-105326","AIT - MCSI","2016-03-25T11:53:12","CSAC",null,null,"SYN_ALTIS ","B751_3_4_MV,B78_mi_vie,B81_Chine_Fenêtre_VS,C84_Chine,G95_PH2,K0,MODULE_EE02,P1UO,P84_Chine,P87_Chine,P8X,T9_MV,X81_Chine : RADAR GÉN3 : Gestion Hebdomadaire Altis\r\n","2016-06-30","En cours",null,null,"2016-06-30","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-3036-L-105332","AIT - MCSI","2016-03-25T12:01:35","CSAC",null,null,"DO_CDCI_BILAN","B751_3_4_MV,B78_mi_vie,B81_Chine_Fenêtre_VS,C84_Chine,G95_PH2,K0,MODULE_EE02,P1UO,P84_Chine,P87_Chine,P8X,T9_MV,X81_Chine : RADAR GÉN3 : Synthèses d'avancement de toutes les implantation Radar / Fichier de pilotage interne et avec fournisseur.","2016-06-30","En cours",null,null,"2016-06-30","OTD","2016-08-01","ACCEPTE_DEFAUT"]
["MCSH-5616-L-106213","EST - MCSI","2016-04-07T15:12:18","ELAC",null,null,"DO_DIVERS","_METIER : LDA / référentiel technique CLIM : MàJ checklist avis métier (version simplifiée)","2016-06-30","En cours",null,null,"2016-06-30","OTD","2016-07-29","FTR"]
["MCSH-2916-L-107954","AIT - MCSI","2016-05-19T13:55:11","CSAC",null,null,"DO_PEPP","A55_MV,A9MV,A5X_F_05_16,A94_MV,B9_Mi_Vie_2_F11/2015,F3,MODULE_EE02 : LIDAR : Réactivité 120j Buée Lidar: PEPP Industrialisation","2016-06-30","En cours",null,null,"2016-06-30","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7362-L-108387","AIT - MCSI","2016-06-01T05:39:12","CSAC",null,null,"OF_PIECE","C84_Chine : RADAR GÉN3 (C84) : REC : BOITIER ELECTRONIQUE RADAR AV ASS D5.4","2016-06-30","En cours",null,null,"2016-06-30","DR","2016-06-30","FTR"]
["MCSH-5616-L-108463","EST - MCSI","2016-06-06T08:36:40","ELAC",null,null,"DO_DIVERS","_METIER : LDA / référentiel technique CLIM : Mise à jour LDA ELAC","2016-06-30","En cours",null,null,"2016-06-30","DR","2016-07-29","FTR"]
["MCSH-4158-L-109333","EST - MCSI","2016-06-30T13:56:49","EEMS",null,null,"SYN_DC_ORGANE","_RITUELS : _RITUEL_EEMS_Qualité : Extraction DC CLIM A9/B78/T9/EEE","2016-06-30","En cours",null,null,"2016-06-30","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-4124-L-109129","AIT - MCSI","2016-06-24T09:08:08","CSAC",null,null,"OF_PIECE","X74E : CVM (X74E) : Reconduction des nouvelles références C4 sur X74","2016-07-08","En cours",null,null,"2016-06-30","DR","2016-08-01","ACCEPTE_DEFAUT"]
["MCSH-7415-L-99874","EST - MCSI","2015-12-07T02:19:50","ELAC",null,null,"OF_PIECE","X74E : GRPE_CLIM : Officialisation faisceau groupe ref 2. (CH RF 2Z)","2016-07-15","En cours",null,null,"2016-06-30","OTD","2016-08-01","ACCEPTE_DEFAUT"]
["MCSH-7415-L-99875","EST - MCSI","2015-12-07T02:20:01","ELAC",null,null,"OF_PIECE","X74E : GRPE_CLIM : Officialisation faisceau groupe ref 3. (RF 1Z)","2016-07-15","En cours",null,null,"2016-06-30","OTD","2016-08-01","ACCEPTE_DEFAUT"]
["MCSH-7415-L-99877","EST - MCSI","2015-12-07T02:20:23","ELAC",null,null,"OF_PIECE","X74E : GRPE_CLIM : Officialisation faisceau groupe ref 5. (RFTA sans AQS)","2016-07-15","En cours",null,null,"2016-06-30","OTD","2016-08-01","ACCEPTE_DEFAUT"]
["MCSH-3053-L-105829","AIT - MCSI","2016-04-01T15:54:45","CSAC",null,null,"OF_CAL","A9MV : LIDAR (A9MV) : Officialisation Calibration A9MV pour suppression message ","2016-07-15","En cours",null,null,"2016-06-30","OTD","2016-07-01","FTR"]
["MCSH-7439-L-105831","AIT - MCSI","2016-04-01T15:56:30","CSAC",null,null,"OF_CAL","A94_MV : LIDAR (A94MV) : Officialisation Calibration A94MV pour suppression message ","2016-07-15","En cours",null,null,"2016-06-30","OTD","2016-06-30","FTR"]
["MCSH-3053-L-106050","AIT - MCSI","2016-04-06T18:05:34","CSAC",null,null,"DO_BE_CESARE","A9MV : LIDAR (A9MV) : BE A9MV pour suppression message ","2016-07-15","En cours",null,null,"2016-06-30","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7439-L-106051","AIT - MCSI","2016-04-06T18:06:09","CSAC",null,null,"DO_BE_CESARE","A94_MV : LIDAR (A94MV) : BE A94MV pour suppression message ","2016-07-15","En cours",null,null,"2016-06-30","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-6825-L-107756","AIT - MCSI","2016-05-13T04:09:54","CSAC",null,null,"OF_CAL","B78_mi_vie : RADAR GÉN3 (B78 MV) : MAJ CALs MDL D5.3b (ACC tuning completed)","2016-07-19","En cours",null,null,"2016-06-30","OTD","2016-06-30","FTR"]
["MCSH-7520-L-104595","AIT - MCSI","2016-03-14T03:41:54","CSAC",null,null,"OF_PIECE","K9 : CVP (K9) : Officialisation d'une pièce : Céméras 130 et 180 pour véhicule L2","2016-07-01","En cours","2016-08-15",null,"2016-07-01","OTD","2016-08-16","ACCEPTE_DEFAUT"]
["MCSH-7439-L-109377","AIT - MCSI","2016-07-01T13:54:45","CSAC",null,null,"OF_DOTE","A94_MV : LIDAR (A94MV) : Officialisation de DOTE A94MV suite à problème codification","2016-07-04","En cours",null,null,"2016-07-01","DR","2016-07-01","FTR"]
["MCSH-3042-L-109236","AIT - MCSI","2016-06-28T11:08:09","CSAC",null,null,"OF_PIECE","K0 : RADAR GÉN3 (K0) : REC Assemblé Radar Gen 3 D5.3","2016-07-08","En cours",null,null,"2016-07-01","DR","2016-07-07","FTR"]
["MCSH-3741-L-101049","AIT - MCSI","2016-01-06T03:03:15","SWES",null,null,"SYN_A3_EQP","_QUALITE : IND_QUAL (Indicateurs EQP et Réactivité) : A3 Synthèse EQP","2016-07-04","En cours",null,null,"2016-07-04","OTD","2016-07-08","FTR"]
["MCSH-3745-L-101175","AIT - MCSI","2016-01-08T01:08:47","SWES",null,null,"SYN_DC_ORGANE","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_SR-VCI Marquardt","2016-07-04","En cours",null,null,"2016-07-04","OTD","2016-07-27","FTR"]
["MCSH-3745-L-101495","AIT - MCSI","2016-01-13T07:53:45","SWES",null,null,"SYN_DC_ORGANE","_QUALITE : DETEC_SIGN (Indicateurs pole EMCD_A3_SR_organes) : IQC_ORGANE_SR-VCI DELPHI","2016-07-04","En cours",null,null,"2016-07-04","OTD","2016-07-27","FTR"]
["MCSH-3536-L-109281","AIT - MCSI","2016-06-29T08:42:55","CSAC",null,null,"OF_CAL","P8X : VISIO_PARK (P8) : Officialisation d'une calibration P84","2016-07-06","En cours",null,null,"2016-07-04","DR","2016-08-05","ACCEPTE_DEFAUT"]
["MCSH-7363-L-96381","AIT - MCSI","2015-09-07T18:43:32","CSAC",null,null,"OF_DOTE","C84_Chine : CVM (C84) : Pour Stade OCM VRSDV","2016-07-13","En cours",null,null,"2016-07-04","OTD","2016-08-05","ACCEPTE_DEFAUT"]
["MCSH-7480-L-100334","AIT - MCSI","2015-12-14T11:22:09","CSAC",null,null,"DO_CESARE","B751_3_4_MV : RADAR GÉN3 (B753_4  MV) : Création de référence/Mise à jour CESARE C4 VRS1","2016-07-08","En cours",null,null,"2016-07-05","OTD","2016-07-07","FTR"]
["MCSH-3536-L-109376","AIT - MCSI","2016-07-01T13:52:40","CSAC",null,null,"DO_BE_CESARE","P8X : VISIO_PARK (P8) : Mise à jour BE CESARE pour P84 Mainstream","2016-07-06","En cours",null,null,"2016-07-06","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-3536-L-109378","AIT - MCSI","2016-07-01T01:55:22","CSAC",null,null,"DO_BE_CESARE","P8X : VISIO_PARK (P8) : Mise à jour BE CESARE pour P84 Upper","2016-07-06","En cours",null,null,"2016-07-06","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-3052-L-105828","AIT - MCSI","2016-04-01T15:53:00","CSAC",null,null,"OF_CAL","A55_MV : LIDAR (A55MV) : Officialisation Calibration A55 pour suppression message ","2016-09-19","En cours",null,null,"2016-07-06","OTD","2016-07-11","FTR"]
["MCSH-8246-L-104531","AIT - MCDV","2016-03-10","HDTC",null,null,"OF_PIECE","_TOUS : _TRAVAUX_CAO : création et officialisation de référence FNR support faisceau capteur Nox pour EMP2 DW dépoll €6.2 DAG, et rattachement au FCT 9813404780","2016-04-22","En cours","2016-07-15","Retard fournisseur","2016-07-07","OTD","2016-08-08","ACCEPTE_DEFAUT"]
["MCSH-8246-L-108872","AIT - MCDV","2016-06-16T15:24:01","HDTC",null,null,"OF_PIECE","_TOUS : _TRAVAUX_CAO : Création et officialisation de référence FNR support faisceau capteur Nox pour EMP2DW dépoll €6.2 DAD, et rattachement au FCT 9813405180","2016-07-15","En cours",null,null,"2016-07-07","DR","2016-10-14","ACCEPTE_DEFAUT"]
["MCSH-5876-L-102265","EST - MCSI","2016-01-22T15:06:15","ELAC",null,null,"OF_PIECE","P84_Chine : GRPE_CLIM : Officialisation faisceau (Inversion signal µm G de mixage)","2016-06-30","En cours","2016-07-15","Retard fournisseur","2016-07-08","OTD","2016-08-09","ACCEPTE_DEFAUT"]
["MCSH-7373-L-99364","EST - MCSI","2015-11-20T09:19:04","EACC",null,null,"OF_PIECE","R83_Chine : BEM : Officialisation du BEM pour R83_Chine","2016-07-08","En cours",null,null,"2016-07-08","OTD","2016-06-22","FTR"]
["MCSH-925-L-108831","EST - MCSI","2016-06-15T14:15:42","ELAC",null,null,"DO_DIVERS","_METIER,_QUALITE : _QUALITE : Checklist de robustesse des données qualité à chaque step","2016-07-08","En cours",null,null,"2016-07-08","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-3052-L-106049","AIT - MCSI","2016-04-06T18:04:33","CSAC",null,null,"DO_BE_CESARE","A55_MV : LIDAR (A55MV) : BE A55 pour suppression message ","2016-09-19","En cours",null,null,"2016-07-08","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-8247-L-109109","AIT - MCDV","2016-06-23","ECHP",null,null,"OF_PIECE","_TOUS : _TRAVAUX_CAO : Officialisation d'une pièce","2016-07-15","En cours",null,null,"2016-07-10","DR","2016-10-14","ACCEPTE_DEFAUT"]
["MCSH-8545-L-104790","EST - MCSI","2016-03-17T08:39:48","EACC",null,null,"DO_BE_CESARE","A94_Iran_CKD2 : AVE : Création /Mise à jour BE CESARE","2016-05-01","En cours",null,null,"2016-07-11","Retard",null,"ACCEPTE_DEFAUT"]
["MCSH-7480-L-100346","AIT - MCSI","2015-12-14T11:22:09","CSAC",null,null,"OF_CAL","B751_3_4_MV : RADAR GÉN3 (B753_4  MV) : Calibration pour VRS1","2016-07-08","En cours","2016-07-11","Retard fournisseur","2016-07-11","OTD","2016-07-22","FTR"]
["MCSH-7801-L-108287","EST - MCSI","2016-05-26T08:48:12","ECPC",null,null,"OF_PIECE","X74E : CMD_RETRO_RE : Officialisation d'une pièce\r\nCOMMUTATEUR RETRO version DàD","2016-07-08","En cours",null,null,"2016-07-11","OTD","2016-08-12","ACCEPTE_DEFAUT"]
["MCSH-7486-L-80765","EST - MCSI","2014-12-16T17:48:52","ELPS",null,null,"OF_PIECE","X74E : SIRENE_LIN_SSCAS,RUPTEUR_CAPOT,MUS2 : OCM MUS2 Cheminement Faisceau capteurs US","2016-07-11","En cours","2016-07-11",null,"2016-07-11","OTD","2016-08-12","ACCEPTE_DEFAUT"]
["MCSH-7415-L-98914","EST - MCSI","2015-11-12T14:11:59","ELAC",null,null,"VAL_ANA_PT_FNR","X74E : GRPE_CLIM : Analyse Plan De Test FNR","2016-07-11","En cours",null,null,"2016-07-11","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-8161-L-103260","AIT - MCSI - SMEG","2016-02-15T11:39:22","IDEV",null,null,"OF_DOTE","MODULE_EE07 : SMEG+_I_V2 : Officialisation des DOTE 6.3.B","2016-07-11","En cours",null,null,"2016-07-11","OTD","2016-08-12","ACCEPTE_DEFAUT"]
["MCSH-5876-L-71292","EST - MCSI","2014-06-06T16:15:00","ELAC",null,null,"DO_DIVERS","P84_Chine : GRPE_CLIM : Fichier paramètrage  ADTH ->CAL7 issu mission VRSUT pour PRSEL","2016-04-11","En cours","2016-07-12","Retard fournisseur","2016-07-12","OTD","2016-08-26","FTR"]
["MCSH-6959-L-109013","EST - MCSI","2016-06-22T10:23:28","EACC",null,null,"DO_QIA","C4X,D34E,MODULE_HAB01,P24E : LUMBAFLEX : Issu du QIA Consultation - Fin à RT_PASS_DEV_MET (ce n'est pas un livrable, à mettre dans l'onglet Infos)","2016-07-12","En cours","2016-07-15","Retard fournisseur","2016-07-12","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-7486-L-82085","EST - MCSI","2015-01-09T15:56:14","ELPS",null,null,"OF_PIECE","X74E : SIRENE_LIN_SSCAS,RUPTEUR_CAPOT,MUS2 : OFFI OCM MDT Plan FNR MUS 2\r\n","2016-07-15","En cours","2016-07-01",null,"2016-07-12","OTD","2016-08-15","ACCEPTE_DEFAUT"]
["MCSH-8302-L-99883","EST - MCSI","2015-12-07T14:46:36","ELPS",null,null,"SDF_PSDF_FNR","A9X_F_05_17 : PROJ : Plan de sûreté de fonctionnement du fournisseur. Attendu : AMDEC, AFI, AFE et ADD","2016-02-01","En cours","2016-07-13","Retard fournisseur","2016-07-13","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-8545-L-104794","EST - MCSI","2016-03-17T08:41:54","EACC",null,null,"DO_FC_RFQ","A94_Iran_CKD2 : AVE : Fiches composants pour consultation faisceaux","2016-05-01","En cours",null,null,"2016-07-13","Retard",null,"ACCEPTE_DEFAUT"]
["MCSH-8161-L-109528","AIT - MCSI - SMEG","2016-07-06T16:15:52","IDEV",null,null,"OF_PIECE","_F09/2016 : SMEG+_I_V2 : Officialisation des références de vis pour A9 et A5 Poissy ","2016-07-07","En cours",null,null,"2016-07-13","NDR","2016-08-15","ACCEPTE_DEFAUT"]
["MCSH-8304-L-99948","EST - MCSI","2015-12-07T16:49:28","ELPS",null,null,"SDF_NS","A9X_F_05_17 : PROJ (_STT) : Avis et Synthèse SDF sur organe","2016-07-13","En cours",null,null,"2016-07-13","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-2916-L-107955","AIT - MCSI","2016-05-19T01:56:06","CSAC",null,null,"DO_PEPP","A55_MV,A9MV,A5X_F_05_16,A94_MV,B9_Mi_Vie_2_F11/2015,F3,MODULE_EE02 : LIDAR : Réactivité 120j Buée Lidar: PEPP Démarrage","2016-07-13","En cours",null,null,"2016-07-13","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-8071-L-108878","EST - MCSI","2016-06-16T17:49:11","EACC",null,null,"DO_EDS","C84_Export : AVE (C84_Chine,C84_Export) : Renseigner OPHELIE EDS Tool","2016-07-15","En cours",null,null,"2016-07-13","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-3039-L-109599","AIT - MCSI","2016-07-08T09:04:03","CSAC",null,null,"OF_PIECE","MODULE_EE02 : CVM : Officialisation module de la CVM niv1 et niv2 (D5.2f)","2016-07-15","En cours",null,null,"2016-07-13","DR","2016-07-26","FTR"]
["MCSH-5674-L-106046","AIT - MCSI","2016-04-06T18:01:59","CSAC",null,null,"DO_BE_CESARE","B9_Mi_Vie_2_F11/2015 : LIDAR (B9MV2) : BE B9MV_2 VP pour suppression message ","2016-09-09","En cours",null,null,"2016-07-13","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-5674-L-106047","AIT - MCSI","2016-04-06T06:02:41","CSAC",null,null,"DO_BE_CESARE","B9_Mi_Vie_2_F11/2015 : LIDAR (B9MV2) : BE B9MV_2 VU pour suppression message ","2016-09-09","En cours",null,null,"2016-07-13","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-5674-L-106048","AIT - MCSI","2016-04-06T06:02:41","CSAC",null,null,"DO_BE_CESARE","B9_Mi_Vie_2_F11/2015 : LIDAR (B9MV2) : BE B9MV_2 CROSSOVER pour suppression message ","2016-09-09","En cours",null,null,"2016-07-13","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-4127-L-85629","EST - MCSI","2015-03-02T16:05:12","EACC",null,null,"DO_INC_VALID","C84_Export,MODULE_CPE09,P1UO,P8X,X74E : RETRO_EXT : Incontournables partie validation P8x","2015-12-21","En cours","2016-05-06","Retard fournisseur","2016-07-14","Retard",null,"ACCEPTE_DEFAUT"]
["MCSH-7164-L-77088","AIT - MCSI","2014-10-15T10:49:19","CSAC",null,null,"DO_CESARE","P84_Chine : RADAR GÉN3 (P84_C) : Livraison BE CESARE EL2","2016-07-12","En cours","2016-07-15","Retard fournisseur","2016-07-14","OTD","2016-07-22","FTR"]
["MCSH-7415-L-99873","EST - MCSI","2015-12-07T14:14:23","ELAC",null,null,"OF_PIECE","X74E : GRPE_CLIM : Officialisation faisceau groupe ref 1. (CH 1Z)","2016-07-15","En cours","2016-07-15",null,"2016-07-14","OTD","2016-08-15","ACCEPTE_DEFAUT"]
["MCSH-7415-L-99878","EST - MCSI","2015-12-07T02:20:35","ELAC",null,null,"OF_PIECE","X74E : GRPE_CLIM : Officialisation faisceau groupe ref 6. (RFTA sans AQS K0 )","2016-07-15","En cours","2016-07-15",null,"2016-07-14","OTD","2016-08-15","ACCEPTE_DEFAUT"]
["MCSH-3536-L-109902","AIT - MCSI","2016-07-19T17:45:18","CSAC",null,null,"DO_BE_CESARE","P8X : VISIO_PARK (P8) : Création /Mise à jour BE CESARE P87 Mainstream","2016-07-29","En cours",null,null,"2016-07-14","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-3536-L-109903","AIT - MCSI","2016-07-19T05:46:22","CSAC",null,null,"DO_BE_CESARE","P8X : VISIO_PARK (P8) : Création /Mise à jour BE CESARE P87 Upper","2016-07-29","En cours",null,null,"2016-07-14","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-7373-L-106642","EST - MCSI","2016-04-15T16:13:30","EACC",null,null,"DO_EDS","R82E,R83E,R83_Chine : BEM : Renseigner OPHELIE EDS Tool","2016-07-15","En cours",null,null,"2016-07-15","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7486-L-106475","EST - MCSI","2016-04-13T09:55:29","ELPS",null,null,"OF_PIECE","X74E : SIRENE_LIN_SSCAS,RUPTEUR_CAPOT,MUS2 : Officialisation d'une pièce MUS2\r\nREC def MDT sur X74","2016-06-17","En cours","2016-07-18","Retard fournisseur","2016-07-18","OTD","2016-08-19","ACCEPTE_DEFAUT"]
["MCSH-7164-L-77089","AIT - MCSI","2014-10-15T10:49:19","CSAC",null,null,"OF_CAL","P84_Chine : RADAR GÉN3 (P84_C) : Calibration pour EL2","2016-07-12","En cours","2016-07-18","Retard fournisseur","2016-07-18","OTD","2016-07-22","FTR"]
["MCSH-5893-L-109089","AIT - MCSI","2016-06-23T15:26:56","CSAC",null,null,"OF_PIECE","P1MO : CVM (A88,P1MO) : P1MO: Reconduction CVM VAEB SW6 pour MVBNs","2016-07-15","En cours","2016-07-18",null,"2016-07-18","DR","2016-07-26","FTR"]
["MCSH-5893-L-109092","AIT - MCSI","2016-06-23T15:52:30","CSAC",null,null,"OF_PIECE","A88 : CVM (A88,P1MO) : A88: Reconduction CVM VAEB SW6 pour PPV3","2016-07-15","En cours",null,null,"2016-07-18","NDR","2016-08-05","FTR"]
["MCSH-7034-L-109512","AIT - MCSI","2016-07-06T09:10:12","CSAC",null,null,"OF_DOTE","B78_mi_vie : CVM (B78_mi_vie) : Officialisation de DOTE VS","2016-07-15","En cours",null,null,"2016-07-18","NDR","2016-08-05","FTR"]
["MCSH-3533-L-109649","AIT - MCSI","2016-07-12T15:31:10","CSAC",null,null,"OF_PIECE","P8X : CVM (P8) : P84 & P87: Reconduction CVM niv1 & 2 D5.2f","2016-07-18","En cours",null,null,"2016-07-18","DR","2016-07-26","FTR"]
["MCSH-7034-L-109763","AIT - MCSI","2016-07-13T13:51:28","CSAC",null,null,"DO_CESARE","B78_mi_vie : CVM (B78_mi_vie) : BE CVM niv2 en configuration D5.2d avec nouveau DOTE","2016-07-18","En cours",null,null,"2016-07-18","DR","2016-07-26","FTR"]
["MCSH-6127-L-109283","AIT - MCSI","2016-06-29T09:04:39","CSAC",null,null,"OF_CAL","X81_Chine : VISIO_PARK (X81_Chine) : Officialisation d'une calibration VP2 pour X81C","2016-07-22","En cours",null,null,"2016-07-18","DR","2016-08-19","ACCEPTE_DEFAUT"]
["MCSH-6127-L-109899","AIT - MCSI","2016-07-19T17:34:37","CSAC",null,null,"DO_BE_CESARE","X81_Chine : VISIO_PARK (X81_Chine) : Création /Mise à jour BE CESARE","2016-07-22","En cours",null,null,"2016-07-18","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-7236-L-109901","AIT - MCSI","2016-07-19T17:44:10","CSAC",null,null,"DO_BE_CESARE","P84_Chine : VISIO_PARK (P84 Chine) : Création /Mise à jour BE CESARE","2016-07-29","En cours",null,null,"2016-07-18","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-7482-L-80710","EST - MCSI","2014-12-16T15:24:57","ELPS",null,null,"OF_PIECE","K9 : SIRENE_LIN_SSCAS,RUPTEUR_CAPOT,MUS2 : DEF Cheminement faisceau pour VRS1","2016-05-20","En cours","2016-07-19","Retard fournisseur","2016-07-19","OTD","2016-08-05","FTR"]
["MCSH-7482-L-80711","EST - MCSI","2014-12-16T15:24:57","ELPS",null,null,"OF_PIECE","K9 : SIRENE_LIN_SSCAS,RUPTEUR_CAPOT,MUS2 : DEF Rupteur Capot avec implantation définitive","2016-05-20","En cours","2016-07-19","Retard fournisseur","2016-07-19","OTD","2016-08-19","FTR"]
["MCSH-7953-L-109348","AIT - MCSI - NAC","2016-06-30T18:00:52","IVI",null,null,"OF_PIECE","MODULE_EE07 : NAC Wave 3 : Officialisation module HW C SW V3","2016-06-10","En cours",null,null,"2016-07-19","NDR","2016-08-22","ACCEPTE_DEFAUT"]
["MCSH-8419-L-109168","EST - MCSI","2016-06-24T16:39:53","ECPC",null,null,"OF_PIECE","B9_Mi_Vie_2 : PUSH_LVE_AV,PUSH_LVI_AV : Officialisation (REC) 3D/2D FNR (DIL EE) - Push LVI B78 VALEO","2016-07-08","En cours","2016-07-19",null,"2016-07-19","DR","2016-08-22","ACCEPTE_DEFAUT"]
["MCSH-8419-L-109169","EST - MCSI","2016-06-24T16:40:59","ECPC",null,null,"OF_PIECE","B9_Mi_Vie_2 : PUSH_LVE_AV,PUSH_LVI_AV : Officialisation (REC) 3D/2D FNR (DIL MECA) - Push LVE A9 VALEO","2016-07-08","En cours","2016-07-31",null,"2016-07-19","DR","2016-08-22","ACCEPTE_DEFAUT"]
["MCSH-7363-L-109245","AIT - MCSI","2016-06-28T13:59:16","CSAC",null,null,"OF_PIECE","C84_Chine : CVM (C84) : VRSDV: Reconduction de la CVM VAEB SW6","2016-07-13","En cours","2016-07-18",null,"2016-07-19","NDR","2016-08-05","FTR"]
["MCSH-2178-L-105867","EST - MCSI","2016-04-04T13:56:53","ELPS",null,null,"OF_PIECE","MODULE_EE03 : MUS2 (Dev.MUS2) : Officialisation d'une pièce MDT EE03 3 x100mm","2016-07-15","En cours","2016-07-19","Retard fournisseur","2016-07-19","OTD","2016-08-22","ACCEPTE_DEFAUT"]
["MCSH-7343-L-101477","AIT - MCSI","2016-01-12T10:24:28","CSAC",null,null,"OF_PIECE","K9 : CVM (K9) : Officialisation d'une pièce","2016-07-29","En cours",null,null,"2016-07-19","OTD","2016-08-01","FTR"]
["MCSH-7236-L-109900","AIT - MCSI","2016-07-19T17:43:10","CSAC",null,null,"OF_CAL","P84_Chine : VISIO_PARK (P84 Chine) : Officialisation d'une calibration","2016-07-29","En cours",null,null,"2016-07-19","DR","2016-08-22","ACCEPTE_DEFAUT"]
["MCSH-8545-L-104793","EST - MCSI","2016-03-17T08:40:23","EACC",null,null,"DO_EDS","A94_Iran_CKD2 : AVE : Renseigner OPHELIE EDS Tool","2016-05-01","En cours",null,null,"2016-07-20","Retard",null,"ACCEPTE_DEFAUT"]
["MCSH-1862-L-107532","EST - MCSI","2016-05-09T10:35:53","EACC",null,null,"DO_EDS","A94_Chine,A94_Iran_CKD2,B78 : SECU_DML (Rec. A94_Chine,A94_Iran_CKD2,B78) : Renseigner OPHELIE EDS Tool","2016-05-31","En cours","2016-07-20","Retard fournisseur","2016-07-20","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-3533-L-109650","AIT - MCSI","2016-07-12T15:35:42","CSAC",null,null,"DO_CESARE","P8X : CVM (P8) : P84 & P87: BE D5.2f pour CVM niv1 & 2","2016-07-20","En cours","2016-07-19",null,"2016-07-20","DR","2016-07-26","FTR"]
["MCSH-3536-L-61687","AIT - MCSI","2014-01-09T04:43:15","CSAC",null,null,"OF_CAL","P8X : VISIO_PARK (P8) : Officialisation d'une calibration : CAL VP2 pour P87","2016-07-29","En cours","2016-07-10",null,"2016-07-20","OTD","2016-08-22","ACCEPTE_DEFAUT"]
["MCSH-5674-L-105830","AIT - MCSI","2016-04-01T15:55:37","CSAC",null,null,"OF_CAL","B9_Mi_Vie_2_F11/2015 : LIDAR (B9MV2) : Officialisation Calibration B9MV_2 VP pour suppression message ","2016-09-09","En cours",null,null,"2016-07-20","OTD","2016-07-21","FTR"]
["MCSH-5674-L-106044","AIT - MCSI","2016-04-06T06:00:31","CSAC",null,null,"OF_CAL","B9_Mi_Vie_2_F11/2015 : LIDAR (B9MV2) : Officialisation Calibration B9MV_2 VU pour suppression message ","2016-09-09","En cours",null,null,"2016-07-20","OTD","2016-07-21","FTR"]
["MCSH-5674-L-106045","AIT - MCSI","2016-04-06T06:00:31","CSAC",null,null,"OF_CAL","B9_Mi_Vie_2_F11/2015 : LIDAR (B9MV2) : Officialisation Calibration B9MV_2 CROSSOVER pour suppression message ","2016-09-09","En cours",null,null,"2016-07-20","OTD","2016-07-21","FTR"]
["MCSH-3619-L-34839","EST - MCSI","2012-12-20T16:50:34","EACC",null,null,"VAL_ANA_RAPP_ESSAIS","K0,MODULE_CE_MDT : AOS,SERRURE_PORTE : Phase=PV FNR|","2015-09-15","En cours","2016-07-22","Retard fournisseur","2016-07-21","OTD","2016-07-26","FTR"]
["MCSH-3619-L-34843","EST - MCSI","2012-12-20T16:50:34","EACC",null,null,"VAL_BILAN","K0,MODULE_CE_MDT : AOS,SERRURE_PORTE : Phase=PV|","2015-10-15","En cours","2016-07-22","Retard fournisseur","2016-07-21","OTD","2016-07-26","FTR"]
["MCSH-3042-L-109238","AIT - MCSI","2016-06-28T11:19:26","CSAC",null,null,"OF_CAL","K0 : RADAR GÉN3 (K0) : CALs D5.3b (EL1s F05/2017)","2016-07-22","En cours",null,null,"2016-07-21","DR","2016-07-22","FTR"]
["MCSH-5893-L-109930","AIT - MCSI","2016-07-21T16:19:55","CSAC",null,null,"OF_CAL","P1MO : CVM (A88,P1MO) : Calibration CVM Gen 2 Niveau 1 (D5.2d + SW5d) pour stade PPV2 P1MO version DàG (LHD) et DàD (RHD)","2016-07-25","En cours",null,null,"2016-07-21","DR","2016-07-26","FTR"]
["MCSH-5893-L-109931","AIT - MCSI","2016-07-21T16:20:07","CSAC",null,null,"OF_CAL","A88 : CVM (A88,P1MO) : Calibration CVM Gen 2 Niveau 1 (D5.2d + SW5d) pour stade PPV1 A88 version DàG (LHD) et DàD (RHD)","2016-07-25","En cours",null,null,"2016-07-21","DR","2016-07-26","FTR"]
["MCSH-5893-L-109932","AIT - MCSI","2016-07-21T17:11:04","CSAC",null,null,"DO_CESARE","P1MO : CVM (A88,P1MO) : BE CVM Gen 2 Niv1 et niv3 pour mise à jour en PPV2 P1MO","2016-07-25","En cours",null,null,"2016-07-21","DR","2016-07-26","FTR"]
["MCSH-5893-L-109933","AIT - MCSI","2016-07-21T17:13:44","CSAC",null,null,"DO_CESARE","A88 : CVM (A88,P1MO) : BE CVM Gen 2 Niv1 et niv3 pour mise à jour en PPV1 A88","2016-07-25","En cours",null,null,"2016-07-21","DR","2016-07-26","FTR"]
["MCSH-7787-L-88056","EST - MCSI","2015-04-08T14:43:39","ECPC",null,null,"OF_PIECE","K9 : PUSH_LVI_AR,PUSH_LVI_AV : Officialisation DFNU - FNR\r\nPUSH LVI AR VALEO","2016-07-29","En cours","2016-07-15",null,"2016-07-21","OTD","2016-08-05","FTR"]
["MCSH-3042-L-109241","AIT - MCSI","2016-06-28T11:21:36","CSAC",null,null,"DO_CESARE","K0 : RADAR GÉN3 (K0) : Livraison BEs CESARE D5.3","2016-09-09","En cours",null,null,"2016-07-21","OTD","2016-07-22","FTR"]
["MCSH-2937-L-55449","EST - MCSI","2013-09-23T16:39:20","ELPS",null,null,"DO_QUALIF_PROD","K0 : PROJ : Acceptation Qualification Produit (synthèse Q3P)","2015-11-02","En cours","2016-07-30","Retard fournisseur","2016-07-22","OTD","2016-08-23","ACCEPTE_DEFAUT"]
["MCSH-7186-L-92239","EST - MCSI","2015-06-08T09:28:39","EACC",null,null,"RT_HW","B618,R82E,R83E : POMPES_LV_LP : Revue Technique de Conception Préliminaire Electronique","2015-11-20","En cours","2016-07-29","Retard fournisseur","2016-07-22","OTD","2016-07-25","FTR"]
["MCSH-7186-L-92245","EST - MCSI","2015-06-08T09:28:39","EACC",null,null,"VAL_ANA_PV_FNR","B618,R82E,R83E : POMPES_LV_LP : Analyse du planning de validation fournisseur","2016-01-08","En cours","2016-07-29","Retard fournisseur","2016-07-22","OTD","2016-11-22","NOT FTR"]
["MCSH-5876-L-75863","EST - MCSI","2014-09-26T02:22:27","ELAC",null,null,"DO_DIVERS","P84_Chine : GRPE_CLIM : Fichier paramètrage  ADTH ->CAL8 issu mission VRSUT pour PRSEL2","2016-05-30","En cours","2016-07-22","Retard fournisseur","2016-07-22","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-5616-L-99545","EST - MCSI","2015-11-26T11:19:29","ELAC",null,null,"PROGRES","_METIER : LDA / référentiel technique CLIM : Guide des livrables CLIM à traduire en anglais ","2016-07-22","En cours",null,null,"2016-07-22","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-6555-L-108858","EST - MCSI","2016-06-16T10:21:11","ELAC",null,null,"OF_SDP","A88 : GRPE_CLIM : Officialisation de Schéma de Principe","2016-07-31","En cours",null,null,"2016-07-22","OTD","2016-08-23","ACCEPTE_DEFAUT"]
["MCSH-8481-L-103593","EST - MCSI","2016-02-18T17:03:44","ELAC",null,null,"OF_PIECE","_DMTRless_ELAC : TDC_RF2 : Officialisation d'une pièce","2016-09-02","En cours",null,null,"2016-07-22","OTD","2016-08-05","FTR"]
["MCSH-5893-L-109088","AIT - MCSI","2016-06-23T15:26:36","CSAC",null,null,"OF_PIECE","P1MO : CVM (A88,P1MO) : P1MO: Reconduction CVM niv1 D5.3 pour MVBns (EL1)","2016-07-25","En cours",null,null,"2016-07-25","DR","2016-07-27","FTR"]
["MCSH-5893-L-109091","AIT - MCSI","2016-06-23T15:52:05","CSAC",null,null,"OF_PIECE","A88 : CVM (A88,P1MO) : A88: Reconduction CVM niv1 D5.3 pour PPV3","2016-07-25","En cours",null,null,"2016-07-25","DR","2016-07-27","FTR"]
["MCSH-4192-L-109924","AIT - MCSI","2016-07-21T11:36:50","CSAC",null,null,"OF_PIECE","X81_Chine : CVM (X81_Chine) : Reconduction CVM niv2 D5.2f (lancement 07/2016)","2016-07-25","En cours",null,null,"2016-07-25","DR","2016-07-27","FTR"]
["MCSH-8246-L-105515","AIT - MCDV","2016-03-30","HDTC",null,null,"OF_PIECE","_TOUS : _TRAVAUX_CAO : Création et officialisation de référence FNR du support faisceau NOX pour DV5R, et rattachement au FCT 9814415180","2016-04-22","En cours","2016-07-30","Retard fournisseur","2016-07-26","DR","2016-08-29","ACCEPTE_DEFAUT"]
["MCSH-7953-L-109529","AIT - MCSI - NAC","2016-07-06T17:47:46","IVI",null,null,"OF_PIECE","X74E : NAC Wave 3 : Officialisation REC HW C SW V3 sur X74","2016-07-22","En cours",null,null,"2016-07-26","NDR","2016-08-29","ACCEPTE_DEFAUT"]
["MCSH-3382-L-85497","AIT - MCSI","2015-02-27T16:20:46","CSAC",null,null,"OF_DOC","MODULE_EE02 : CVP : Officialisation du PCP","2016-07-29","En cours","2016-05-27","Retard fournisseur","2016-07-26","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7154-L-109120","AIT - MCSI","2016-06-24T08:50:27","CSAC",null,null,"OF_PIECE","P1UO : CVM (P1UO) : VRSUT: Reconduction des 3 variantes CVM","2016-07-29","En cours","2016-07-29",null,"2016-07-26","DR","2016-08-18","FTR"]
["MCSH-7684-L-109898","AIT - MCSI","2016-07-19T17:13:30","CSAC",null,null,"OF_PIECE","X74E : VISIO_PARK (X74E) : REC ECU VP2 Module ADAS Vague 2 sur X74","2016-07-29","En cours",null,null,"2016-07-26","DR","2016-08-29","ACCEPTE_DEFAUT"]
["MCSH-7480-L-110155","AIT - MCSI","2016-07-25T06:52:12","CSAC",null,null,"OF_CAL","B751_3_4_MV : RADAR GÉN3 (B753_4  MV) : Ajout GMPs China 6 sur Cals Officialisées pour VRS0","2016-07-29","En cours",null,null,"2016-07-26","DR","2016-08-05","FTR"]
["MCSH-8301-L-100190","AIT - MCSI","2015-12-10T14:42:45","CSAC",null,null,"DO_CDCI_BILAN","F3 : CVM (F3) : Bilan des retours des CDCI","2016-07-27","En cours","2016-06-17","Retard fournisseur","2016-07-27","OTD","2016-08-18","FTR"]
["MCSH-8301-L-100191","AIT - MCSI","2015-12-10T14:42:45","CSAC",null,null,"RT_CDCI","F3 : CVM (F3) : Revue technique de CDCI","2016-07-27","En cours","2016-06-17","Retard fournisseur","2016-07-27","OTD","2016-08-18","FTR"]
["MCSH-7064-L-111181","AIT - MCSI","2016-08-18T09:57:18","CSAC",null,null,"DO_CESARE","P84_Chine : CVM (P84_C) : BE CVM niv1 & 2 D5.2f","2016-07-27","En cours",null,null,"2016-07-27","DR","2016-09-26","FTR"]
["MCSH-3053-L-109970","AIT - MCSI","2016-07-21T17:49:53","CSAC",null,null,"DO_DIVERS","A9MV : LIDAR (A9MV) : Fiche ATI A9MV suite à réactivité 120j Lidar","2016-07-28","En cours",null,null,"2016-07-27","DR","2016-07-27","FTR"]
["MCSH-7034-L-110697","AIT - MCSI","2016-07-29T14:46:29","CSAC",null,null,"OF_PIECE","B78_mi_vie : CVM (B78_mi_vie) : REC CVM niv2 D5.2f","2016-07-29","En cours",null,null,"2016-07-27","DR","2016-08-08","FTR"]
["MCSH-4192-L-110441","AIT - MCSI","2016-07-27T15:47:49","CSAC",null,null,"DO_CESARE","X81_Chine : CVM (X81_Chine) : BE CVM D5.2f: Configuration D5.2d pièce + D5.2f soft","2016-08-05","En cours",null,null,"2016-07-27","DR","2016-08-08","FTR"]
["MCSH-4192-L-110442","AIT - MCSI","2016-07-27T15:48:16","CSAC",null,null,"DO_CESARE","X81_Chine : CVM (X81_Chine) : BE CVM D5.2f: Configuration Full D5.2f","2016-08-05","En cours",null,null,"2016-07-27","DR","2016-08-08","FTR"]
["MCSH-4127-L-85631","EST - MCSI","2015-03-02T16:05:37","EACC",null,null,"DO_INC_VALID","C84_Export,MODULE_CPE09,P1UO,P8X,X74E : RETRO_EXT : Incontournables partie validation P1UO","2015-11-16","En cours","2016-07-29","Retard fournisseur","2016-07-28","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7156-L-82869","EST - MCSI","2015-01-20T13:57:45","EACC",null,null,"DO_EXP_BES_PIECES","D34E,R82E,R83E,R83_Chine,X83_Chine,MODULE_CPE09 : RETRO_EXT : Expression de besoin pièces. Initialiser l'expression de besoin des pièces nécessaires pour les TU en cohérence avec le PVO","2015-02-12","En cours","2016-08-05","Retard fournisseur","2016-07-29","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-6027-L-108401","EST - MCSI","2016-06-02T10:07:58","ECPC",null,null,"RI_TOP_RO","R83E : PUSH_TO_VELUM : Revue Technique d'interface pour robustesse avant top RO\r\n(idem ARIS)","2016-03-03","En cours","2016-07-31","Evolution donnée d'entrée","2016-07-29","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-7953-L-109530","AIT - MCSI - NAC","2016-07-06T17:52:21","IVI",null,null,"OF_PIECE","R83E : NAC Wave 3 : Officialisation REC HW C SW V3 sur R83","2016-07-13","En cours",null,null,"2016-07-29","NDR","2016-08-30","ACCEPTE_DEFAUT"]
["MCSH-7486-L-80768","EST - MCSI","2014-12-16T17:48:52","ELPS",null,null,"OF_DOTE","X74E : SIRENE_LIN_SSCAS,RUPTEUR_CAPOT,MUS2 : DOTE pour VRS1","2016-07-29","En cours",null,null,"2016-07-29","OTD","2016-08-19","FTR"]
["MCSH-6027-L-108402","EST - MCSI","2016-06-02T10:07:58","ECPC",null,null,"OF_PIECE","R83E : PUSH_TO_VELUM : Officialisation (REC) 3D/2D Fonctionnel - Module TO/VELUM ","2016-07-29","En cours","2016-07-31",null,"2016-07-29","OTD","2016-08-30","ACCEPTE_DEFAUT"]
["MCSH-7121-L-109184","AIT - MCSI","2016-06-27T09:22:16","CSAC",null,null,"OF_PIECE","T9_MV : CVM (T9MV) : Reconduction CVM niv2 D5.3 pour EL1","2016-07-29","En cours",null,null,"2016-07-29","DR","2016-08-18","FTR"]
["MCSH-7154-L-109653","AIT - MCSI","2016-07-12T16:40:07","CSAC",null,null,"OF_DOTE","P1UO : CVM (P1UO) : Officialisation DOTE pour VRSUT","2016-07-29","En cours","2016-07-29",null,"2016-07-29","DR","2016-08-18","FTR"]
["MCSH-3036-L-110517","AIT - MCSI","2016-07-29T08:42:47","CSAC",null,null,"SYN_ALTIS ","B751_3_4_MV,B78_mi_vie,B81_Chine_Fenêtre_VS,C84_Chine,G95_PH2,K0,MODULE_EE02,P1UO,P84_Chine,P87_Chine,P8X,T9_MV,X81_Chine : RADAR GÉN3 : Gestion Hebdomadaire Altis\r\n","2016-07-29","En cours",null,null,"2016-07-29","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-3036-L-110631","AIT - MCSI","2016-07-29T08:48:27","CSAC",null,null,"DO_CDCI_BILAN","B751_3_4_MV,B78_mi_vie,B81_Chine_Fenêtre_VS,C84_Chine,G95_PH2,K0,MODULE_EE02,P1UO,P84_Chine,P87_Chine,P8X,T9_MV,X81_Chine : RADAR GÉN3 : Synthèses d'avancement de toutes les implantation Radar / Fichier de pilotage interne et avec fournisseur.","2016-07-29","En cours",null,null,"2016-07-29","DR","2016-08-05","FTR"]
["MCSH-8246-L-109437","AIT - MCDV","2016-07-04","HDTC",null,null,"OF_PIECE","_TOUS : _TRAVAUX_CAO : Officialisation d'une pièce","2016-07-30","En cours",null,null,"2016-07-30","DR","2016-08-31","ACCEPTE_DEFAUT"]
["MCSH-8246-L-109438","AIT - MCDV","2016-07-04","HDTC",null,null,"OF_PIECE","_TOUS : _TRAVAUX_CAO : Officialisation d'une pièce","2016-07-30","En cours",null,null,"2016-07-30","DR","2016-08-31","ACCEPTE_DEFAUT"]
["MCSH-3540-L-93859","AIT - MCSI","2015-07-02T14:38:07","CSAC",null,null,"DO_CESARE","P8X,P8_Europe_VS_Fenetre : RADAR GÉN3 (P8X) : Livraison BE D5.4 CESARE EL2 (TMC 11 selon FSP V13)","2016-08-03","En cours",null,null,"2016-08-01","OTD","2016-08-05","FTR"]
["MCSH-3540-L-93860","AIT - MCSI","2015-07-02T14:38:07","CSAC",null,null,"OF_CAL","P8X : RADAR GÉN3 (P8X) : CAL D5.4 EL2 (TMC 11 selon FSP V13)","2016-08-03","En cours",null,null,"2016-08-02","OTD","2016-08-05","FTR"]
["MCSH-7010-L-92225","EST - MCSI","2015-06-08T09:16:41","EACC",null,null,"DO_CCA_TOPHW","K9,MODULE_CPE02 : EVAV : Fiche CCA phase 2 (conception)","2016-08-03","En cours","2016-08-19","Retard fournisseur","2016-08-03","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7010-L-92226","EST - MCSI","2015-06-08T09:16:41","EACC",null,null,"DO_INC_CONCEPT","K9,MODULE_CPE02 : EVAV : Incontournables partie conception","2016-08-03","En cours","2016-08-19","Retard fournisseur","2016-08-03","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-3040-L-110706","AIT - MCSI","2016-08-01T08:49:36","CSAC",null,null,"OF_PIECE","K0 : CVM (K0) : Reconduction CVM niv2 D5.2f","2016-08-03","En cours",null,null,"2016-08-03","DR","2016-08-08","FTR"]
["MCSH-5891-L-110710","AIT - MCSI","2016-08-01T10:02:58","CSAC",null,null,"OF_PIECE","B618 : CVM (B618) : Reconduction CVM niv1 D5.2f","2016-08-03","En cours",null,null,"2016-08-03","DR","2016-08-18","FTR"]
["MCSH-8302-L-99901","EST - MCSI","2015-12-07T14:46:36","ELPS",null,null,"RI_CONTRAINTES","A9X_F_05_17 : PROJ : Revue technique d'interface HW avec BSLE et CA2E","2016-02-29","En cours","2016-08-04","Retard fournisseur","2016-08-04","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7358-L-106712","EST - MCSI","2016-04-18T09:50:41","ELPS",null,null,"RI_CONTRAINTES","D34E : FEUX_AR : Revue technique d'interface HW avec BSLE et CA2E","2016-06-13","En cours","2016-09-15","Evolution donnée d'entrée","2016-08-04","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7362-L-96409","AIT - MCSI","2015-09-08T09:54:00","CSAC",null,null,"DO_CESARE","C84_Chine : RADAR GÉN3 (C84) : Livraison BE VRS DV (D5.3b)","2016-08-04","En cours",null,null,"2016-08-04","OTD","2016-08-05","FTR"]
["MCSH-4192-L-110443","AIT - MCSI","2016-07-27T15:48:35","CSAC",null,null,"DO_CESARE","X81_Chine : CVM (X81_Chine) : BE CVM D5.2f: Configuration D5.2d pièce + D5.2f soft + CAL new support","2016-08-05","En cours",null,null,"2016-08-04","DR","2016-08-08","FTR"]
["MCSH-4192-L-110445","AIT - MCSI","2016-07-27T16:14:17","CSAC",null,null,"DO_CESARE","X81_Chine : CVM (X81_Chine) : BE CVM D5.2f: Configuration full D5.2f + CAL new support","2016-08-05","En cours",null,null,"2016-08-04","DR","2016-08-08","FTR"]
["MCSH-6437-L-95813","EST - MCSI","2015-08-19T08:47:18","ELAC",null,null,"RT_PV","B618 : TDC_CH_RF : Revue fin PV avec le Fnr ( Validation Fonct, EE, Meca, Envir)","2016-08-12","En cours",null,null,"2016-08-04","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-6555-L-65053","EST - MCSI","2014-02-21T14:19:28","ELAC",null,null,"DO_ETAT_ACCEPT","A88 : GRPE_CLIM : Etat d'acceptation Produit (pièce R2)","2016-04-15","En cours","2016-08-19","Blocage technique","2016-08-05","OTD","2016-09-06","ACCEPTE_DEFAUT"]
["MCSH-6555-L-65063","EST - MCSI","2014-02-21T14:19:28","ELAC",null,null,"DO_ETAT_ACCEPT","P1MO : GRPE_CLIM : Etat d'acceptation Produit (pièce R2)","2016-05-19","En cours","2016-08-19","Blocage technique","2016-08-05","OTD","2016-08-26","FTR"]
["MCSH-7505-L-108038","EST - MCSI","2016-05-23T13:53:30","ELPS",null,null,"OF_PIECE","_VS :  (MUS, Rupteur, Sirène, AUS, ) : Officialisation d'une pièce\r\nSIRENE avec plan Homologation","2016-08-05","En cours",null,null,"2016-08-05","OTD","2016-08-05","FTR"]
["MCSH-4192-L-110436","AIT - MCSI","2016-07-27T12:02:20","CSAC",null,null,"OF_CAL","X81_Chine : CVM (X81_Chine) : Officialisation d'une calibration CVM D5.2f","2016-08-05","En cours",null,null,"2016-08-05","DR","2016-08-08","FTR"]
["MCSH-3040-L-110711","AIT - MCSI","2016-08-01T10:34:33","CSAC",null,null,"DO_CESARE","K0 : CVM (K0) : BE CVM niv2 D5.2f (VS)","2016-08-05","En cours",null,null,"2016-08-05","DR","2016-08-18","FTR"]
["MCSH-925-L-110924","EST - MCSI","2016-08-04T01:22:56","ELAC",null,null,"DO_DIVERS","_METIER,_QUALITE : _QUALITE : Indicateurs qualité ELAC de Juillet (données de Juin)","2016-08-05","En cours",null,null,"2016-08-05","DR","2016-11-21","NOT FTR"]
["MCSH-7034-L-111015","AIT - MCSI","2016-08-08T14:56:07","CSAC",null,null,"DO_CESARE","B78_mi_vie : CVM (B78_mi_vie) : BE CVM niv2 D5.2f: Config réf pièce D5.2d + soft D5.2f","2016-08-05","En cours",null,null,"2016-08-05","DR","2016-08-18","FTR"]
["MCSH-7034-L-111016","AIT - MCSI","2016-08-08T14:56:22","CSAC",null,null,"DO_CESARE","B78_mi_vie : CVM (B78_mi_vie) : BE CVM niv2 D5.2f: full D5.2f","2016-08-05","En cours",null,null,"2016-08-05","DR","2016-08-18","FTR"]
["MCSH-5891-L-111165","AIT - MCSI","2016-08-17T14:41:30","CSAC",null,null,"DO_CESARE","B618 : CVM (B618) : (F09/2016): BE CVM niv1 D5.2f","2016-08-05","En cours",null,null,"2016-08-05","DR","2016-09-26","FTR"]
["MCSH-7066-L-111183","AIT - MCSI","2016-08-18T10:26:02","CSAC",null,null,"DO_CESARE","G95_PH2,MODULE_EE02 : CVM (G95 Ph2) : BE pour CVM niv2 D5.2f","2016-08-05","En cours",null,null,"2016-08-05","DR","2016-09-21","FTR"]
["MCSH-5891-L-111162","AIT - MCSI","2016-08-17T11:10:45","CSAC",null,null,"OF_PIECE","B618 : CVM (B618) : EL1 (F05.2017): Reconduction CVM niv3 VAEB SW6","2016-08-19","En cours",null,null,"2016-08-08","DR","2016-08-18","FTR"]
["MCSH-2509-L-106484","AIT - MCSI","2016-04-13T11:45:36","SWES",null,null,"ANI_GARANTIE","MODULE_HAB10,A58VS,Ai51M,B9,B9E,G9,T1_Iran,T3,T3_Iran,T61_Chine,T7,T7xA,T73,T7x_Mercosur,T73_Chine,T73_Malaisie,T73_Russie,T75,T76,T7H : COM2005_EV3 (Delphi : Suivi Vie Série) : Le FNR complète le Gate Chart. Le CD joint le CR de la séance. Fréquence des séances à définir par le CD","2016-05-31","En cours","2016-08-09","Blocage technique","2016-08-09","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-8247-L-109770","AIT - MCDV","2016-07-14","ECHP",null,null,"OF_PIECE","_TOUS : _TRAVAUX_CAO : Officialisation d'une pièce","2016-07-29","En cours","2016-08-09",null,"2016-08-09","DR","2016-10-14","ACCEPTE_DEFAUT"]
["MCSH-8629-L-107462","EST - MCSI","2016-05-04T09:06:31","EACC",null,null,"DO_EDS","B73_Russie,B73_Russie_Mi_Vie,T73_Russie_VS_MV : POMPES_LV_LP : Renseigner OPHELIE EDS Tool pour le stade consolidé","2016-08-09","En cours","2016-08-12","Retard fournisseur","2016-08-09","OTD","2016-08-25","FTR"]
["MCSH-8562-L-106403","AIT - MCSI","2016-04-11T14:14:50","SWES",null,null,"VAL_ANA_PT_FNR","MODULE_HAB10 : COM200X_CSV (DELPHI: rupture appro flex) : Analyse Plan De Test FNR","2016-04-22","En cours","2016-08-10","Retard fournisseur","2016-08-10","DR","2016-08-10","FTR"]
["MCSH-8562-L-106404","AIT - MCSI","2016-04-11T14:14:50","SWES",null,null,"VAL_BILAN","MODULE_HAB10 : COM200X_CSV (DELPHI: rupture appro flex) : Bilan de validation Fournisseur et PSA","2016-05-13","En cours","2016-08-10","Retard fournisseur","2016-08-10","DR","2016-09-08","FTR"]
["MCSH-7010-L-92220","EST - MCSI","2015-06-08T09:16:41","EACC",null,null,"VAL_ANA_PT_FNR","K9,MODULE_CPE02 : EVAV : Analyse Plan De Test FNR","2016-08-15","En cours","2016-08-12","Retard fournisseur","2016-08-15","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7362-L-96419","AIT - MCSI","2015-09-08T09:54:00","CSAC",null,null,"OF_CAL","C84_Chine : RADAR GÉN3 (C84) : Calibration pour VRS DV (D5.3b)","2016-08-18","Plan d'action",null,null,"2016-08-17","OTD","2016-08-29","FTR"]
["MCSH-3540-L-110205","AIT - MCSI","2016-07-26T11:17:42","CSAC",null,null,"DO_CESARE","P8X : RADAR GÉN3 (P8X) : Livraison BE CESARE D5.3b pour VRS DV5RC ML6C HF11-2017","2016-08-22","Plan d'action",null,null,"2016-08-17","DR","2016-08-29","FTR"]
["MCSH-7066-L-109516","AIT - MCSI","2016-07-06T09:56:44","CSAC",null,null,"OF_PIECE","G95_PH2 : CVM (G95 Ph2) : Reconduction de la CVM niv2 D5.2f","2016-08-19","Plan d'action",null,null,"2016-08-18","OTD","2016-09-28","RR"]
["MCSH-6959-L-109005","EST - MCSI","2016-06-22T10:23:28","EACC",null,null,"RT_HW","C4X,D34E,MODULE_HAB01,P24E : LUMBAFLEX : Revue Technique de Conception Préliminaire Electronique","2016-06-27","Plan d'action","2016-08-31","Blocage technique","2016-08-19","DR","2016-09-20","ACCEPTE_DEFAUT"]
["MCSH-7363-L-96380","AIT - MCSI","2015-09-07T18:43:32","CSAC",null,null,"DO_CESARE","C84_Chine : CVM (C84) : BE CVM Gen 2 VAEB SW5d pour stade VRSDV1","2016-08-19","Plan d'action",null,null,"2016-08-19","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-8378-L-101816","EST - MCSI","2016-01-18T13:39:59","ELPS",null,null,"OF_PIECE","A55_PRO : SIRENE_LIN_SSCAS,RUPTEUR_CAPOT,MUS_LIN,SIRENE_LIN_CAS : REC SIRENE avec CAS pour DFNu","2016-08-19","Plan d'action",null,null,"2016-08-19","OTD","2016-08-26","FTR"]
["MCSH-5891-L-109085","AIT - MCSI","2016-06-23T14:04:09","CSAC",null,null,"OF_CAL","B618 : CVM (B618) : (F05.2017): Officialisation Calibration CVM Gen2 VAEB (SW6)","2016-08-19","Plan d'action",null,null,"2016-08-19","OTD","2016-08-23","FTR"]
["MCSH-3533-L-109138","AIT - MCSI","2016-06-24T10:17:03","CSAC",null,null,"OF_CAL","P8X : CVM (P8) : P87 (EL2): Officialisation CAL CVM VAEB SW6 (0,9g)","2016-08-19","Plan d'action",null,null,"2016-08-19","OTD","2016-08-23","FTR"]
["MCSH-5267-L-109389","AIT - MCSI","2016-07-01T15:32:55","AURA",null,null,"OF_PIECE","MODULE_EE12 : LECTEUR_CD_EXTERNE (SANS FACADE) : Officialisation d'une pièce","2016-08-19","Plan d'action","2016-08-19",null,"2016-08-19","OTD","2016-09-15","NOT FTR"]
["MCSH-1030-L-109613","EST - MCSI","2016-07-08T15:55:21","ECPC",null,null,"OF_PIECE","C84_Export : PDPC_4LVI_RE_RA_ME_MUX,PDPC_4LVI_RE_RA_MUX : Officialisation (REC) 3D/2D FNR (DIL EE) - PDPC 4LVI RE RA MUX en DAG","2016-08-12","Plan d'action","2016-08-31","Abscence valideur ou expert","2016-08-22","DR","2016-09-23","ACCEPTE_DEFAUT"]
["MCSH-1030-L-109614","EST - MCSI","2016-07-08T16:01:37","ECPC",null,null,"OF_PIECE","C84_Export : PDPC_4LVI_RE_RA_ME_MUX,PDPC_4LVI_RE_RA_MUX : Officialisation (REC) 3D/2D FNR (DIL EE) - PDPC 4LVI RE RA MEMO MUX en DAG","2016-08-12","Plan d'action","2016-08-31","Abscence valideur ou expert","2016-08-22","DR","2016-09-23","ACCEPTE_DEFAUT"]
["MCSH-954-L-109616","EST - MCSI","2016-07-08T16:26:09","ECPC",null,null,"OF_PIECE","C84_Export : PDPC_4LVI_RE : Officialisation (REC) 3D/2D FNR (DIL EE) - PDPC 4LVI RE en DAG","2016-08-12","Plan d'action","2016-08-31","Abscence valideur ou expert","2016-08-22","DR","2016-09-23","ACCEPTE_DEFAUT"]
["MCSH-7010-L-92228","EST - MCSI","2015-06-08T09:16:41","EACC",null,null,"VAL_ANA_PT_FNR","K9,MODULE_CPE02 : EVAV : Analyse Plan De Test FNR","2016-08-22","Plan d'action","2016-08-26","Retard fournisseur","2016-08-22","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-3533-L-109229","AIT - MCSI","2016-06-28T08:59:50","CSAC",null,null,"DO_CESARE","P8X : CVM (P8) : P87 (EL2): BE SW6 pour VAEB 0.9g full breaking","2016-08-22","Plan d'action",null,null,"2016-08-22","OTD","2016-09-26","FTR"]
["MCSH-3540-L-110204","AIT - MCSI","2016-07-26T11:17:30","CSAC",null,null,"OF_CAL","P8X : RADAR GÉN3 (P8X) : CALs D5.3b pour VRS DV5RC ML6C HF11-2017","2016-08-26","Plan d'action",null,null,"2016-08-22","DR","2016-08-29","FTR"]
["MCSH-8378-L-101791","EST - MCSI","2016-01-18T13:36:05","ELPS",null,null,"OF_PIECE","A55_PRO : SIRENE_LIN_SSCAS,RUPTEUR_CAPOT,MUS_LIN,SIRENE_LIN_CAS : REC OCM MUS1 pour VRS1","2016-08-19","Plan d'action","2016-09-02","Retard fournisseur","2016-08-23","OTD","2016-09-02","FTR"]
["MCSH-7363-L-96389","AIT - MCSI","2015-09-07T18:43:32","CSAC",null,null,"OF_CAL","C84_Chine : CVM (C84) : Calibration CVM2 VAEB SW5d pour VRSDV1","2016-08-26","Plan d'action",null,null,"2016-08-23","OTD","2016-08-23","FTR"]
["MCSH-6555-L-105347","EST - MCSI","2016-03-25T02:51:53","ELAC",null,null,"OF_PIECE","P1MO : GRPE_CLIM : Officialisation sonde ACCEL (Prise d'indice sur la modificatIon HW)","2016-08-31","Plan d'action",null,null,"2016-08-23","OTD","2016-09-06","FTR"]
["MCSH-7415-L-98913","EST - MCSI","2015-11-12T14:11:59","ELAC",null,null,"DO_INC_CONCEPT","X74E : GRPE_CLIM : Incontournables partie conception","2016-09-09","Plan d'action",null,null,"2016-08-23","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-8064-L-95731","EST - MCSI","2015-08-14T13:43:01","ELAC",null,null,"RT_DV","R83E,X74E : SONDE : Revue fin DV avec le Fnr ( Validation Fonct, EE, Meca, Envir)","2016-11-30","Plan d'action","2016-08-26","Retard fournisseur","2016-08-23","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-8161-L-109073","AIT - MCSI - SMEG","2016-06-22T17:06:55","IDEV",null,null,"OF_PIECE","MODULE_EE07 : SMEG+_I_V2 : Reconduction de la variante E1 en 2ISO projet T7 Amlat pour les PRS7","2016-08-12","Plan d'action",null,null,"2016-08-24","Retard","2016-09-26","ACCEPTE_DEFAUT"]
["MCSH-5891-L-109086","AIT - MCSI","2016-06-23T14:29:19","CSAC",null,null,"DO_CESARE","B618 : CVM (B618) : EL1 (F05.2017): Création BE CVM Gen 2 VAEB (SW6)","2016-08-24","Plan d'action","2016-08-15","Retard fournisseur","2016-08-24","OTD","2016-09-26","FTR"]
["MCSH-7363-L-109250","AIT - MCSI","2016-06-28T14:45:20","CSAC",null,null,"DO_CESARE","C84_Chine : CVM (C84) : BE CVM Gen 2 niv2 D5.2d pour stade VRSDV1","2016-08-26","Plan d'action",null,null,"2016-08-24","OTD","2016-09-21","FTR"]
["MCSH-3036-L-110632","AIT - MCSI","2016-07-29T08:48:27","CSAC",null,null,"DO_CDCI_BILAN","B751_3_4_MV,B78_mi_vie,B81_Chine_Fenêtre_VS,C84_Chine,G95_PH2,K0,MODULE_EE02,P1UO,P84_Chine,P87_Chine,P8X,T9_MV,X81_Chine : RADAR GÉN3 : Synthèses d'avancement de toutes les implantation Radar / Fichier de pilotage interne et avec fournisseur.","2016-08-31","Plan d'action",null,null,"2016-08-24","DR","2016-08-29","FTR"]
["MCSH-6555-L-65061","EST - MCSI","2014-02-21T14:19:28","ELAC",null,null,"RT_DV","A88,MODULE_HAB05,P1MO : GRPE_CLIM : Revue fin de DV avec Fnr","2016-04-29","Plan d'action","2016-08-26","Blocage technique","2016-08-25","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-3127-L-109077","AIT - MCSI","2016-06-23T08:43:47","CSAC",null,null,"DO_DIVERS","B78,MODULE_EE02,T9 : ARTIV_ARCOLL : Traitement de la FAS 2433305 (T9)","2016-08-26","Plan d'action",null,null,"2016-08-25","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-8301-L-100192","AIT - MCSI","2015-12-10T14:42:45","CSAC",null,null,"RP_DFNU","F3 : CVM (F3) : Revue Technique projet pour le stade DFNu","2016-09-15","Plan d'action","2016-09-15",null,"2016-08-25","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7885-L-89457","AIT - MCSI","2015-04-22T14:24:06","CSAC",null,null,"DO_CESARE","C84_Chine : VISIO_PARK (C84 Chine) : Création de référence/Mise à jour CESARE C4","2016-08-26","Plan d'action",null,null,"2016-08-26","OTD","2016-09-05","FTR"]
["MCSH-7885-L-89466","AIT - MCSI","2015-04-22T14:24:06","CSAC",null,null,"OF_CAL","C84_Chine : VISIO_PARK (C84 Chine) : Calibration pour VRS1","2016-08-26","Plan d'action",null,null,"2016-08-26","OTD","2016-09-05","FTR"]
["MCSH-8657-L-108298","EST - MCSI","2016-05-26T13:40:14","ELAC",null,null,"VAL_ANA_PT_FNR","P8X : RCP : Analyse Plan De Test FNR","2016-08-26","Plan d'action",null,null,"2016-08-26","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7363-L-109248","AIT - MCSI","2016-06-28T14:39:39","CSAC",null,null,"OF_CAL","C84_Chine : CVM (C84) : Calibration CVM2 niv2 D5.2d-f pour VRSDV1","2016-08-26","Plan d'action",null,null,"2016-08-26","OTD","2016-09-19","FTR"]
["MCSH-6771-L-110958","AIT - MCSI","2016-08-05T09:11:53","CSAC",null,null,"OF_PIECE","_VS : AVR : Officialisation évolution sertissage du faisceau de la caméra AVR S&T sur A9x","2016-08-31","Plan d'action",null,null,"2016-08-26","DR","2016-09-27","ACCEPTE_DEFAUT"]
["MCSH-6771-L-110959","AIT - MCSI","2016-08-05T09:11:53","CSAC",null,null,"OF_PIECE","_VS : AVR : Officialisation évolution sertissage du faisceau de la caméra AVR S&T sur A94","2016-08-31","Plan d'action",null,null,"2016-08-26","DR","2016-09-27","ACCEPTE_DEFAUT"]
["MCSH-6771-L-110965","AIT - MCSI","2016-08-05T09:11:53","CSAC",null,null,"OF_PIECE","_VS : AVR : Officialisation évolution sertissage du faisceau de la caméra AVR S&T sur B9","2016-08-31","Plan d'action",null,null,"2016-08-26","DR","2016-09-27","ACCEPTE_DEFAUT"]
["MCSH-3533-L-109335","AIT - MCSI","2016-06-30T14:06:19","CSAC",null,null,"OF_CAL","P8X : CVM (P8) : P84 (F02/2017): Officialisation CAL CVM VAEB SW6 (0,9g)","2016-09-23","Plan d'action",null,null,"2016-08-26","OTD","2016-09-26","FTR"]
["MCSH-7486-L-80767","EST - MCSI","2014-12-16T17:48:52","ELPS",null,null,"DO_CESARE","X74E : SIRENE_LIN_SSCAS,RUPTEUR_CAPOT,MUS2 : Livraison BE Cesare pour VRS1 (C4)","2016-08-28","Plan d'action",null,null,"2016-08-28","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-8071-L-103450","EST - MCSI","2016-02-16T14:42:58","EACC",null,null,"DO_EDS","C84_Chine : AVE (C84_Chine,C84_Export) : Renseigner OPHELIE EDS Tool","2016-02-22","Plan d'action","2016-08-29","Retard fournisseur","2016-08-29","DR","2016-08-25","NOT FTR"]
["MCSH-8051-L-103752","AIT - MCSI","2016-02-23T17:40:44","CSAC",null,null,"OF_PIECE","R83E : CVP (R83E) : REC Caméra Longhorn (avant)","2016-07-22","Plan d'action",null,null,"2016-08-29","Retard",null,"ACCEPTE_DEFAUT"]
["MCSH-6771-L-110956","AIT - MCSI","2016-08-05T09:10:24","CSAC",null,null,"OF_PIECE","_VS : AVR : Officialisation evolution sertissage du faisceau de la caméra AVR S&T sur B81","2016-08-31","Plan d'action",null,null,"2016-08-29","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-6771-L-110962","AIT - MCSI","2016-08-05T09:11:53","CSAC",null,null,"OF_PIECE","_VS : AVR : Officialisation évolution sertissage du faisceau de la caméra AVR S&T sur T87","2016-08-31","Plan d'action",null,null,"2016-08-29","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-8246-L-106237","AIT - MCDV","2016-04-07","HDTC",null,null,"OF_PIECE","_TOUS : _TRAVAUX_CAO : Officialisation d'une pièce: Founisseur ,Accéléromètre AMVAR","2016-04-30","Plan d'action",null,null,"2016-08-30","NDR",null,"ACCEPTE_DEFAUT"]
["MCSH-7164-L-110447","AIT - MCSI","2016-07-27T06:24:50","CSAC",null,null,"DO_CESARE","P84_Chine : RADAR GÉN3 (P84_C) : Livraison BE CESARE D5.3b full braking en cours d'EL2","2016-08-30","Plan d'action",null,null,"2016-08-30","DR","2016-09-01","FTR"]
["MCSH-6771-L-110957","AIT - MCSI","2016-08-05T09:11:53","CSAC",null,null,"OF_PIECE","_VS : AVR : Officialisation évolution sertissage du faisceau de la caméra AVR S&T sur T84","2016-08-31","Plan d'action",null,null,"2016-08-30","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-6771-L-110960","AIT - MCSI","2016-08-05T09:11:53","CSAC",null,null,"OF_PIECE","_VS : AVR : Officialisation évolution sertissage du faisceau de la caméra AVR S&T sur W2","2016-08-31","Plan d'action",null,null,"2016-08-30","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-6771-L-110961","AIT - MCSI","2016-08-05T09:11:53","CSAC",null,null,"OF_PIECE","_VS : AVR : Officialisation évolution sertissage du faisceau de la caméra AVR S&T sur E3","2016-08-31","Plan d'action",null,null,"2016-08-30","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-6771-L-110963","AIT - MCSI","2016-08-05T09:11:53","CSAC",null,null,"OF_PIECE","_VS : AVR : Officialisation évolution sertissage du faisceau de la caméra AVR S&T sur A58","2016-08-31","Plan d'action",null,null,"2016-08-30","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-6771-L-110964","AIT - MCSI","2016-08-05T09:11:53","CSAC",null,null,"OF_PIECE","_VS : AVR : Officialisation évolution sertissage du faisceau de la caméra AVR S&T sur X7","2016-08-31","Plan d'action",null,null,"2016-08-30","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-6771-L-110966","AIT - MCSI","2016-08-05T09:11:53","CSAC",null,null,"OF_PIECE","_VS : AVR : Officialisation évolution sertissage du faisceau de la caméra AVR S&T sur A5x","2016-08-31","Plan d'action",null,null,"2016-08-30","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-6771-L-110967","AIT - MCSI","2016-08-05T09:11:53","CSAC",null,null,"OF_PIECE","_VS : AVR : Officialisation évolution sertissage du faisceau de la caméra AVR S&T sur W2","2016-08-31","Plan d'action",null,null,"2016-08-30","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-6771-L-110968","AIT - MCSI","2016-08-05T09:41:18","CSAC",null,null,"DO_CESARE","_VS : AVR : Création de référence/Mise à jour CESARE B81","2016-08-31","Plan d'action",null,null,"2016-08-30","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-6771-L-110969","AIT - MCSI","2016-08-05T09:41:42","CSAC",null,null,"DO_CESARE","_VS : AVR : Création de référence/Mise à jour CESARE T84","2016-08-31","Plan d'action",null,null,"2016-08-30","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-6771-L-110970","AIT - MCSI","2016-08-05T09:41:42","CSAC",null,null,"DO_CESARE","_VS : AVR : Création de référence/Mise à jour CESARE A9x","2016-08-31","Plan d'action",null,null,"2016-08-30","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-6771-L-110971","AIT - MCSI","2016-08-05T09:41:42","CSAC",null,null,"DO_CESARE","_VS : AVR : Création de référence/Mise à jour CESARE A94","2016-08-31","Plan d'action",null,null,"2016-08-30","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-6771-L-110972","AIT - MCSI","2016-08-05T09:41:42","CSAC",null,null,"DO_CESARE","_VS : AVR : Création de référence/Mise à jour CESARE W22/W24","2016-08-31","Plan d'action",null,null,"2016-08-30","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-6771-L-110973","AIT - MCSI","2016-08-05T09:41:42","CSAC",null,null,"DO_CESARE","_VS : AVR : Création de référence/Mise à jour CESARE E3","2016-08-31","Plan d'action",null,null,"2016-08-30","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-6771-L-110974","AIT - MCSI","2016-08-05T09:41:42","CSAC",null,null,"DO_CESARE","_VS : AVR : Création de référence/Mise à jour CESARE T87","2016-08-31","Plan d'action",null,null,"2016-08-30","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-6771-L-110975","AIT - MCSI","2016-08-05T09:41:42","CSAC",null,null,"DO_CESARE","_VS : AVR : Création de référence/Mise à jour CESARE A58","2016-08-31","Plan d'action",null,null,"2016-08-30","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-6771-L-110976","AIT - MCSI","2016-08-05T09:41:42","CSAC",null,null,"DO_CESARE","_VS : AVR : Création de référence/Mise à jour CESARE X7","2016-08-31","Plan d'action",null,null,"2016-08-30","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-6771-L-110977","AIT - MCSI","2016-08-05T09:41:42","CSAC",null,null,"DO_CESARE","_VS : AVR : Création de référence/Mise à jour CESARE B9","2016-08-31","Plan d'action",null,null,"2016-08-30","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-6771-L-110978","AIT - MCSI","2016-08-05T09:41:42","CSAC",null,null,"DO_CESARE","_VS : AVR : Création de référence/Mise à jour CESARE A51/A55/A56","2016-08-31","Plan d'action",null,null,"2016-08-30","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-6771-L-110979","AIT - MCSI","2016-08-05T09:41:42","CSAC",null,null,"DO_CESARE","_VS : AVR : Création de référence/Mise à jour CESARE W23","2016-08-31","Plan d'action",null,null,"2016-08-30","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-6771-L-110997","AIT - MCSI","2016-08-05T05:13:06","CSAC",null,null,"OF_PIECE","_VS : AVR : Officialisation évolution sertissage du faisceau de la caméra AVR S&T sur T9","2016-08-31","Plan d'action",null,null,"2016-08-30","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-6771-L-110998","AIT - MCSI","2016-08-05T05:13:57","CSAC",null,null,"DO_CESARE","_VS : AVR : Création de référence/Mise à jour CESARE T9","2016-08-31","Plan d'action",null,null,"2016-08-30","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-6771-L-111496","AIT - MCSI","2016-08-30T11:12:54","CSAC",null,null,"OF_PIECE","_VS : AVR : Officialisation évolution sertissage du faisceau de la caméra AVR S&T sur T87","2016-08-31","Plan d'action",null,null,"2016-08-30","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-6771-L-111497","AIT - MCSI","2016-08-30T11:12:54","CSAC",null,null,"OF_PIECE","_VS : AVR : Officialisation évolution sertissage du faisceau de la caméra AVR S&T sur B9","2016-09-01","Plan d'action",null,null,"2016-08-30","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-6771-L-111498","AIT - MCSI","2016-08-30T11:12:54","CSAC",null,null,"OF_PIECE","_VS : AVR : Officialisation évolution sertissage du faisceau de la caméra AVR S&T sur B81","2016-09-02","Plan d'action",null,null,"2016-08-30","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-6771-L-111499","AIT - MCSI","2016-08-30T11:12:54","CSAC",null,null,"OF_PIECE","_VS : AVR : Officialisation évolution sertissage du faisceau de la caméra AVR S&T sur A94","2016-09-03","Plan d'action",null,null,"2016-08-30","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-7590-L-82922","AIT - MCSI","2015-01-21T09:37:01","SWES",null,null,"DO_SUIVI_PROCESS","MODULE_HAB10,A5X_F_02_16,T9_MV,_QUALITE : CSV (VS_A5x_T9x_noir HZD et blanc sonic) : Mise à jour du document de suivi produit/process","2016-03-30","Plan d'action","2016-08-31","Retard fournisseur","2016-08-31","OTD","2016-09-08","FTR"]
["MCSH-7164-L-110446","AIT - MCSI","2016-07-27T06:24:35","CSAC",null,null,"OF_CAL","P84_Chine : RADAR GÉN3 (P84_C) : Calibration D5.3b full braking en cours d'EL2","2016-08-30","Plan d'action","2016-09-02",null,"2016-08-31","DR","2016-09-01","FTR"]
["MCSH-1658-L-110466","AIT - MCSI","2016-07-28T13:08:51","SWES",null,null,"VAL_ANA_INDIC","MODULE_HAB10,_QUALITE,A9,A94,A94_Chine,A97,Ai94M,Ai9M,T9,T9_Chine,  : VCI DELPHI (A9-T9-B7x-B8-E3) : Vérifier les engagements qualité du FNR et prioriser en fonction des têtes de pareto. Objectif en début d'année, bilan à mi et fin d'année.","2016-09-01","Plan d'action",null,null,"2016-09-01","DR","2016-09-08","FTR"]
["MCSH-1727-L-110479","AIT - MCSI","2016-07-28T13:09:41","SWES",null,null,"VAL_ANA_INDIC","MODULE_HAB10,_QUALITE,G95,K0,M44_Chine,T7xA,T9_Chine,W2_VS : VCI MARQUARDT (W2-K0) : Vérifier les engagements qualité du FNR et prioriser en fonction des têtes de pareto. Objectif en début d'année, bilan à mi et fin d'année.","2016-09-01","Plan d'action",null,null,"2016-09-01","DR","2016-09-08","FTR"]
["MCSH-7684-L-84888","AIT - MCSI","2015-02-19T13:53:07","CSAC",null,null,"OF_CAL","X74E : VISIO_PARK (X74E) : Calibration pour VRS1","2016-09-02","Plan d'action",null,null,"2016-09-01","OTD","2016-09-05","FTR"]
["MCSH-8050-L-95082","AIT - MCSI","2015-07-27T08:59:37","CSAC",null,null,"DO_CESARE","X74E : CVP (X74E) : Création de référence/Mise à jour CESARE C4","2016-09-02","Plan d'action",null,null,"2016-09-01","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7684-L-84876","AIT - MCSI","2015-02-19T13:53:07","CSAC",null,null,"DO_CESARE","X74E : VISIO_PARK (X74E) : Création de référence/Mise à jour CESARE C4","2016-10-10","Plan d'action",null,null,"2016-09-01","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-3036-L-110518","AIT - MCSI","2016-07-29T08:42:47","CSAC",null,null,"SYN_ALTIS ","B751_3_4_MV,B78_mi_vie,B81_Chine_Fenêtre_VS,C84_Chine,G95_PH2,K0,MODULE_EE02,P1UO,P84_Chine,P87_Chine,P8X,T9_MV,X81_Chine : RADAR GÉN3 : Gestion Hebdomadaire Altis\r\n","2016-09-02","Plan d'action",null,null,"2016-09-02","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-7888-L-89739","AIT - MCSI","2015-04-23T07:52:12","CSAC",null,null,"DO_CESARE","X7RR : VISIO_PARK (X7RR) : Création de référence/Mise à jour CESARE C5","2016-09-09","Plan d'action","2016-06-28","Retard fournisseur","2016-09-02","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7888-L-89740","AIT - MCSI","2015-04-23T07:52:12","CSAC",null,null,"OF_CAL","X7RR : VISIO_PARK (X7RR) : Calibration pour VRS2","2016-09-09","Plan d'action","2016-07-10",null,"2016-09-02","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7831-L-105734","EST - MCSI","2016-04-01T10:51:11","EACC",null,null,"RT_CDCI","K9 : ANTENNE_BACKUP (REC K9) : Revue technique de CDCI : implantation antenne Backup","2016-04-25","Plan d'action","2016-09-05","RAL en retard","2016-09-05","DR","2016-08-25","NOT FTR"]
["MCSH-8071-L-104806","EST - MCSI","2016-03-17T09:26:35","EACC",null,null,"RT_CDCI","C84_Export : AVE (C84_Chine,C84_Export) : Revue technique de CDCI","2016-04-30","Plan d'action","2016-09-05","Manque donnée d'entrée","2016-09-05","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-8051-L-109289","AIT - MCSI","2016-06-29T14:20:00","CSAC",null,null,"OF_PIECE","R83E : CVP (R83E) : REC camera aide visuelle panoramique","2016-07-22","Plan d'action","2016-09-09","Livrable affecté en retard","2016-09-05","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-5876-L-109923","EST - MCSI","2016-07-21T10:33:27","ELAC",null,null,"DO_DDM","P84_Chine : GRPE_CLIM : Demande De Modification : Passage à sonde évapo EPCOS","2016-08-31","Plan d'action","2016-09-05","Retard fournisseur","2016-09-05","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-7400-L-89717","EST - MCSI","2015-04-22T16:58:35","ELPS",null,null,"VAL_ANA_PT_FNR","X74E : FEU_AV : Analyse Plan De Test FNR","2016-09-10","Plan d'action",null,null,"2016-09-05","OTD","2016-09-14","FTR"]
["MCSH-7479-L-109145","AIT - MCSI","2016-06-24T12:41:16","CSAC",null,null,"OF_PIECE","B751_3_4_MV : CVM (B753_4  MV) : B754MV: Reconduction de la CVM niv2 D5.3 pour VRS2","2016-09-16","Plan d'action",null,null,"2016-09-05","OTD","2016-09-26","FTR"]
["MCSH-3533-L-109231","AIT - MCSI","2016-06-28T09:27:09","CSAC",null,null,"OF_PIECE","P8X : CVM (P8) : P8x (F05/2017); Reconduction globale P8x € + P8x Chine  CVM niv1 & 2 D5.3","2016-09-23","Plan d'action",null,null,"2016-09-05","OTD","2016-10-14","NOT FTR"]
["MCSH-7989-L-109189","AIT - MCSI","2016-06-27T09:48:19","CSAC",null,null,"OF_PIECE","P87_Chine : CVM (P87C) : EL1: Reconduction CVM niv1 & 2 D5.3 ","2016-09-30","Plan d'action",null,null,"2016-09-05","OTD","2016-10-14","NOT FTR"]
["MCSH-7882-L-89326","EST - MCSI","2015-04-21T14:43:20","ELPS",null,null,"OF_PIECE","C84_Chine : SIRENE_LIN_SSCAS,RUPTEUR_CAPOT,MUS2 (Réimport Europe) : REC SIRENE avec implantation définitive","2016-06-27","Plan d'action","2016-09-06","Abscence valideur ou expert","2016-09-06","OTD","2016-09-06","FTR"]
["MCSH-7882-L-110217","EST - MCSI","2016-07-26T14:56:14","ELPS",null,null,"OF_PIECE","C84_Chine : SIRENE_LIN_SSCAS,RUPTEUR_CAPOT,MUS2 (Réimport Europe) : Officialisation d'une pièce FIXATIONS SIRENE","2016-09-15","Plan d'action",null,null,"2016-09-06","OTD","2016-09-14","FTR"]
["MCSH-6604-L-76703","AIT - MCSI","2014-10-09T14:26:25","CSAC",null,null,"DO_CESARE","P1UO : RADAR GÉN3 (P1UO) : Livraison BEs D5.3b en cours de VRS UT ","2016-09-16","Plan d'action",null,null,"2016-09-06","OTD","2016-09-07","FTR"]
["MCSH-8071-L-103448","EST - MCSI","2016-02-16T02:31:01","EACC",null,null,"OF_PIECE","C84_Export : AVE (C84_Chine,C84_Export) : Officialisation d'une pièce REC AVE C84€ pour DàD et DàG","2016-07-15","Plan d'action","2016-09-07","Blocage technique","2016-09-07","OTD","2016-09-21","FTR"]
["MCSH-8562-L-106400","AIT - MCSI","2016-04-11T14:14:50","SWES",null,null,"DO_PEPP","MODULE_HAB10 : COM200X_CSV (DELPHI: rupture appro flex) : A3 PEPP à compléter via Altis TE","2016-09-07","Plan d'action","2016-09-07","Retard fournisseur","2016-09-07","OTD",null,"FTR"]
["MCSH-7660-L-84176","AIT - MCSI","2015-02-13T10:42:54","CSAC",null,null,"RT_CDCI","T73_Russie_VS_MV : CVP (T73MV Russie) : Revue technique de CDCI","2016-05-16","Plan d'action","2016-09-08","Manque donnée d'entrée","2016-09-08","OTD",null,"FTR"]
["MCSH-4124-L-82317","AIT - MCSI","2015-01-14T13:07:17","CSAC",null,null,"OF_DOTE","X74E : CVM (X74E) : Pour Stade OCM VRS1 (C4)","2016-09-01","Plan d'action","2016-09-08","Evolution donnée d'entrée","2016-09-08","OTD","2016-09-19","FTR"]
["MCSH-8051-L-95105","AIT - MCSI","2015-07-27T09:10:39","CSAC",null,null,"DO_CESARE","R83E : CVP (R83E) : Création de référence/Mise à jour CESARE C4","2016-09-12","Plan d'action","2016-06-28","Retard fournisseur","2016-09-08","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7479-L-111189","AIT - MCSI","2016-08-18T11:24:26","CSAC",null,null,"DO_CESARE","B751_3_4_MV : CVM (B753_4  MV) : B754: BE CVM niv2 D5.2f pour VRS1","2016-09-16","Plan d'action",null,null,"2016-09-08","DR","2016-09-26","FTR"]
["MCSH-7479-L-111191","AIT - MCSI","2016-08-18T11:25:49","CSAC",null,null,"DO_CESARE","B751_3_4_MV : CVM (B753_4  MV) : B751-3: BE CVM niv2 D5.2f pour VRS1","2016-09-16","Plan d'action",null,null,"2016-09-08","DR","2016-09-26","FTR"]
["MCSH-7590-L-82910","AIT - MCSI","2015-01-21T09:37:01","SWES",null,null,"DO_PEPP","MODULE_HAB10,A5X_F_02_16,T9_MV,_QUALITE : CSV (VS_A5x_T9x_noir HZD et blanc sonic) : A3 PEPP à compléter","2015-07-31","Plan d'action","2016-09-09","Décalage projet","2016-09-09","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-8310-L-100012","EST - MCSI","2015-12-08T19:32:34","EACC",null,null,"OF_PIECE","C84_Export : JDV (Rec C84E) : Rec Antivol Méca + vis de fixation","2016-09-05","Plan d'action","2016-09-09","Manque donnée d'entrée","2016-09-09","OTD","2016-09-15","FTR"]
["MCSH-7987-L-105804","EST - MCSI","2016-04-01T11:31:03","ELPS",null,null,"DO_FC_VRS","D34E : FEU_AV : Fiches composants pour SDP VRS","2016-09-09","Plan d'action",null,null,"2016-09-09","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7683-L-84846","AIT - MCSI","2015-02-19T13:43:26","CSAC",null,null,"OF_CAL","R83E : VISIO_PARK (R83E) : Calibration pour VRS2","2016-09-12","Plan d'action","2016-09-30","Blocage technique","2016-09-09","OTD",null,"FTR"]
["MCSH-6959-L-112155","EST - MCSI","2016-09-16T16:27:43","EACC",null,null,"VAL_RECETTE","C4X,D34E,MODULE_HAB01,P24E : LUMBAFLEX : Recette B1",null,"Plan d'action",null,null,"2016-09-09","NDR",null,"ACCEPTE_DEFAUT"]
["MCSH-5562-L-64968","EST - MCSI","2014-02-21T13:46:22","ELAC",null,null,"DO_INC_VALID","B618,MODULE_HAB05 : GRPE_CLIM : Incontournable après validation","2016-09-12","Plan d'action",null,null,"2016-09-12","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7683-L-84841","AIT - MCSI","2015-02-19T13:43:26","CSAC",null,null,"DO_CESARE","R83E : VISIO_PARK (R83E) : Création de référence/Mise à jour CESARE C4","2016-09-12","Plan d'action","2016-06-28","Retard fournisseur","2016-09-12","OTD",null,"FTR"]
["MCSH-7415-L-98929","EST - MCSI","2015-11-12T14:11:59","ELAC",null,null,"RT_DV","X74E : GRPE_CLIM : Revue fin DV avec le Fnr ( Validation Fonct, EE, Meca, Envir)","2016-09-12","Plan d'action",null,null,"2016-09-12","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7486-L-111777","EST - MCSI","2016-09-05T13:48:12","ELPS",null,null,"OF_PIECE","X74E : SIRENE_LIN_SSCAS,RUPTEUR_CAPOT,MUS2 : Officialisation d'une pièce. REC agrafe Rupteur","2016-09-23","Plan d'action",null,null,"2016-09-12","DR","2016-09-14","FTR"]
["MCSH-8557-L-109452","EST - MCSI","2016-07-04T16:43:59","HD2C",null,null,"VAL_RECETTE","MODULE_EE09 : MATTP (DMTLess) : Recette & validations Sw1.6","2016-09-16","Plan d'action",null,null,"2016-09-13","OTD","2016-10-14","ACCEPTE_DEFAUT"]
["MCSH-6604-L-76704","AIT - MCSI","2014-10-09T14:26:25","CSAC",null,null,"OF_CAL","P1UO : RADAR GÉN3 (P1UO) : CAL D5.3b en cours de VRS UT","2016-09-16","Plan d'action",null,null,"2016-09-14","OTD",null,"FTR"]
["MCSH-7154-L-76348","AIT - MCSI","2014-10-06T13:01:03","CSAC",null,null,"OF_CAL","P1UO : CVM (P1UO) : Calibration CVM Gen 2 Niveau 1 D5.3 pour VRSUT","2016-10-14","Plan d'action",null,null,"2016-09-14","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7154-L-98461","AIT - MCSI","2015-10-26T09:42:18","CSAC",null,null,"OF_CAL","P1UO : CVM (P1UO) : Calibration CVM Gen 2 Niveau 2 D5.3 pour VRSUT","2016-10-14","Plan d'action",null,null,"2016-09-14","OTD","2016-09-26","FTR"]
["MCSH-7154-L-106527","AIT - MCSI","2016-04-15T10:12:40","CSAC",null,null,"OF_CAL","P1UO : CVM (P1UO) : Calibration CVM Gen 2 Niveau 3 (VAEB - SW6)  pour VRSUT","2016-10-14","Plan d'action",null,null,"2016-09-14","OTD","2016-09-26","FTR"]
["MCSH-8378-L-101787","EST - MCSI","2016-01-18T13:36:05","ELPS",null,null,"DO_CESARE","A55_PRO : SIRENE_LIN_SSCAS,RUPTEUR_CAPOT,MUS_LIN,SIRENE_LIN_CAS : Livraison BE Cesare pour TI (B2)","2016-11-17","Plan d'action",null,null,"2016-09-14","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-8378-L-101818","EST - MCSI","2016-01-18T13:39:59","ELPS",null,null,"DO_BE_CESARE","A55_PRO : SIRENE_LIN_SSCAS,RUPTEUR_CAPOT,MUS_LIN,SIRENE_LIN_CAS : Livraison BE Cesare pour TI","2016-11-17","Plan d'action",null,null,"2016-09-14","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7479-L-92329","AIT - MCSI","2015-06-08T10:45:43","CSAC",null,null,"OF_CAL","B751_3_4_MV : CVM (B753_4  MV) : B754: Offi CAL CVM niv2 D5.3 pour VRS2","2016-09-16","Plan d'action",null,null,"2016-09-16","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7479-L-98480","AIT - MCSI","2015-10-26T11:28:36","CSAC",null,null,"OF_CAL","B751_3_4_MV : CVM (B753_4  MV) : B751-3: Offi CAL CVM niv2 D5.3 pour VRS2","2016-09-16","Plan d'action",null,null,"2016-09-16","OTD","2016-09-26","FTR"]
["MCSH-7479-L-109144","AIT - MCSI","2016-06-24T12:40:54","CSAC",null,null,"OF_PIECE","B751_3_4_MV : CVM (B753_4  MV) : B751-3MV: Reconduction de la CVM niv2 D5.3 pour VRS2","2016-09-16","Plan d'action",null,null,"2016-09-16","OTD","2016-09-26","FTR"]
["MCSH-5234-L-111466","AIT - MCSI","2016-08-26T12:04:25","AURA",null,null,"OF_PIECE","B78 : LECTEUR_CD_EXTERNE (AVEC FACADE) : Officialisation d'une pièce","2016-09-23","Plan d'action",null,null,"2016-09-16","DR","2016-10-17","ACCEPTE_DEFAUT"]
["MCSH-954-L-112099","EST - MCSI","2016-09-14T16:38:28","ECPC",null,null,"OF_PIECE","C84_Export : PDPC_4LVI_RE : Officialisation (REC) 3D/2D FNR (DIL EE) - PDPC 4LVI RE en DAD","2016-08-01","Plan d'action","2016-09-30",null,"2016-09-19","DR","2016-10-20","ACCEPTE_DEFAUT"]
["MCSH-1030-L-112100","EST - MCSI","2016-09-14T16:42:23","ECPC",null,null,"OF_PIECE","C84_Export : PDPC_4LVI_RE_RA_ME_MUX,PDPC_4LVI_RE_RA_MUX : Officialisation (REC) 3D/2D FNR (DIL EE) - PDPC 4LVI RE RA MUX en DAD","2016-08-01","Plan d'action","2016-09-30",null,"2016-09-19","DR","2016-10-20","ACCEPTE_DEFAUT"]
["MCSH-1030-L-112101","EST - MCSI","2016-09-14T16:42:23","ECPC",null,null,"OF_PIECE","C84_Export : PDPC_4LVI_RE_RA_ME_MUX,PDPC_4LVI_RE_RA_MUX : Officialisation (REC) 3D/2D FNR (DIL EE) - PDPC 4LVI RE RA MEMO MUX en DAD","2016-08-01","Plan d'action","2016-09-30",null,"2016-09-19","DR","2016-10-20","ACCEPTE_DEFAUT"]
["MCSH-4124-L-82328","AIT - MCSI","2015-01-14T13:07:17","CSAC",null,null,"OF_CAL","X74E : CVM (X74E) : Calibration pour VRS1","2016-09-02","Plan d'action","2016-09-19","Retard","2016-09-19","OTD","2016-09-19","FTR"]
["MCSH-3533-L-112562","AIT - MCSI","2016-10-04T11:32:00","CSAC",null,null,"DO_CESARE","P8X : CVM (P8) : P84: Mise à jour BE CVM niv1 & 2 D5.2f (nouveau DOTE)","2016-09-19","Plan d'action",null,null,"2016-09-19","DR","2016-10-17","FTR"]
["MCSH-3533-L-112573","AIT - MCSI","2016-10-04T01:01:28","CSAC",null,null,"DO_CESARE","P8X : CVM (P8) : P84 (F02/2017): Mise à jour BE CVM VAEB SW6b (nouveau DOTE et CAL)","2016-09-19","Plan d'action",null,null,"2016-09-19","DR","2016-10-17","FTR"]
["MCSH-8657-L-108297","EST - MCSI","2016-05-26T13:40:14","ELAC",null,null,"VAL_ANA_PV_FNR","P8X : RCP : Analyse du planning de validation fournisseur","2016-09-30","Plan d'action",null,null,"2016-09-19","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-2984-L-112102","EST - MCSI","2016-09-14T16:48:29","ECPC",null,null,"OF_PIECE","C84_Export : PUSH_LVI_AR,PUSH_LVI_AV : Officialisation (REC) 3D/2D Fonctionnel - Push LVI BITRON AVG","2016-08-01","Plan d'action","2016-09-30",null,"2016-09-20","DR","2016-10-21","ACCEPTE_DEFAUT"]
["MCSH-2984-L-112103","EST - MCSI","2016-09-14T16:48:29","ECPC",null,null,"OF_PIECE","C84_Export : PUSH_LVI_AR,PUSH_LVI_AV : Officialisation (REC) 3D/2D Fonctionnel - Push LVI BITRON AVD","2016-08-01","Plan d'action","2016-09-30",null,"2016-09-20","DR","2016-10-21","ACCEPTE_DEFAUT"]
["MCSH-8419-L-109170","EST - MCSI","2016-06-24T16:41:55","ECPC",null,null,"OF_PIECE","MODULE_EE05 : PUSH_LVE_AV,PUSH_LVI_AV : Création et Officialisation MDT 3D/2D FNR (DIL MECA) et rattachement au 3D fonctionnel","2016-09-02","Plan d'action","2016-09-30","Blocage technique","2016-09-20","OTD","2016-09-14","FTR"]
["MCSH-7400-L-89705","EST - MCSI","2015-04-22T16:58:35","ELPS",null,null,"VAL_ANA_RAPP_ESSAIS","X74E : FEU_AV : Analyse rapports d'essais FNR Pre DV\r\n","2016-09-09","Plan d'action","2016-09-21","Retard fournisseur","2016-09-20","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-6027-L-112106","EST - MCSI","2016-09-14T17:01:17","ECPC",null,null,"OF_PIECE","C84_Export : PUSH_TO_VELUM : Officialisation (REC) 3D/2D Fonctionnel - Push TO/VELUM","2016-09-09","Plan d'action","2016-09-30",null,"2016-09-20","DR","2016-10-21","ACCEPTE_DEFAUT"]
["MCSH-6973-L-108367","EST - MCSI","2016-05-31T15:41:02","ELAC",null,null,"OF_PIECE","R83E : GRPE_CLIM : Officialisation faisceau HVAC avec et sans AQS","2016-09-23","Plan d'action","2016-09-23",null,"2016-09-20","OTD","2016-09-22","FTR"]
["MCSH-5893-L-111170","AIT - MCSI","2016-08-17T03:29:32","CSAC",null,null,"DO_CESARE","P1MO : CVM (A88,P1MO) : P1MO (DàD/DàG): BE CVM Niv 3 VAEB SW6 pour stade MVBns","2016-09-30","Annulé",null,null,"2016-09-20","OTD","2016-09-26","FTR"]
["MCSH-5893-L-111172","AIT - MCSI","2016-08-17T03:31:11","CSAC",null,null,"DO_CESARE","A88 : CVM (A88,P1MO) : A88 (DàD/DàG): BE CVM Niv 3 VAEB SW6 pour stade PPV3","2016-09-30","Annulé",null,null,"2016-09-20","OTD","2016-09-26","FTR"]
["MCSH-3540-L-111366","AIT - MCSI","2016-08-25T15:07:20","CSAC",null,null,"OF_CAL","P8X : RADAR GÉN3 (P8X) : Officialisation calibration D5.3b switch off FCW on radar only stationary targets (not confirmed by camera and not seen moving in the past) ","2016-09-16","Annulé","2016-09-23",null,"2016-09-21","DR",null,"FTR"]
["MCSH-6611-L-111774","EST - MCSI","2016-09-05T13:36:15","ELPS",null,null,"OF_PIECE","P1MO : RUPTEUR_CAPOT,SIRENE_LIN_SSCAS,MUS2 (Rec. P1MO) : Officialisation d'une pièce\r\nMUS2 P1MO 3 capteurs CAS","2016-09-16","Annulé","2016-09-21",null,"2016-09-21","DR","2016-09-21","FTR"]
["MCSH-6608-L-111775","EST - MCSI","2016-09-05T13:39:27","ELPS",null,null,"OF_PIECE","A88 : SIRENE_LIN_SSCAS,MUS2,RUPTEUR_CAPOT : Officialisation d'une pièce P1MT 3 capteurs CAS","2016-09-16","Annulé","2016-09-21",null,"2016-09-21","DR","2016-09-21","FTR"]
["MCSH-7164-L-111487","AIT - MCSI","2016-08-29T04:52:47","CSAC",null,null,"DO_CESARE","P84_Chine : RADAR GÉN3 (P84_C) : Livraison BEs CESARE D5.3b (modif FCW) MDL","2016-09-21","Annulé",null,null,"2016-09-21","DR",null,"FTR"]
["MCSH-3533-L-112564","AIT - MCSI","2016-10-04T11:35:40","CSAC",null,null,"DO_CESARE","P8X : CVM (P8) : P87: Mise à jour BE CVM niv1 & 2 D5.2f (nouveau DOTE)","2016-09-21","Annulé",null,null,"2016-09-21","DR","2016-10-17","FTR"]
["MCSH-3533-L-112574","AIT - MCSI","2016-10-04T01:08:58","CSAC",null,null,"DO_CESARE","P8X : CVM (P8) : P87: Mise à jour BE CVM VAEB SW6b (nouveau DOTE et CAL)","2016-09-21","Annulé",null,null,"2016-09-21","DR","2016-10-17","FTR"]
["MCSH-6867-L-89663","EST - MCSI","2015-04-22T16:39:50","ELPS",null,null,"RT_HW","K9 : PROJ : Bilan LayOut - Verif CCA et EMC","2016-09-29","Annulé","2016-06-30","Retard fournisseur","2016-09-21","OTD",null,"FTR"]
["MCSH-7358-L-106693","EST - MCSI","2016-04-18T09:50:41","ELPS",null,null,"VAL_ANA_PT_FNR","D34E : FEUX_AR : Analyse Plan De Test FNR","2016-09-29","Annulé","2016-09-21","Retard fournisseur","2016-09-21","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-8657-L-108304","EST - MCSI","2016-05-26T13:42:41","ELAC",null,null,"OF_PIECE","P8X : RCP : Officialisation d'une pièce","2016-09-30","Annulé",null,null,"2016-09-21","OTD","2016-09-21","FTR"]
["MCSH-3533-L-111780","AIT - MCSI","2016-09-05T14:23:21","CSAC",null,null,"OF_DOTE","P8X : CVM (P8) : DOTE P84 pour modification type AFIL","2016-09-30","Annulé",null,null,"2016-09-21","DR","2016-09-26","FTR"]
["MCSH-3533-L-111781","AIT - MCSI","2016-09-05T02:24:58","CSAC",null,null,"OF_DOTE","P8X : CVM (P8) : DOTE P87 pour modification type AFIL","2016-09-30","Annulé",null,null,"2016-09-21","DR","2016-09-26","FTR"]
["MCSH-8821-L-112131","AIT - MCSI","2016-09-16T13:26:08","AURA",null,null,"OF_PIECE","A88 : LECTEUR_CD_EXTERNE : Officialisation d'une pièce",null,"Annulé",null,null,"2016-09-21","NDR",null,"ACCEPTE_DEFAUT"]
["MCSH-6641-L-80526","EST - MCSI","2014-12-15T22:43:47","ELPS",null,null,"VAL_ANA_PT_FNR","P1UO : FEUX_AR : Analyse Plan De Test PV FNR","2016-09-22","Annulé",null,null,"2016-09-22","OTD",null,"FTR"]
["MCSH-3540-L-111482","AIT - MCSI","2016-08-29T04:42:12","CSAC",null,null,"DO_CESARE","P8X : RADAR GÉN3 (P8X) : Livraison BEs CESARE D5.3b (switch off FCW...) pour F10-2016","2016-09-22","Annulé","2016-09-22","Retard fournisseur","2016-09-22","DR",null,"FTR"]
["MCSH-3540-L-111483","AIT - MCSI","2016-08-29T04:43:51","CSAC",null,null,"DO_CESARE","P8X : RADAR GÉN3 (P8X) : Livraison BEs CESARE D5.4 (switch off FCW...) pour F10-2016","2016-09-22","Annulé",null,null,"2016-09-22","DR",null,"FTR"]
["MCSH-3540-L-111367","AIT - MCSI","2016-08-25T03:10:27","CSAC",null,null,"OF_CAL","P8X : RADAR GÉN3 (P8X) : Officialisation calibration D5.4 switch off FCW on radar only stationary targets (not confirmed by camera and not seen moving in the past) ","2016-09-23","Annulé",null,null,"2016-09-22","DR",null,"FTR"]
["MCSH-7164-L-111486","AIT - MCSI","2016-08-29T04:51:49","CSAC",null,null,"OF_CAL","P84_Chine : RADAR GÉN3 (P84_C) : CALs D5.3b (modif FCW...) pour MDL","2016-09-23","Annulé",null,null,"2016-09-22","DR",null,"FTR"]
["MCSH-7467-L-82081","EST - MCSI","2015-01-09T15:55:51","ELPS",null,null,"OF_PIECE","R83E : SIRENE_LIN_SSCAS,RUPTEUR_CAPOT,MUS2 : OFFI OCM Plan FNR MUS 2","2016-07-29","Annulé","2016-09-30","Evolution donnée d'entrée","2016-09-23","OTD",null,"FTR"]
["MCSH-6641-L-80518","EST - MCSI","2014-12-15T22:43:47","ELPS",null,null,"VAL_ANA_RAPP_ESSAIS","P1UO : FEUX_AR : Analyse CR Essais DV","2016-08-31","Annulé","2016-09-27","Retard fournisseur","2016-09-23","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-6437-L-65003","EST - MCSI","2014-02-21T14:00:35","ELAC",null,null,"DO_INC_VALID","B618 : TDC_CH_RF : Incontournable après validation","2016-09-12","Annulé","2016-09-30","Evolution donnée d'entrée","2016-09-23","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7479-L-92328","AIT - MCSI","2015-06-08T10:45:43","CSAC",null,null,"DO_CESARE","B751_3_4_MV : CVM (B753_4  MV) : B754: BE CVM niv2 D5.3 pour VRS2","2016-09-23","Annulé",null,null,"2016-09-23","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7479-L-98475","AIT - MCSI","2015-10-26T10:46:42","CSAC",null,null,"DO_CESARE","B751_3_4_MV : CVM (B753_4  MV) : B751-3: BE CVM niv2 D5.3 pour VRS2","2016-09-23","Annulé",null,null,"2016-09-23","OTD","2016-09-26","FTR"]
["MCSH-3533-L-109235","AIT - MCSI","2016-06-28T10:59:19","CSAC",null,null,"DO_CESARE","P8X : CVM (P8) : P84 (F05/2017): BE D5.3 pour CVM niv1 & 2","2016-09-23","Annulé",null,null,"2016-09-23","OTD","2016-09-26","FTR"]
["MCSH-5234-L-111465","AIT - MCSI","2016-08-26","AURA",null,null,"OF_PIECE","A9 : LECTEUR_CD_EXTERNE (AVEC FACADE) : Officialisation d'une pièce: REC du lecteur CD DMTless sans façade","2016-09-23","Annulé",null,null,"2016-09-23","DR",null,"FTR"]
["MCSH-5893-L-109418","AIT - MCSI","2016-07-04T10:31:43","CSAC",null,null,"OF_CAL","P1MO : CVM (A88,P1MO) : Calibration CVM Gen 2 Niveau 1 (soft D5.3) pour stade MVBns P1MO version DàD (RHD)","2016-09-23","Annulé",null,null,"2016-09-23","OTD",null,"FTR"]
["MCSH-5893-L-109428","AIT - MCSI","2016-07-04T11:22:46","CSAC",null,null,"OF_CAL","A88 : CVM (A88,P1MO) : Calibration CVM Gen 2 Niveau 1 (soft D5.3) pour stade PPV3 A88 version DàD (RHD)","2016-09-23","Annulé","2016-09-30",null,"2016-09-23","OTD",null,"FTR"]
["MCSH-7034-L-111017","AIT - MCSI","2016-08-08T15:03:15","CSAC",null,null,"OF_PIECE","B78_mi_vie : CVM (B78_mi_vie) : (F05/2017): REC CVM niv2 D5.3","2016-09-23","Annulé","2016-09-28",null,"2016-09-23","OTD",null,"FTR"]
["MCSH-3533-L-110696","AIT - MCSI","2016-07-29T14:44:41","CSAC",null,null,"DO_CESARE","P8X : CVM (P8) : P87 (F05/2016); BE D5.3 pour CVM niv1 & 2","2016-09-23","Annulé",null,null,"2016-09-23","OTD","2016-09-26","FTR"]
["MCSH-5234-L-111467","AIT - MCSI","2016-08-26T12:04:29","AURA",null,null,"OF_PIECE","A94 : LECTEUR_CD_EXTERNE (AVEC FACADE) : Officialisation d'une pièce","2016-09-23","Annulé",null,null,"2016-09-23","DR","2016-09-30","FTR"]
["MCSH-5893-L-111169","AIT - MCSI","2016-08-17T03:26:57","CSAC",null,null,"DO_CESARE","P1MO : CVM (A88,P1MO) : P1MO (DàD/DàG): BE CVM Niv 1 D5.3 pour stade MVBns","2016-09-30","Annulé",null,null,"2016-09-23","OTD","2016-09-26","FTR"]
["MCSH-5893-L-111171","AIT - MCSI","2016-08-17T03:30:38","CSAC",null,null,"DO_CESARE","A88 : CVM (A88,P1MO) : A88 (DàD/DàG): BE CVM Niv 1 D5.3 pour stade PPV3","2016-09-30","Annulé",null,null,"2016-09-23","OTD","2016-09-26","FTR"]
["MCSH-8050-L-111611","AIT - MCSI","2016-09-02T11:38:39","CSAC",null,null,"OF_PIECE","X74E : CVP (X74E) : Officialisation d'une pièce. Officialisation de la caméra AV pour X74E","2016-09-30","Annulé",null,null,"2016-09-23","DR","2016-10-24","ACCEPTE_DEFAUT"]
["MCSH-8050-L-111613","AIT - MCSI","2016-09-02T11:38:54","CSAC",null,null,"OF_PIECE","X74E : CVP (X74E) : Officialisation d'une pièce: officialisation de la caméra AR sur X74E","2016-09-30","Annulé",null,null,"2016-09-23","DR","2016-10-24","ACCEPTE_DEFAUT"]
["MCSH-7066-L-112226","AIT - MCSI","2016-09-21T03:45:37","CSAC",null,null,"DO_CESARE","G95_PH2,MODULE_EE02 : CVM (G95 Ph2) : BE pour CVM niv2 D5.2f (màj CAL)","2016-09-30","Annulé",null,null,"2016-09-23","DR","2016-10-21","FTR"]
["MCSH-3533-L-109336","AIT - MCSI","2016-06-30T02:09:30","CSAC",null,null,"OF_CAL","P8X : CVM (P8) : P84 & P87 (F05/2017): Officialisation CAL CVM niv1 & 2 D5.3","2016-09-23","Annulé","2016-09-30","Retard fournisseur","2016-09-26","OTD",null,"FTR"]
["MCSH-8700-L-110723","AIT - MCSI","2016-08-01T03:42:09","SWES",null,null,"OF_PIECE","M3M4_MV : _COM200X (Impact DMT sur e6.2 = MAJ diversité COM) : Officialisation d'une pièce - REC M3M4","2016-09-30","Annulé",null,null,"2016-09-26","OTD",null,"FTR"]
["MCSH-7066-L-112213","AIT - MCSI","2016-09-21T02:11:26","CSAC",null,null,"OF_CAL","G95_PH2 : CVM (G95 Ph2) : Officialisation CAL CVM niv2 D5.2f","2016-09-30","Annulé",null,null,"2016-09-26","DR","2016-09-27","FTR"]
["MCSH-2984-L-112104","EST - MCSI","2016-09-14T16:49:12","ECPC",null,null,"OF_PIECE","C84_Export : PUSH_LVI_AR,PUSH_LVI_AV : Officialisation (REC) 3D/2D Fonctionnel - Push LVI BITRON AR","2016-08-01","Annulé","2016-09-30",null,"2016-09-27","DR","2016-10-28","ACCEPTE_DEFAUT"]
["MCSH-7505-L-111778","EST - MCSI","2016-09-05T13:54:43","ELPS",null,null,"OF_PIECE","_VS :  (MUS, Rupteur, Sirène, AUS, ) : Officialisation d'une pièce REC agrafe rupteur","2016-09-30","Annulé",null,null,"2016-09-27","DR",null,"FTR"]
["MCSH-5893-L-109417","AIT - MCSI","2016-07-04T10:31:31","CSAC",null,null,"OF_CAL","P1MO : CVM (A88,P1MO) : Calibration CVM Gen 2 Niveau 1 (soft D5.3) pour stade MVBns  P1MO version DàG (LHD)","2016-09-23","Annulé","2016-09-30","Abscence valideur ou expert","2016-09-28","OTD",null,"FTR"]
["MCSH-4124-L-111853","AIT - MCSI","2016-09-08T14:26:26","CSAC",null,null,"DO_BE_CESARE","X74E : CVM (X74E) : Mise à jour et livraison BE CESARE pour VRS DV","2016-09-23","Annulé","2016-09-28",null,"2016-09-28","DR","2016-10-12","FTR"]
["MCSH-5893-L-109415","AIT - MCSI","2016-07-04T10:30:34","CSAC",null,null,"OF_CAL","P1MO : CVM (A88,P1MO) : Calibration CVM Gen 2 Niveau 3 (SW6) pour stade MVBNs P1MO version DàG (LHD)","2016-09-30","Annulé",null,null,"2016-09-28","OTD",null,"FTR"]
["MCSH-5893-L-109425","AIT - MCSI","2016-07-04T11:21:57","CSAC",null,null,"OF_CAL","A88 : CVM (A88,P1MO) : Calibration CVM Gen 2 Niveau 3 (SW6) pour stade PPV3 A88 version DàG (LHD)","2016-09-30","Annulé",null,null,"2016-09-28","OTD","2016-09-28","FTR"]
["MCSH-5893-L-109426","AIT - MCSI","2016-07-04T11:22:25","CSAC",null,null,"OF_CAL","A88 : CVM (A88,P1MO) : Calibration CVM Gen 2 Niveau 3 (SW6) pour stade PPV3 A88 version DàD (RHD)","2016-09-30","Annulé",null,null,"2016-09-28","OTD","2016-09-28","FTR"]
["MCSH-8007-L-112375","EST - MCSI","2016-09-28T12:06:04","HD2C",null,null,"DO_BE_CESARE","MODULE_EE09 : MATTC (SW3.0) : Création /Mise à jour BE CESARE","2016-10-10","Annulé",null,null,"2016-09-28","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-8007-L-112376","EST - MCSI","2016-09-28T12:07:06","HD2C",null,null,"DO_BE_CESARE","MODULE_EE09 : MATTC (SW3.0) : Création /Mise à jour BE CESARE","2016-10-10","Annulé",null,null,"2016-09-28","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-8007-L-112377","EST - MCSI","2016-09-28T12:11:20","HD2C",null,null,"DO_EDE_FM","MODULE_EE09 : MATTC (SW3.0) : Expression de besoin EDE et des FM pour le développement.","2016-10-10","Annulé",null,null,"2016-09-28","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-8007-L-112378","EST - MCSI","2016-09-28T12:11:41","HD2C",null,null,"DO_EDE_FM","MODULE_EE09 : MATTC (SW3.0) : Expression de besoin EDE et des FM pour le développement.","2016-10-10","Annulé",null,null,"2016-09-28","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-6555-L-77413","EST - MCSI","2014-10-17T11:26:52","ELAC",null,null,"RT_CALIB","A88,MODULE_HAB05,P1MO : GRPE_CLIM : RT robustesse calibration BCC ->CAL 5 pour  EL1","2016-09-29","Annulé",null,null,"2016-09-29","OTD","2016-10-17","FTR"]
["MCSH-6555-L-77419","EST - MCSI","2014-10-17T11:26:52","ELAC",null,null,"LIV_PARAM_GRP_RG_1","A88,MODULE_HAB05,P1MO : GRPE_CLIM : Réception du Fichier paramètrage  ADTH validé pour calibration 5 EL1","2016-09-29","Annulé",null,null,"2016-09-29","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7121-L-109183","AIT - MCSI","2016-06-27T09:17:26","CSAC",null,null,"OF_CAL","T9_MV : CVM (T9MV) : Calibration CVM Gen 2 Niv 2 D5.3 pour EL1","2016-09-30","Annulé","2016-08-19",null,"2016-09-29","OTD",null,"FTR"]
["MCSH-5893-L-109416","AIT - MCSI","2016-07-04T10:30:56","CSAC",null,null,"OF_CAL","P1MO : CVM (A88,P1MO) : Calibration CVM Gen 2 Niveau 3 (SW6) pour stade MVBNs P1MO version DàD (RHD)","2016-09-30","Annulé",null,null,"2016-09-29","OTD",null,"FTR"]
["MCSH-7415-L-111473","EST - MCSI","2016-08-26T15:23:54","ELAC",null,null,"OF_PIECE","X74E : GRPE_CLIM : Officialisation faisceauRFTA sans AQS","2016-09-30","Annulé",null,null,"2016-09-29","DR",null,"FTR"]
["MCSH-7480-L-92355","AIT - MCSI","2015-06-08T12:00:35","CSAC",null,null,"DO_CESARE","B751_3_4_MV : RADAR GÉN3 (B753_4  MV) : Livraison BEs D5.4 VRS UT (VRS2)","2016-10-03","Annulé",null,null,"2016-09-29","OTD","2016-09-29","FTR"]
["MCSH-7480-L-100338","AIT - MCSI","2015-12-14T11:22:09","CSAC",null,null,"DO_CESARE","B751_3_4_MV : RADAR GÉN3 (B753_4  MV) : Création de référence/Mise à jour CESARE pour D5.4 VRS2","2016-10-03","Annulé",null,null,"2016-09-29","OTD","2016-09-29","FTR"]
["MCSH-8302-L-99895","EST - MCSI","2015-12-07T14:46:36","ELPS",null,null,"SDF_NS","A9X_F_05_17 : PROJ : Avis et Synthèse SDF sur organe","2015-12-07","Annulé","2016-09-30","Retard fournisseur","2016-09-30","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-8302-L-99887","EST - MCSI","2015-12-07T14:46:36","ELPS",null,null,"VAL_ANA_PV_FNR","A9X_F_05_17 : PROJ : Analyse du plan de validation fournisseur","2016-01-11","Annulé","2016-10-07",null,"2016-09-30","DR","2016-10-31","ACCEPTE_DEFAUT"]
["MCSH-8302-L-99890","EST - MCSI","2015-12-07T14:46:36","ELPS",null,null,"DO_STD","A9X_F_05_17 : PROJ : Spécification Technique Détaillée","2016-01-20","Annulé","2016-10-05","Décalage projet","2016-09-30","OTD","2016-10-31","ACCEPTE_DEFAUT"]
["MCSH-8302-L-99888","EST - MCSI","2015-12-07T14:46:36","ELPS",null,null,"RT_STD","A9X_F_05_17 : PROJ : Avec le Fournisseur - Vérif indice STD","2016-02-01","Annulé","2016-10-03","Décalage projet","2016-09-30","OTD","2016-10-31","ACCEPTE_DEFAUT"]
["MCSH-8304-L-99951","EST - MCSI","2015-12-07T16:49:28","ELPS",null,null,"SDF_PSDF_FNR","A9X_F_05_17 : PROJ (_STT) : Plan de sûreté de fonctionnement du fournisseur. Attendu : AMDEC, AFI, AFE et ADD","2016-02-15","Annulé","2016-10-06",null,"2016-09-30","Retard",null,"ACCEPTE_DEFAUT"]
["MCSH-5876-L-71295","EST - MCSI","2014-06-06T16:15:00","ELAC",null,null,"DO_DIVERS","P84_Chine : GRPE_CLIM : Mise en nomenclature des référence APV","2016-03-21","Annulé","2016-09-30","Manque donnée d'entrée","2016-09-30","OTD","2016-10-17","FTR"]
["MCSH-8302-L-99886","EST - MCSI","2015-12-07T14:46:36","ELPS",null,null,"VAL_PT","A9X_F_05_17 : PROJ : Plan de test (description des outils, des protocoles utilisés, ...) pour TU","2016-03-21","Annulé","2016-10-04","Décalage projet","2016-09-30","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-5893-L-109427","AIT - MCSI","2016-07-04T11:22:36","CSAC",null,null,"OF_CAL","A88 : CVM (A88,P1MO) : Calibration CVM Gen 2 Niveau 1 (soft D5.3) pour stade PPV3 A88 version DàG (LHD)","2016-09-23","Annulé","2016-09-30","Abscence valideur ou expert","2016-09-30","OTD",null,"FTR"]
["MCSH-8059-L-112236","AIT - MCSI","2016-09-22T09:21:27","AURA",null,null,"OF_PIECE","P1MO : LECTEUR_CD_EXTERNE (Avec Facade) : Officialisation d'une pièce, Lecteur CD DMTLESS avec façade VAR A","2016-09-30","Annulé",null,null,"2016-09-30","DR","2016-10-31","ACCEPTE_DEFAUT"]
["MCSH-8304-L-99944","EST - MCSI","2015-12-07T16:49:28","ELPS",null,null,"VAL_ANA_PV_FNR","A9X_F_05_17 : PROJ (_STT) : Analyse du plan  de validation fournisseur","2016-09-30","Annulé","2016-09-30","Retard fournisseur","2016-09-30","OTD","2016-10-31","ACCEPTE_DEFAUT"]
["MCSH-8161-L-103255","AIT - MCSI - SMEG","2016-02-15T11:32:38","IDEV",null,null,"ANI_RD_PROJET","MODULE_EE07,_F09/2016 : SMEG+_I_V2 : Réunion de décision projet MDT","2016-09-30","Annulé",null,null,"2016-09-30","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-3036-L-110633","AIT - MCSI","2016-07-29T08:48:27","CSAC",null,null,"DO_CDCI_BILAN","B751_3_4_MV,B78_mi_vie,B81_Chine_Fenêtre_VS,C84_Chine,G95_PH2,K0,MODULE_EE02,P1UO,P84_Chine,P87_Chine,P8X,T9_MV,X81_Chine : RADAR GÉN3 : Synthèses d'avancement de toutes les implantation Radar / Fichier de pilotage interne et avec fournisseur.","2016-09-30","Annulé",null,null,"2016-09-30","OTD","2016-09-30","FTR"]
["MCSH-7121-L-111179","AIT - MCSI","2016-08-18T08:51:57","CSAC",null,null,"DO_CESARE","T9_MV : CVM (T9MV) : BE CVM niv2 D5.3","2016-09-30","Annulé",null,null,"2016-09-30","OTD","2016-10-21","FTR"]
["MCSH-5267-L-111838","AIT - MCSI","2016-09-07T16:47:31","AURA",null,null,"OF_PIECE","W2_R : LECTEUR_CD_EXTERNE (SANS FACADE) : W2  -Officialisation d'une pièce","2016-09-30","Annulé",null,null,"2016-09-30","DR","2016-10-05","FTR"]
["MCSH-7480-L-92356","AIT - MCSI","2015-06-08T12:00:35","CSAC",null,null,"OF_CAL","B751_3_4_MV : RADAR GÉN3 (B753_4  MV) : Calibration D5.4 pour VRS UT (VRS2)","2016-10-03","Annulé",null,null,"2016-09-30","OTD","2016-09-30","FTR"]
["MCSH-7480-L-100339","AIT - MCSI","2015-12-14T11:22:09","CSAC",null,null,"OF_CAL","B751_3_4_MV : RADAR GÉN3 (B753_4  MV) : Calibration D5.4 pour VRS2","2016-10-03","Annulé",null,null,"2016-09-30","OTD","2016-09-30","FTR"]
["MCSH-5876-L-109905","EST - MCSI","2016-07-20T09:00:46","ELAC",null,null,"OF_PIECE","P84_Chine : GRPE_CLIM : Officialisation Faisceau","2016-10-14","Annulé","2016-09-30",null,"2016-09-30","OTD",null,"FTR"]
["MCSH-8557-L-109453","EST - MCSI","2016-07-04T16:45:16","HD2C",null,null,"OF_DOC","MODULE_EE09 : MATTP (Sw1.6 (DMTLess)) : Officialisation ULP Sw1.6","2016-10-14","Annulé",null,null,"2016-09-30","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-3040-L-112510","AIT - MCSI","2016-09-30T16:22:19","CSAC",null,null,"OF_CAL","K0 : CVM (K0) : Vie série (Modernisation APV): officialisation CAL D5.2f","2016-10-07","Annulé",null,null,"2016-10-04","DR","2016-10-07","FTR"]
["MCSH-3040-L-112511","AIT - MCSI","2016-09-30T16:26:06","CSAC",null,null,"DO_CESARE","K0 : CVM (K0) : Vie série (Modernisation APV): BE D5.2f","2016-10-07","Annulé",null,null,"2016-10-04","DR","2016-10-07","FTR"]
["MCSH-7358-L-106687","EST - MCSI","2016-04-18T09:50:41","ELPS",null,null,"RT_HW","D34E : FEUX_AR : Bilan LayOut - Verif CCA et EMC","2016-06-15","Annulé","2016-10-06","Décalage projet","2016-10-05","OTD","2016-10-07","FTR"]
["MCSH-7311-L-77842","AIT - MCSI","2014-10-30T15:11:16","SWES",null,null,"DO_PEPP","_QUALITE : COM2005_EV3 (Réactivité sans délai_DELPHI : pb son) : A3 PEPP à compléter","2016-09-30","Annulé","2016-10-05","Retard fournisseur","2016-10-05","OTD","2016-10-26","FTR"]
["MCSH-5891-L-112468","AIT - MCSI","2016-09-29T17:20:52","CSAC",null,null,"OF_PIECE","B618 : CVM (B618) : (F05/2017): Reconduction CVM niv1 D5.3","2016-10-07","Annulé",null,null,"2016-10-05","DR","2016-10-21","FTR"]
["MCSH-5893-L-111176","AIT - MCSI","2016-08-18T08:26:03","CSAC",null,null,"DO_CESARE","P1MO : CVM (A88,P1MO) : P1MO (DàD/DàG): BE CVM VAEB SW6c","2016-10-07","Annulé",null,null,"2016-10-05","OTD","2016-10-21","FTR"]
["MCSH-5893-L-111177","AIT - MCSI","2016-08-18T08:28:10","CSAC",null,null,"DO_CESARE","A88 : CVM (A88,P1MO) : A88 (DàD/DàG): BE CVM VAEB SW6c","2016-10-07","Annulé",null,null,"2016-10-05","OTD","2016-10-21","FTR"]
["MCSH-6027-L-112501","EST - MCSI","2016-09-30T14:48:58","ECPC",null,null,"OF_PIECE","R83E : PUSH_TO_VELUM : Officialisation (REC) 3D/2D Fonctionnel - Module TO/VELUM ","2016-09-30","Annulé","2016-10-07",null,"2016-10-06","DR","2016-11-07","ACCEPTE_DEFAUT"]
["MCSH-6825-L-112354","AIT - MCSI","2016-09-27T05:18:13","CSAC",null,null,"OF_CAL","B78_mi_vie : RADAR GÉN3 (B78 MV) : MAJ CALs D5.3b (Modif FCW) pour MDL F02/2017","2016-10-06","Annulé",null,null,"2016-10-06","DR","2016-10-10","FTR"]
["MCSH-6825-L-112355","AIT - MCSI","2016-09-27T05:18:34","CSAC",null,null,"DO_CESARE","B78_mi_vie : RADAR GÉN3 (B78 MV) : Livraison BEs CESARE D5.3b (Modif FCW) pour MDL F02/2017","2016-10-06","Annulé",null,null,"2016-10-06","DR","2016-10-10","FTR"]
["MCSH-7147-L-86499","AIT - MCSI","2015-03-18T13:08:58","CSAC",null,null,"DO_CESARE","G95_PH2 : RADAR GÉN3 (G95Ph2) : Livraison BE CESARE D5.3b (modif FCW) en cours d'EL2","2016-10-07","Annulé",null,null,"2016-10-06","OTD","2016-10-10","FTR"]
["MCSH-5893-L-112382","AIT - MCSI","2016-09-28T13:53:05","CSAC",null,null,"OF_PIECE","P1MO : CVM (A88,P1MO) : P1MO: Reconduction CVM VAEB SW6c pour MVBNs","2016-10-07","Annulé",null,null,"2016-10-06","DR","2016-10-21","FTR"]
["MCSH-5893-L-112383","AIT - MCSI","2016-09-28T13:53:22","CSAC",null,null,"OF_PIECE","A88 : CVM (A88,P1MO) : A88: Reconduction CVM VAEB SW6c pour PPV3","2016-10-07","Annulé",null,null,"2016-10-06","DR","2016-10-21","FTR"]
["MCSH-3533-L-112407","AIT - MCSI","2016-09-29T11:03:48","CSAC",null,null,"OF_PIECE","P8X : CVM (P8) : (F05/2017) - P84 et P87 Europe:\r\nReconduction de la CVM niv1 et niv2 D5.3","2016-10-07","Annulé",null,null,"2016-10-06","DR","2016-10-12","FTR"]
["MCSH-5891-L-112470","AIT - MCSI","2016-09-29T17:26:11","CSAC",null,null,"OF_CAL","B618 : CVM (B618) : (F05.2017): Officialisation Calibration CVM niv1 D5.3","2016-10-07","Annulé",null,null,"2016-10-06","DR","2016-10-21","FTR"]
["MCSH-5891-L-112472","AIT - MCSI","2016-09-29T05:33:01","CSAC",null,null,"DO_CESARE","B618 : CVM (B618) : (F05/2017): BE CVM niv1 D5.3","2016-10-07","Annulé",null,null,"2016-10-06","DR","2016-10-21","FTR"]
["MCSH-925-L-110925","EST - MCSI","2016-08-04T01:24:51","ELAC",null,null,"DO_DIVERS","_METIER,_QUALITE : _QUALITE : Indicateurs qualité ELAC de Septembre (données de Juillet et Août)","2016-09-23","Annulé","2016-10-07","Evolution donnée d'entrée","2016-10-07","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-926-L-108466","EST - MCSI","2016-06-06T08:40:01","ELAC",null,null,"DO_DIVERS","_PLANEE,_PM0500_Connaissance,_METIER : _ANALYSE_CONCURRENCE : Bench stepper LIN et CTP.","2016-09-23","Annulé","2016-10-07","Abscence valideur ou expert","2016-10-07","OTD","2016-11-21","NOT FTR"]
["MCSH-7415-L-98917","EST - MCSI","2015-11-12T14:11:59","ELAC",null,null,"DO_ETAT_ACCEPT","X74E : GRPE_CLIM : Etat acceptation pour VRS1.","2016-09-26","Annulé","2016-10-31","Abscence valideur ou expert","2016-10-07","OTD","2016-10-17","FTR"]
["MCSH-4199-L-108355","AIT - MCSI","2016-05-31T09:14:27","CSAC",null,null,"DO_CESARE","X81_Chine : RADAR GÉN3 (X81C) : Livraison BE CESARE D5.4 EL F03/2017","2016-10-10","Annulé",null,null,"2016-10-07","OTD","2016-10-10","FTR"]
["MCSH-7034-L-111018","AIT - MCSI","2016-08-08T15:12:46","CSAC",null,null,"OF_CAL","B78_mi_vie : CVM (B78_mi_vie) : (F05/2017): CAL CVM niv2 D5.3","2016-10-12","Annulé",null,null,"2016-10-07","OTD","2016-10-21","FTR"]
["MCSH-4199-L-108356","AIT - MCSI","2016-05-31T09:14:41","CSAC",null,null,"OF_CAL","X81_Chine : RADAR GÉN3 (X81C) : CAL D5.4 EL F03/2017","2016-10-10","Annulé",null,null,"2016-10-08","OTD","2016-10-10","FTR"]
["MCSH-7147-L-86500","AIT - MCSI","2015-03-18T13:08:58","CSAC",null,null,"OF_CAL","G95_PH2 : RADAR GÉN3 (G95Ph2) : MAJ CAL D5.3b (modif FCW) en cours d'EL2","2016-10-07","Annulé","2016-10-14","Retard du TOP offi","2016-10-09","OTD","2016-10-10","FTR"]
["MCSH-2509-L-106486","AIT - MCSI","2016-04-13T11:45:36","SWES",null,null,"VAL_ANA_INDIC","MODULE_HAB10,A58VS,Ai51M,B9,B9E,G9,T1_Iran,T3,T3_Iran,T61_Chine,T7,T7xA,T73,T7x_Mercosur,T73_Chine,T73_Malaisie,T73_Russie,T75,T76,T7H : COM2005_EV3 (Delphi : Suivi Vie Série) : Vérifier les engagements qualité du FNR et prioriser en fonction des têtes de pareto. Objectif en début d'année, bilan à mi et fin d'année.","2016-09-30","Annulé","2016-10-10","Diponibilté des interlocuteurs","2016-10-10","OTD","2016-10-26","FTR"]
["MCSH-7953-L-111274","AIT - MCSI - NAC","2016-08-24T11:21:34","IVI",null,null,"OF_PIECE","K9 : NAC Wave 3 : Officialisation REC NAC W3 sur K9","2016-09-30","Annulé","2016-10-10","Erreur Metier (RCD, Impl., Concept…)","2016-10-10","DR","2016-11-11","ACCEPTE_DEFAUT"]
["MCSH-7953-L-109880","AIT - MCSI - NAC","2016-07-19T14:56:12","IVI",null,null,"OF_PIECE","K9 : NAC Wave 3 : Officialisation REC NAC sur K9","2016-10-10","Annulé",null,null,"2016-10-10","OTD","2016-11-11","ACCEPTE_DEFAUT"]
["MCSH-7034-L-111019","AIT - MCSI","2016-08-08T15:25:05","CSAC",null,null,"DO_CESARE","B78_mi_vie : CVM (B78_mi_vie) : (F05/2017): BE CVM niv2 D5.3","2016-10-12","Annulé",null,null,"2016-10-10","OTD","2016-10-21","FTR"]
["MCSH-7154-L-76347","AIT - MCSI","2014-10-06T13:01:03","CSAC",null,null,"DO_CESARE","P1UO : CVM (P1UO) : BE CVM Gen 2 Niveau 1 & 2 D5.3 pour stade VRSUT","2016-10-14","Annulé",null,null,"2016-10-10","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-5891-L-112612","AIT - MCSI","2016-10-05T03:06:31","CSAC",null,null,"OF_PIECE","B618 : CVM (B618) : (F05.2017): Reconduction CVM niv3 VAEB SW6c","2016-10-14","Annulé",null,null,"2016-10-10","DR","2016-10-12","FTR"]
["MCSH-7970-L-92192","AIT - MCSI","2015-06-05T16:44:07","CSAC",null,null,"RT_CDCI","C84_Chine : CVP (C84 Chine) : Revue technique de CDCI","2016-10-17","Annulé",null,null,"2016-10-10","OTD","2016-11-11","ACCEPTE_DEFAUT"]
["MCSH-5891-L-113020","AIT - MCSI","2016-10-13T16:09:54","CSAC",null,null,"DO_CESARE","B618 : CVM (B618) : (F05/2017): BE CVM VAEB SW6c","2016-10-21","Annulé",null,null,"2016-10-10","DR","2016-10-21","FTR"]
["MCSH-7970-L-92191","AIT - MCSI","2015-06-05T16:44:07","CSAC",null,null,"DO_CDCI_BILAN","C84_Chine : CVP (C84 Chine) : Bilan des retours des CDCI","2016-10-24","Annulé",null,null,"2016-10-10","OTD","2016-11-11","ACCEPTE_DEFAUT"]
["MCSH-7230-L-100763","AIT - MCSI","2015-12-22T14:58:43","CSAC",null,null,"OF_DOTE","R83_Chine : RADAR_GÉN4 (R83_Chine) : Pour Stade DFE TI (B2)","2016-09-16","Annulé","2016-10-31","Livrable affecté en retard","2016-10-11","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-2509-L-106487","AIT - MCSI","2016-04-13T11:45:36","SWES",null,null,"ANI_MENSUELLE","MODULE_HAB10,A58VS,Ai51M,B9,B9E,G9,T1_Iran,T3,T3_Iran,T61_Chine,T7,T7xA,T73,T7x_Mercosur,T73_Chine,T73_Malaisie,T73_Russie,T75,T76,T7H : COM2005_EV3 (Delphi : Suivi Vie Série) : Trimestrielle FNR. En pièce jointe ODJ (1 semaine avant) + CR technique. Lien vers l'ODJ type : http://docinfogroupe.inetpsa.com/ead/doc/ref.00948_10_00977/v.vc/fiche. Lien vers le CR type : http://docinfo.inetpsa.com/ead00/doc/ref.00948_10_00984/v.vc/fic","2016-09-30","Annulé","2016-10-11","Diponibilté des interlocuteurs","2016-10-11","OTD","2016-10-26","FTR"]
["MCSH-3036-L-110519","AIT - MCSI","2016-07-29T08:42:47","CSAC",null,null,"SYN_ALTIS ","B751_3_4_MV,B78_mi_vie,B81_Chine_Fenêtre_VS,C84_Chine,G95_PH2,K0,MODULE_EE02,P1UO,P84_Chine,P87_Chine,P8X,T9_MV,X81_Chine : RADAR GÉN3 : Gestion Hebdomadaire Altis\r\n","2016-10-12","Annulé",null,null,"2016-10-12","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7094-L-112508","EST - MCSI","2016-09-30T15:33:37","ECPC",null,null,"OF_PIECE","C84_Export : COVML : Officialisation (REC) 3D/2D Fonctionnel - COVML BITRON","2016-10-21","Annulé","2016-10-31",null,"2016-10-12","DR","2016-11-14","ACCEPTE_DEFAUT"]
["MCSH-4124-L-82321","AIT - MCSI","2015-01-14T13:07:17","CSAC",null,null,"OF_CAL","X74E : CVM (X74E) : Calibration pour VRS1 >> version CVM AEE-R3 HS+HS; VIDEO","2016-10-13","Annulé",null,null,"2016-10-13","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-2549-L-85591","AIT - MCSI","2015-03-02T15:39:54","SWES",null,null,"VAL_RECETTE","C84_Chine,D34E,K9,MODULE_HAB10,P24E,R82E,R83E,R83_Chine,X81_Chine,X83_Chine : CSV (2017) : Recette C4 :\r\ncycle de validation du PV de recette initié au plus tard 3 jours apres la recette.","2016-10-13","Annulé",null,null,"2016-10-13","OTD","2016-12-16","ACCEPTE_DEFAUT"]
["MCSH-7075-L-99739","AIT - MCSI","2015-12-01T03:40:50","CSAC",null,null,"DO_CESARE","T9_MV : RADAR GÉN3 (T9MV) : livraison BEs D5.4 EL1.1 T9MV et VRS pour DW10FC-AMN8 pour T91&T92","2016-10-14","Annulé",null,null,"2016-10-13","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-8007-L-103803","EST - MCSI","2016-02-25T13:31:43","HD2C",null,null,"OF_PIECE","MODULE_EE09 : MATTC (SW3.0) : Officialisation pièce Sw3.0","2016-10-14","Annulé",null,null,"2016-10-13","OTD","2016-11-14","ACCEPTE_DEFAUT"]
["MCSH-3533-L-112246","AIT - MCSI","2016-09-22T16:55:55","CSAC",null,null,"OF_PIECE","P8X : CVM (P8) : P87: Reconduction CVM VAEB SW6c","2016-10-14","Annulé",null,null,"2016-10-13","DR","2016-10-21","FTR"]
["MCSH-4124-L-112539","AIT - MCSI","2016-10-03T13:17:28","CSAC",null,null,"OF_CAL","X74E : CVM (X74E) : Officialisation CAL VRS DV pour X74E","2016-10-14","Annulé",null,null,"2016-10-13","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-5895-L-112683","AIT - MCSI","2016-10-06T17:54:49","CSAC",null,null,"OF_PIECE","A88 : CVP : Officialisation d'une pièce","2016-10-14","Annulé","2016-10-14",null,"2016-10-13","DR","2016-10-20","FTR"]
["MCSH-7989-L-112882","AIT - MCSI","2016-10-12T14:28:20","CSAC",null,null,"OF_CAL","P87_Chine : CVM (P87C) : Officialisation des calibrations CVM niv1 & 2 D5.3 (VRS2.2)","2016-10-14","Annulé",null,null,"2016-10-13","DR","2016-10-21","FTR"]
["MCSH-3533-L-113014","AIT - MCSI","2016-10-13T15:48:50","CSAC",null,null,"DO_CESARE","P8X : CVM (P8) : P87 (lancement): BE SW6c pour VAEB 0.9g full breaking","2016-10-14","Annulé",null,null,"2016-10-13","DR","2016-10-21","FTR"]
["MCSH-8682-L-112056","EST - MCSI","2016-09-13T14:24:09","HD2C",null,null,"VAL_RECETTE","MODULE_EE09 : MATTC (SW2.9) : Recette & validation Sw2.9","2016-10-14","Annulé",null,null,"2016-10-14","DR","2016-11-15","ACCEPTE_DEFAUT"]
["MCSH-8262-L-112600","EST - MCSI","2016-10-05T13:24:24","EACC",null,null,"OF_PIECE","P8_Europe_VS_Fenetre : AVE (P8 et P8C) : Officialisation d'une pièce AVE","2016-10-14","Annulé",null,null,"2016-10-14","DR","2016-10-20","FTR"]
["MCSH-8262-L-112601","EST - MCSI","2016-10-05T01:25:19","EACC",null,null,"OF_PIECE","P8_Europe_VS_Fenetre : AVE (P8 et P8C) : Officialisation d'une pièce vis de fixation AVE","2016-10-14","Annulé",null,null,"2016-10-14","DR","2016-10-20","FTR"]
["MCSH-8847-L-113081","EST - MCSI","2016-10-14T17:36:58","HD2C",null,null,"DO_CDCI_BILAN","MODULE_EE09 : TNB (Tous types) : Bilan des retours des CDCI P2x","2016-10-28","Annulé",null,null,"2016-10-14","DR","2016-11-15","ACCEPTE_DEFAUT"]
["MCSH-4192-L-109195","AIT - MCSI","2016-06-27T10:33:02","CSAC",null,null,"OF_CAL","X81_Chine : CVM (X81_Chine) : Vie série (F03/2017): Calibration pour CVM D5.3","2016-11-10","Annulé",null,null,"2016-10-15","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-1014-L-111593","EST - MCSI","2016-09-01T09:19:54","ECPC",null,null,"RI_TOP_RO","A55_PRO,K0,K9,MODULE_EE05,P1MO,P21 : PDPC_2LVI_RE,PDPC_2LVI_RE_RA : Revue Technique d'interface pour robustesse avant top RO\r\n(idem ARIS)","2016-08-11","Annulé","2016-10-31","RAL en retard","2016-10-17","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-8247-L-110955","AIT - MCDV","2016-08-04","ECHP",null,null,"OF_PIECE","PHEV : _TRAVAUX_CAO : Officialisation du plan Fonctionnel capteur point mort complet","2016-10-17","Annulé",null,null,"2016-10-17","OTD","2016-11-02","FTR"]
["MCSH-8007-L-112379","EST - MCSI","2016-09-28T12:17:55","HD2C",null,null,"DO_EDE_FM","MODULE_EE09 : MATTC (SW3.0) : Expression de besoin EDE et des FM pour le développement.","2016-10-17","Annulé",null,null,"2016-10-17","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-7164-L-112595","AIT - MCSI","2016-10-05T11:45:18","CSAC",null,null,"DO_CESARE","P84_Chine : RADAR GÉN3 (P84_C) : Livraison BEs CESARE D5.4 pour EL F03/2017","2016-10-18","Annulé",null,null,"2016-10-17","DR","2016-10-20","FTR"]
["MCSH-8072-L-108877","EST - MCSI","2016-06-16T17:43:53","EACC",null,null,"OF_PIECE","C84_Export : ANTENNE_BACKUP (C84) : Officialisation d'une pièce","2016-10-21","Annulé",null,null,"2016-10-17","OTD","2016-10-26","FTR"]
["MCSH-8007-L-112494","EST - MCSI","2016-09-30T13:43:27","HD2C",null,null,"OF_DOC","MODULE_EE09 : MATTC (SW3.0) : Officialisation ULP 2.9 \r\nCorrection  des ALTIS 7006603 et 7672990 ","2016-10-28","Annulé",null,null,"2016-10-17","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-8682-L-112057","EST - MCSI","2016-09-13T14:28:29","HD2C",null,null,"OF_DOC","MODULE_EE09 : MATTC (SW2.9) : Officialisation ULP Sw2.9","2016-10-31","Annulé",null,null,"2016-10-17","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-8847-L-113082","EST - MCSI","2016-10-14T17:37:35","HD2C",null,null,"DO_CDCI_BILAN","MODULE_EE09 : TNB (Tous types) : Bilan des retours des CDCI D34","2016-10-31","Annulé",null,null,"2016-10-17","DR","2016-11-18","ACCEPTE_DEFAUT"]
["MCSH-7953-L-111275","AIT - MCSI - NAC","2016-08-24T11:24:11","IVI",null,null,"OF_PIECE","MODULE_EE07 : NAC Wave 3 : Officialisation REC NAC W3 sur F3","2016-11-04","Annulé",null,null,"2016-10-17","OTD","2016-11-18","ACCEPTE_DEFAUT"]
["MCSH-3014-L-106507","EST - MCSI","2016-04-14T14:51:25","EACC",null,null,"OF_PIECE","C84_Europe : BOB_ADC : Officialisation d'une pièce","2016-06-27","Annulé","2016-10-31","Retard fournisseur","2016-10-18","OTD","2016-11-10","FTR"]
["MCSH-7164-L-112594","AIT - MCSI","2016-10-05T11:43:40","CSAC",null,null,"OF_CAL","P84_Chine : RADAR GÉN3 (P84_C) : CALs D5.4 pour EL F03/2017","2016-10-18","Annulé",null,null,"2016-10-18","DR","2016-10-20","FTR"]
["MCSH-7684-L-113262","AIT - MCSI","2016-10-20T14:52:38","CSAC",null,null,"DO_BE_CESARE","X74E : VISIO_PARK (X74E) : Création /Mise à jour BE CESARE: livraison BE pour mise à jour des articles HW et SW pour être compatibles avec la CVP LH et DOP/CPK VALEO","2016-10-18","Annulé",null,null,"2016-10-18","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-7482-L-80673","EST - MCSI","2014-12-16T12:04:14","ELPS",null,null,"OF_DOTE","K9 : SIRENE_LIN_SSCAS,RUPTEUR_CAPOT,MUS2 : DOTE pour VRS1","2016-11-26","Annulé",null,null,"2016-10-18","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7230-L-109927","AIT - MCSI","2016-07-21T13:18:20","CSAC",null,null,"OF_PIECE","R83_Chine : RADAR_GÉN4 (R83_Chine) : Officialisation écrou de fixation radar","2016-09-30","Annulé","2016-10-31","Livrable affecté en retard","2016-10-19","OTD","2016-10-20","FTR"]
["MCSH-5865-L-74514","EST - MCSI","2014-08-11T16:01:30","ELPS",null,null,"DO_CESARE","P8X : SIRENE_LIN_SSCAS (Adapt. P8) : Livraison du BE SIR pour EL - P87\r\n","2016-10-19","Annulé",null,null,"2016-10-19","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7075-L-99738","AIT - MCSI","2015-12-01T03:37:39","CSAC",null,null,"OF_CAL","T9_MV : RADAR GÉN3 (T9MV) : CALs D5.4 EL1.1 T9MV et VRS pour DW10FC-AMN8 pour T91&T92","2016-10-19","Annulé",null,null,"2016-10-19","OTD","2016-10-20","FTR"]
["MCSH-7363-L-112868","AIT - MCSI","2016-10-12T09:58:50","CSAC",null,null,"OF_CAL","C84_Chine : CVM (C84) : Calibration CVM2 niv2 D5.3 pour VRS1.2","2016-10-24","Annulé",null,null,"2016-10-19","DR","2016-10-21","FTR"]
["MCSH-5616-L-113611","EST - MCSI","2016-10-27T17:57:58","ELAC",null,null,"DO_DIVERS","_METIER : LDA / référentiel technique CLIM : -\tAnalyse et proposition MàJ file d'essais PIV générique ELAC -> cohérence avec les derniers indices des normes B217110, 20 et B217130 ind D?","2016-11-04","Annulé",null,null,"2016-10-19","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-8822-L-112182","AIT - MCSI","2016-09-19T17:29:22","AURA",null,null,"OF_PIECE","T93_Malaisie : LECTEUR_CD_EXTERNE : Officialisation d'une pièce, Lecteur CD sans façade DMTLESS","2016-10-20","Annulé",null,null,"2016-10-20","DR","2016-11-21","ACCEPTE_DEFAUT"]
["MCSH-5267-L-112183","AIT - MCSI","2016-09-19T17:45:44","AURA",null,null,"OF_PIECE","B8_Mi_Vie : LECTEUR_CD_EXTERNE (SANS FACADE) : B81\r\nOfficialisation d'une pièce,  Lecteur CD sans façade DMTLESS","2016-10-20","Annulé",null,null,"2016-10-20","DR","2016-11-21","ACCEPTE_DEFAUT"]
["MCSH-8682-L-113394","EST - MCSI","2016-10-21T12:41:18","HD2C",null,null,"OF_DOTE","MODULE_EE09 : MATTC (SW2.9) : Officialisation de DOTE B7 MATT_C 2010 SW2.8","2016-10-31","Annulé",null,null,"2016-10-20","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-8682-L-113396","EST - MCSI","2016-10-21T12:57:33","HD2C",null,null,"DO_BE_CESARE","MODULE_EE09 : MATTC (SW2.9) : Création /Mise à jour BE CESARE W2/W2 HYB MATT_C 2010 SW2.8","2016-10-31","Annulé",null,null,"2016-10-20","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-8682-L-113397","EST - MCSI","2016-10-21T12:57:55","HD2C",null,null,"DO_BE_CESARE","MODULE_EE09 : MATTC (SW2.9) : Création /Mise à jour BE CESARE B7 pour MATT_C 2010 SW2.8","2016-10-31","Annulé",null,null,"2016-10-20","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-3533-L-108477","AIT - MCSI","2016-06-06T11:29:27","CSAC",null,null,"DO_CESARE","P8X : CVM (P8) : P84 (F02/2017): BE SW6c pour VAEB 0.9g full breaking","2016-12-31","Annulé",null,null,"2016-10-20","OTD","2016-10-21","FTR"]
["MCSH-1727-L-110484","AIT - MCSI","2016-07-28T13:09:41","SWES",null,null,"ANI_MENSUELLE","MODULE_HAB10,_QUALITE,G95,K0,M44_Chine,T7xA,T9_Chine,W2_VS : VCI MARQUARDT (W2-K0) : Trimestrielle FNR. En pièce jointe ODJ (1 semaine avant) + CR technique. Lien vers l'ODJ type : http://docinfogroupe.inetpsa.com/ead/doc/ref.00948_10_00977/v.vc/fiche. Lien vers le CR type : http://docinfo.inetpsa.com/ead00/doc/ref.00948_10_00984/v.vc/fic","2016-10-18","Annulé","2016-10-21","Retard fournisseur","2016-10-21","OTD","2016-10-26","FTR"]
["MCSH-3042-L-112356","AIT - MCSI","2016-09-27T05:22:12","CSAC",null,null,"OF_CAL","K0 : RADAR GÉN3 (K0) : CALs D5.3b (Modif FCW) pour HF Vague F","2016-10-21","Annulé","2016-10-31",null,"2016-10-21","DR","2016-10-21","FTR"]
["MCSH-3042-L-112357","AIT - MCSI","2016-09-27T05:24:22","CSAC",null,null,"DO_CESARE","K0 : RADAR GÉN3 (K0) : Livraison BEs CESARE D5.3b (Modif FCW) pour HF Vague F","2016-10-21","Annulé","2016-10-31",null,"2016-10-21","DR","2016-10-21","FTR"]
["MCSH-3052-L-112634","AIT - MCSI","2016-10-06T10:08:49","CSAC",null,null,"OF_DOTE","A55_MV : LIDAR (A55MV) : Officialisation DOTE A55P (Prolongation) pour passage AEE2004 vers AEE2010","2016-10-21","Annulé",null,null,"2016-10-21","DR","2016-10-21","FTR"]
["MCSH-3533-L-113401","AIT - MCSI","2016-10-21T13:36:24","CSAC",null,null,"DO_CESARE","P8X : CVM (P8) : P87 (F11/2016): Mise à jour BE SW6x pour VAEB 0.9g full breaking suite à la MAJ CAL (évolution seuil de vitesse à 32km/h)","2016-10-21","Annulé",null,null,"2016-10-21","DR","2016-10-21","FTR"]
["MCSH-3533-L-113404","AIT - MCSI","2016-10-21T01:54:55","CSAC",null,null,"DO_CESARE","P8X : CVM (P8) : P84 (F02/2016): Mise à jour BE SW6x pour VAEB 0.9g full breaking suite à la MAJ CAL (évolution seuil de vitesse à 32km/h)","2016-10-21","Annulé",null,null,"2016-10-21","DR","2016-10-21","FTR"]
["MCSH-6825-L-112361","AIT - MCSI","2016-09-27T05:55:30","CSAC",null,null,"DO_CESARE","B78_mi_vie : RADAR GÉN3 (B78 MV) : Livraison BEs CESARE D5.4 pour EL1 F05/2017","2016-10-25","Annulé",null,null,"2016-10-21","DR","2016-10-24","FTR"]
["MCSH-4199-L-112412","AIT - MCSI","2016-09-29T11:52:50","CSAC",null,null,"OF_PIECE","X81_Chine : RADAR GÉN3 (X81C) : Reconduction Assemblé Radar Gen 3 D5.5 pour F11/2017 X81_CH : OCM (Application dés VRS TBC)","2016-10-28","Annulé",null,null,"2016-10-21","DR","2016-10-26","FTR"]
["MCSH-8851-L-113085","AIT - MCSI","2016-10-17T09:33:29","CSAC",null,null,"OF_DOTE","A55_PRO : LIDAR (A55P) : Officialisation DOTE A55P (Prolongation) pour passage AEE2004 vers AEE2010","2016-10-28","Annulé",null,null,"2016-10-21","DR","2016-10-21","FTR"]
["MCSH-8682-L-113395","EST - MCSI","2016-10-21T12:41:37","HD2C",null,null,"OF_DOTE","MODULE_EE09 : MATTC (SW2.9) : Officialisation de DOTE W2/W2 Hybride pour MATT_c 2010 SW2.8","2016-10-31","Annulé",null,null,"2016-10-21","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-5616-L-113612","EST - MCSI","2016-10-27T17:58:48","ELAC",null,null,"DO_DIVERS","_METIER : LDA / référentiel technique CLIM : MàJ poster archi électrique CLIM (02017_16_01766).","2016-11-11","Annulé",null,null,"2016-10-21","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-8301-L-106760","AIT - MCSI","2016-04-19T16:25:44","CSAC",null,null,"OF_PIECE","F3 : CVM (F3) : REC CVM Gen2 variante V-AEB SW6c","2016-10-21","Annulé","2016-10-31","Blocage technique","2016-10-22","OTD","2016-11-23","ACCEPTE_DEFAUT"]
["MCSH-3540-L-111484","AIT - MCSI","2016-08-29T04:47:14","CSAC",null,null,"DO_CESARE","P8_Europe_VS_Fenetre : RADAR GÉN3 (P8X) : Livraison BEs CESARE D5.4 pour EL1 P84 F05-2017","2016-10-25","Annulé",null,null,"2016-10-24","OTD","2016-10-25","FTR"]
["MCSH-3540-L-111485","AIT - MCSI","2016-08-29T04:48:38","CSAC",null,null,"OF_CAL","P8_Europe_VS_Fenetre : RADAR GÉN3 (P8X) : CALs D5.4 pour EL1 P84 F05/2017.","2016-10-25","Annulé",null,null,"2016-10-24","OTD","2016-10-25","FTR"]
["MCSH-6825-L-112362","AIT - MCSI","2016-09-27T05:56:27","CSAC",null,null,"OF_CAL","B78_mi_vie : RADAR GÉN3 (B78 MV) : CALs D5.4 pour EL1 F05/2017","2016-10-25","Annulé",null,null,"2016-10-24","DR","2016-10-24","FTR"]
["MCSH-7480-L-113171","AIT - MCSI","2016-10-17T12:36:16","CSAC",null,null,"OF_PIECE","B751_3_4_MV : RADAR GÉN3 (B753_4  MV) : REC Assemblé Radar D5.5 sur EL1.1 B75x_MV (1/3&4)","2016-10-28","Annulé",null,null,"2016-10-24","DR","2016-10-26","FTR"]
["MCSH-3533-L-113038","AIT - MCSI","2016-10-14T11:09:41","CSAC",null,null,"OF_CAL","P8X : CVM (P8) : P84 (F02/2017): CAL VAEB SW6x","2016-12-31","Annulé",null,null,"2016-10-24","OTD","2016-10-25","FTR"]
["MCSH-3040-L-110712","AIT - MCSI","2016-08-01T10:49:44","CSAC",null,null,"OF_PIECE","K0 : CVM (K0) : (F10/2017): Reconduction CVM niv2 D5.3","2016-10-28","Annulé",null,null,"2016-10-25","OTD","2016-10-26","FTR"]
["MCSH-7075-L-112404","AIT - MCSI","2016-09-28T06:39:35","CSAC",null,null,"OF_PIECE","T9_MV : RADAR GÉN3 (T9MV) : REC Assemblé Radar Gen 3 D5.5 en cours d'EL1 T9MV et EL1.2 pour DV5 & EL1 pour DW10FC-AMN8 pour T91&T92","2016-10-28","Annulé",null,null,"2016-10-25","DR","2016-10-26","FTR"]
["MCSH-8851-L-113086","AIT - MCSI","2016-10-17T10:00:36","CSAC",null,null,"DO_CESARE","A55_PRO : LIDAR (A55P) : BE FARCU A55P (VRS2)","2016-10-28","Annulé",null,null,"2016-10-25","DR","2016-10-26","FTR"]
["MCSH-6604-L-113172","AIT - MCSI","2016-10-17T12:54:39","CSAC",null,null,"OF_PIECE","P1UO : RADAR GÉN3 (P1UO) : REC : BOITIER ELECTRONIQUE RADAR AV ASS D5.5. (EL1 TMC7) ","2016-10-28","Annulé",null,null,"2016-10-25","DR","2016-10-25","FTR"]
["MCSH-8247-L-111043","AIT - MCDV","2016-08-09","ECHP",null,null,"OF_PIECE","PHEV : _TRAVAUX_CAO : Officialisation d'une pièce FCT capteur point mort application BE/MB6","2016-10-21","Annulé",null,null,"2016-10-26","OTD","2016-11-02","FTR"]
["MCSH-3540-L-112406","AIT - MCSI","2016-09-29T11:03:07","CSAC",null,null,"OF_PIECE","P8X : RADAR GÉN3 (P8X) : REC : BOITIER ELECTRONIQUE RADAR AV ASS D5.5 : OCM sur P8x€ & CH EL1 F10/2017","2016-10-28","Annulé",null,null,"2016-10-26","DR","2016-11-02","FTR"]
["MCSH-8247-L-111044","AIT - MCDV","2016-08-09","ECHP",null,null,"OF_PIECE","PHEV : _TRAVAUX_CAO : Officialisation d'une pièce  FCT : Capteur point mort application BV ML ","2016-10-28","Annulé",null,null,"2016-10-26","OTD","2016-11-02","FTR"]
["MCSH-7154-L-98455","AIT - MCSI","2015-10-26T09:16:03","CSAC",null,null,"DO_CESARE","P1UO : CVM (P1UO) : BE CVM Gen 2 Niveau 3 VAEB SW6 pour stade VRSUT","2016-10-30","Annulé",null,null,"2016-10-26","OTD","2016-10-26","FTR"]
["MCSH-7154-L-111184","AIT - MCSI","2016-08-18T10:36:48","CSAC",null,null,"OF_PIECE","P1UO : CVM (P1UO) : VRSUT: REC CVM VAEB SW6","2016-10-30","Annulé",null,null,"2016-10-26","OTD","2016-11-04","FTR"]
["MCSH-8847-L-112969","EST - MCSI","2016-10-13T13:17:42","HD2C",null,null,"DO_FETE","MODULE_EE09 : TNB (Tous types) : FETE transmise au fournisseur\r\nEvolution Sw « clignotement témoins airbag » ","2016-09-16","Annulé","2016-10-31",null,"2016-10-27","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-6825-L-112421","AIT - MCSI","2016-09-29T01:35:07","CSAC",null,null,"OF_PIECE","B78_mi_vie : RADAR GÉN3 (B78 MV) : REC : BOITIER ELECTRONIQUE RADAR AV ASS D5.5 pour F10/2017","2016-10-28","Annulé",null,null,"2016-10-27","DR","2016-11-28","ACCEPTE_DEFAUT"]
["MCSH-7362-L-112442","AIT - MCSI","2016-09-29T04:12:28","CSAC",null,null,"OF_PIECE","C84_Chine : RADAR GÉN3 (C84) : REC : BOITIER ELECTRONIQUE RADAR AV ASS D5.5 pour EL1","2016-10-28","Annulé",null,null,"2016-10-27","DR","2016-10-27","FTR"]
["MCSH-6206-L-81190","EST - MCSI","2014-12-19T13:42:16","EACC",null,null,"VAL_ANA_PT_FNR","B618,B81,B8_Mi_Vie,MODULE_CPE09,W2_VS : RETRO_EXT : Analyse Plan De Test FNR","2015-09-01","Annulé","2016-10-28","Retard fournisseur","2016-10-28","OTD","2016-11-02","FTR"]
["MCSH-6206-L-85655","EST - MCSI","2015-03-03T11:02:17","EACC",null,null,"DO_CCA_VAL","B618,B81,B8_Mi_Vie,MODULE_CPE09,W2_VS : RETRO_EXT : Fiche CCA phase 3 (validation et process)\r\n","2016-04-18","Annulé","2016-10-31","Retard fournisseur","2016-10-28","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-6206-L-85656","EST - MCSI","2015-03-03T11:02:17","EACC",null,null,"DO_INC_VALID","B618,B81,B8_Mi_Vie,MODULE_CPE09,W2_VS : RETRO_EXT : Incontournables partie validation","2016-04-18","Annulé","2016-10-31","Retard fournisseur","2016-10-28","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-8482-L-103584","EST - MCSI","2016-02-18T16:58:49","ELAC",null,null,"DO_PEPP","_DMTRless_ELAC : TDC_RFTA_CH/RF  : PEPP 2 Industrialisation","2016-05-30","Annulé","2016-11-11","Retard fournisseur","2016-10-28","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-6206-L-81198","EST - MCSI","2014-12-19T13:42:16","EACC",null,null,"VAL_ANA_RAPP_ESSAIS","B618,B81,B8_Mi_Vie,MODULE_CPE09,W2_VS : RETRO_EXT : Analyse CR Essais PV","2016-07-29","Annulé","2016-10-28","Retard fournisseur","2016-10-28","OTD","2016-11-02","FTR"]
["MCSH-8480-L-103580","EST - MCSI","2016-02-18T16:43:18","ELAC",null,null,"DO_PEPP","_DMTRless_ELAC : PULSEUR : PEPP 2 Industrialisation","2016-09-15","Annulé","2016-10-28","Retard fournisseur","2016-10-28","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-5616-L-107306","EST - MCSI","2016-04-29T17:34:09","ELAC",null,null,"DO_DIVERS","_METIER : LDA / référentiel technique CLIM : Création PMR générique pour ELAC","2016-09-30","Annulé","2016-10-28","Retard fournisseur","2016-10-28","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-4192-L-109194","AIT - MCSI","2016-06-27T10:27:42","CSAC",null,null,"OF_PIECE","X81_Chine : CVM (X81_Chine) : Vie série (F03/2017): reconduction CVM niv2 D5.3","2016-10-28","Annulé","2016-10-29",null,"2016-10-28","OTD","2016-11-07","FTR"]
["MCSH-3040-L-109338","AIT - MCSI","2016-06-30T14:12:14","CSAC",null,null,"OF_CAL","K0 : CVM (K0) : (F10/2017): Officialisation CAL CVM niv2 D5.3","2016-10-28","Annulé",null,null,"2016-10-28","OTD","2016-11-07","FTR"]
["MCSH-3036-L-110634","AIT - MCSI","2016-07-29T08:48:27","CSAC",null,null,"DO_CDCI_BILAN","B751_3_4_MV,B78_mi_vie,B81_Chine_Fenêtre_VS,C84_Chine,G95_PH2,K0,MODULE_EE02,P1UO,P84_Chine,P87_Chine,P8X,T9_MV,X81_Chine : RADAR GÉN3 : Synthèses d'avancement de toutes les implantation Radar / Fichier de pilotage interne et avec fournisseur.","2016-10-28","Annulé",null,null,"2016-10-28","OTD","2016-11-07","FTR"]
["MCSH-3040-L-110713","AIT - MCSI","2016-08-01T10:50:40","CSAC",null,null,"DO_CESARE","K0 : CVM (K0) : (F10/2017): BE CVM niv2 D5.3 ","2016-10-28","Annulé",null,null,"2016-10-28","OTD","2016-11-07","FTR"]
["MCSH-7006-L-111840","AIT - MCSI","2016-09-07","AURA",null,null,"OF_PIECE","B73_Russie : LECTEUR_CD_EXTERNE : Officialisation d'une pièce","2016-10-28","Annulé",null,null,"2016-10-28","OTD","2016-10-12","FTR"]
["MCSH-7147-L-112471","AIT - MCSI","2016-09-29T05:32:57","CSAC",null,null,"OF_PIECE","G95_PH2 : RADAR GÉN3 (G95Ph2) : REC BOITIER ELECTRONIQUE RADAR AV ASS D5.5 EL F11/2017 (TBC by PEPP)","2016-10-28","Annulé",null,null,"2016-10-28","DR","2016-11-07","FTR"]
["MCSH-3039-L-113520","AIT - MCSI","2016-10-26T15:44:09","CSAC",null,null,"DO_TDB","A88,A88_Chine,B618,B751_3_4_MV,B78_mi_vie,B81_Chine_Fenêtre_VS,C84_Chine,F3,G95_PH2,K0,K0_Russie,MODULE_EE02,P1MO,P1UO,P84_Chine,P87_Chine,P8X,T9_MV,X81_Chine : CVM : Création ou mise à jour d'un tableau de bord","2016-10-31","Annulé",null,null,"2016-10-28","DR","2016-11-07","FTR"]
["MCSH-3533-L-112247","AIT - MCSI","2016-09-22T17:00:24","CSAC",null,null,"OF_CAL","P8X : CVM (P8) : P87: CAL VAEB SW6x","2016-12-31","Annulé",null,null,"2016-10-28","OTD","2016-11-07","FTR"]
["MCSH-4127-L-85622","EST - MCSI","2015-03-02T16:00:52","EACC",null,null,"DO_CCA_VAL","C84_Europe,MODULE_CPE09,P1UO,P8X,X74E : RETRO_EXT : Fiche CCA phase 3 (validation et process)\r\n","2017-02-06","Annulé",null,null,"2016-10-28","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-5267-L-112153","AIT - MCSI","2016-09-16T15:47:15","AURA",null,null,"OF_PIECE","B7_Mi_Vie : LECTEUR_CD_EXTERNE (SANS FACADE) : B75\r\nOfficialisation d'une pièce, Lecteur CD sans façade DMTLESS","2016-10-30","Annulé",null,null,"2016-10-30","OTD","2016-09-30","FTR"]
["MCSH-8247-L-112154","AIT - MCDV","2016-09-16","ECHP",null,null,"OF_PIECE","PHEV : _TRAVAUX_CAO : Officialisation d'une pièce","2016-10-30","Annulé","2016-10-29",null,"2016-10-30","OTD","2016-11-02","FTR"]
["MCSH-5267-L-112184","AIT - MCSI","2016-09-20T10:01:37","AURA",null,null,"OF_PIECE","B7_Mi_Vie : LECTEUR_CD_EXTERNE (SANS FACADE) : B71\r\nOfficialisation d'une pièce, Lecteur CD sans façade DMTLESS","2016-10-30","Annulé",null,null,"2016-10-30","DR","2016-10-05","FTR"]
["MCSH-5751-L-80279","EST - MCSI","2014-12-15T16:46:12","ELAC",null,null,"DO_ETAT_ACCEPT","P8X : TDC AR : Etat acceptation pour VRS1.'=> Contribution R2 pour R1","2015-09-21","Annulé","2016-10-31","Abscence valideur ou expert","2016-10-31","OTD","2016-11-04","FTR"]
["MCSH-3934-L-76575","EST - MCSI","2014-10-08T11:54:21","ELAC",null,null,"DO_ETAT_ACCEPT","P8X : PULSEUR_AR : Etat d'acceptation Produit (pièce R2)","2015-09-30","Annulé","2016-10-31","Abscence valideur ou expert","2016-10-31","OTD","2016-11-04","FTR"]
["MCSH-7156-L-92386","EST - MCSI","2015-06-08T14:47:25","EACC",null,null,"DO_EDS","D34E,R82E,R83E,R83_Chine,X83_Chine,MODULE_CPE09 : RETRO_EXT : Renseigner OPHELIE EDS Tool pour le stade consolidé","2015-11-23","Annulé","2016-11-30","Blocage technique","2016-10-31","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-5751-L-80284","EST - MCSI","2014-12-15T16:46:12","ELAC",null,null,"DO_ETAT_ACCEPT","P8X : TDC AR : Etat acceptation pour VRS2.'=> Contribution R2 pour R1","2015-12-28","Annulé","2016-10-31","Abscence valideur ou expert","2016-10-31","OTD","2016-11-04","FTR"]
["MCSH-7075-L-113603","AIT - MCSI","2016-10-27T05:44:41","CSAC",null,null,"DO_CESARE","T9_MV : RADAR GÉN3 (T9MV) : livraison de tous les BEs T9MV à refaire pour prendre en compte le DOTE refait suite au problème de codif.","2016-11-04","Annulé",null,null,"2016-10-31","DR","2016-11-07","FTR"]
["MCSH-4192-L-111012","AIT - MCSI","2016-08-08T14:27:10","CSAC",null,null,"DO_CESARE","X81_Chine : CVM (X81_Chine) : BE CVM D5.3 (F03/2017)","2016-11-10","Annulé",null,null,"2016-10-31","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7064-L-111182","AIT - MCSI","2016-08-18T10:09:48","CSAC",null,null,"DO_CESARE","P84_Chine : CVM (P84_C) : (VS - F03/2017): BE CVM niv1 & 2 D5.3","2016-11-10","Annulé",null,null,"2016-10-31","OTD","2016-11-07","FTR"]
["MCSH-8735-L-110928","EST - MCSI","2016-08-04T13:47:00","ELAC",null,null,"DO_STD","A9x_Iran,M33_Iran_Full_Speed : SONDE_PRESSION : Spécification Technique Détaillée","2016-11-11","Annulé","2016-10-31",null,"2016-10-31","OTD","2016-12-22","NOT FTR"]
["MCSH-3934-L-76589","EST - MCSI","2014-10-08T11:54:21","ELAC",null,null,"DO_ETAT_ACCEPT","MODULE_HAB06 : PULSEUR_AR : Etat d'acceptation Produit (pièce R2)","2016-11-18","Annulé","2016-11-18",null,"2016-10-31","OTD","2016-11-04","FTR"]
["MCSH-3042-L-112413","AIT - MCSI","2016-09-29T12:02:43","CSAC",null,null,"OF_PIECE","K0 : RADAR GÉN3 (K0) : REC Assemblé Radar Gen 3 D5.5 sur EL1 F10/2017 ","2016-10-28","Annulé","2016-11-02",null,"2016-11-02","DR","2016-11-07","FTR"]
["MCSH-7075-L-78425","AIT - MCSI","2014-11-19T17:00:36","CSAC",null,null,"OF_DOTE","T9_MV : RADAR GÉN3 (T9MV) : DOTE à refaire à cause d'une mauvaise codification des cas d'emplois.","2016-11-04","Annulé",null,null,"2016-11-02","OTD","2016-11-07","FTR"]
["MCSH-7230-L-112129","AIT - MCSI","2016-09-16T12:53:17","CSAC",null,null,"OF_CAL","R83_Chine : RADAR_GÉN4 (R83_Chine) : Officialisation d'une calibration pour stade TI","2016-09-23","Annulé","2016-11-05","Manque donnée d'entrée","2016-11-03","DR","2016-11-07","FTR"]
["MCSH-7366-L-80232","EST - MCSI","2014-12-15T15:05:55","ELPS",null,null,"OF_PIECE","P1UO : SIRENE_LIN_SSCAS,RUPTEUR_CAPOT,MUS2 : OCM MUS pour EL1","2016-10-15","Annulé","2016-11-17","Retard fournisseur","2016-11-03","OTD",null,"FTR"]
["MCSH-7064-L-77070","AIT - MCSI","2014-10-15T10:44:44","CSAC",null,null,"OF_CAL","P84_Chine : CVM (P84_C) : (VS - F03/2017): Calibration CVM Gen 2 D5.3 niveau 1 & 2","2016-11-10","Annulé",null,null,"2016-11-03","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-8302-L-99885","EST - MCSI","2015-12-07T14:46:36","ELPS",null,null,"RT_HW","A9X_F_05_17 : PROJ : Bilan LayOut - Verif CCA et EMC","2016-02-19","Annulé","2016-11-14","Manque donnée d'entrée","2016-11-04","OTD","2016-12-29","RR"]
["MCSH-8302-L-99889","EST - MCSI","2015-12-07T14:46:36","ELPS",null,null,"VAL_ANA_PT_FNR","A9X_F_05_17 : PROJ : Analyse Plan De Test FNR","2016-02-19","Annulé","2016-11-14","Livrable affecté en retard","2016-11-04","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-8302-L-99884","EST - MCSI","2015-12-07T14:46:36","ELPS",null,null,"VAL_ANA_PT_FNR","A9X_F_05_17 : PROJ : Analyse Plan De Test FNR","2016-02-20","Annulé","2016-11-14","Manque donnée d'entrée","2016-11-04","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7953-L-109349","AIT - MCSI - NAC","2016-06-30T18:05:55","IVI",null,null,"OF_PIECE","MODULE_EE07 : NAC Wave 3 : Officialisation module HW C SW V3 (variante pour A55P)","2016-06-10","Annulé","2016-11-11",null,"2016-11-04","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-8304-L-99945","EST - MCSI","2015-12-07T16:49:28","ELPS",null,null,"VAL_ANA_PT_FNR","A9X_F_05_17 : PROJ (_STT) : Analyse Plan De Test FNR","2016-08-12","Annulé","2016-11-14","Livrable affecté en retard","2016-11-04","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-3036-L-110520","AIT - MCSI","2016-07-29T08:42:47","CSAC",null,null,"SYN_ALTIS ","B751_3_4_MV,B78_mi_vie,B81_Chine_Fenêtre_VS,C84_Chine,G95_PH2,K0,MODULE_EE02,P1UO,P84_Chine,P87_Chine,P8X,T9_MV,X81_Chine : RADAR GÉN3 : Gestion Hebdomadaire Altis\r\n","2016-11-07","Annulé",null,null,"2016-11-07","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7066-L-109515","AIT - MCSI","2016-07-06T09:53:00","CSAC",null,null,"OF_CAL","G95_PH2 : CVM (G95 Ph2) : (F03/2017): Officialisation CAL CVM niv2 D5.3","2016-12-30","Annulé",null,null,"2016-11-07","OTD","2016-11-07","FTR"]
["MCSH-7186-L-92247","EST - MCSI","2015-06-08T09:28:39","EACC",null,null,"DO_EDS","B618,R82E,R83E : POMPES_LV_LP : Renseigner OPHELIE EDS Tool pour le stade consolidé","2015-11-23","Annulé","2016-11-11","Retard fournisseur","2016-11-08","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7154-L-113023","AIT - MCSI","2016-10-13T17:32:09","CSAC",null,null,"OF_DOTE","P1UO : CVM (P1UO) : Mise à jour des cas d'emploi sur DOTE","2016-10-30","Annulé","2016-11-08",null,"2016-11-08","DR","2016-11-09","FTR"]
["MCSH-7154-L-113024","AIT - MCSI","2016-10-13T17:32:24","CSAC",null,null,"OF_CAL","P1UO : CVM (P1UO) : Mise à jour des cas d'emploi sur CAL","2016-10-30","Annulé","2016-11-07",null,"2016-11-08","NDR","2016-11-10","FTR"]
["MCSH-8052-L-106719","EST - MCSI","2016-04-18T14:44:35","EACC",null,null,"DO_EDS","D34E,P21,P21_DMOA,P23_DMOA,P24E : POMPES_LV_LP : Renseigner OPHELIE EDS Tool pour le stade consolidé","2016-11-08","Annulé","2016-11-11","Retard fournisseur","2016-11-08","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-8717-L-109938","AIT - MCSI","2016-07-21T17:20:33","CSAC",null,null,"OF_DOTE","X74_Chine : CVM (X74_Chine) : Pour Stade DFE TI (B2)","2016-11-10","Annulé","2016-11-30",null,"2016-11-08","OTD","2016-11-09","FTR"]
["MCSH-7362-L-96411","AIT - MCSI","2015-09-08T09:54:00","CSAC",null,null,"DO_CESARE","C84_Chine : RADAR GÉN3 (C84) : Livraison BE VRS UT (D5.4)","2016-11-18","Annulé",null,null,"2016-11-08","OTD","2016-11-18","FTR"]
["MCSH-7683-L-114070","AIT - MCSI","2016-11-10T14:52:13","CSAC",null,null,"DO_BE_CESARE","R83E : VISIO_PARK (R83E) : Création /Mise à jour BE CESARE.Livraison BE CESARE ( Mise à jour des articles HW et SW pour être compatibles avec la CVP LH et DOP/CPK VALEO)","2016-11-10","Annulé",null,null,"2016-11-09","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-6648-L-103096","EST - MCSI","2016-02-11T05:39:18","EACC",null,null,"OF_PIECE","P1MO : JDV (P1MO) : Officialisation des JDV avec plip coloré","2016-11-11","Annulé","2016-07-31",null,"2016-11-09","OTD","2016-11-18","FTR"]
["MCSH-7774-L-113866","EST - MCSI","2016-11-08T11:39:33","EACC",null,null,"DO_BE_CESARE","K9 : AVE (K9) : Création /Mise à jour BE CESARE","2016-11-18","Annulé","2016-11-09",null,"2016-11-09","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-3895-L-58646","EST - MCSI","2013-11-18T10:51:07","EACC",null,null,"VAL_BILAN","K0,MODULE_CE_MDT : SERRURE_PBAR : Phase=PV|","2015-10-30","Annulé","2016-11-18","Retard fournisseur","2016-11-10","OTD","2016-11-18","FTR"]
["MCSH-3895-L-58645","EST - MCSI","2013-11-18T10:51:07","EACC",null,null,"VAL_ANA_RAPP_ESSAIS","K0,MODULE_CE_MDT : SERRURE_PBAR : Phase=PV FNR|","2015-11-30","Annulé","2016-11-18","Retard fournisseur","2016-11-10","OTD","2016-11-18","FTR"]
["MCSH-8246-L-112259","AIT - MCDV","2016-09-23","HDTC",null,null,"OF_PIECE","_TOUS : _TRAVAUX_CAO : Officialisation d'une pièce","2016-10-22","Annulé","2016-11-11","Erreur Metier (RCD, Impl., Concept…)","2016-11-10","DR","2016-11-09","FTR"]
["MCSH-8847-L-114074","EST - MCSI","2016-11-10T16:12:54","HD2C",null,null,"DO_BE_CESARE","MODULE_EE09 : TNB (Tous types) : Création /Mise à jour BE CESARE pour D34","2016-11-17","Annulé",null,null,"2016-11-10","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-7362-L-96412","AIT - MCSI","2015-09-08T09:54:00","CSAC",null,null,"OF_CAL","C84_Chine : RADAR GÉN3 (C84) : Calibration pour VRS2 (D5.4)","2016-11-18","Annulé",null,null,"2016-11-10","OTD","2016-11-18","FTR"]
["MCSH-8847-L-114072","EST - MCSI","2016-11-10T15:15:56","HD2C",null,null,"OF_PIECE","MODULE_EE09 : TNB (Tous types) : Officialisation du TNB : Correction du Pb de nomenclature du TNB sur le projet B71 (Altis 7165294 ); pour EL1 de la F05/2017.","2016-12-30","Annulé",null,null,"2016-11-10","OTD","2016-12-12","ACCEPTE_DEFAUT"]
["MCSH-5751-L-80283","EST - MCSI","2014-12-15T16:46:12","ELAC",null,null,"DO_EDS","P8X : TDC AR : Renseigner OPHELIE EDS Tool pour le stade clôturé","2016-01-11","Annulé","2016-11-11","Livrable affecté en retard","2016-11-11","OTD","2016-11-16","FTR"]
["MCSH-8480-L-103577","EST - MCSI","2016-02-18T16:43:18","ELAC",null,null,"DO_ALTIS","_DMTRless_ELAC : PULSEUR : Mise à jour ALTIS (EE ou Qualité)","2016-07-15","Annulé","2016-11-11","Retard fournisseur","2016-11-11","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-8007-L-114087","EST - MCSI","2016-11-11T13:00:03","HD2C",null,null,"OF_CAL","MODULE_EE09 : MATTC (SW3.0) : Officialisation d'une calibration \r\n MATT_c  sw2.8 sur W2 chine  Adaptation NAC/RCC ALTIS\r\n6687229 CALE SW2.8)\r\n","2016-11-13","Annulé",null,null,"2016-11-11","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-7882-L-94670","EST - MCSI","2015-07-22T11:22:52","ELPS",null,null,"OF_PIECE","C84_Chine : SIRENE_LIN_SSCAS,RUPTEUR_CAPOT,MUS2 (Réimport Europe) : DEF Cheminement faisceau pour DFNu","2016-06-26","Annulé","2016-11-18","Abscence valideur ou expert","2016-11-14","OTD","2016-12-15","ACCEPTE_DEFAUT"]
["MCSH-7882-L-94671","EST - MCSI","2015-07-22T11:22:52","ELPS",null,null,"OF_PIECE","C84_Chine : SIRENE_LIN_SSCAS,RUPTEUR_CAPOT,MUS2 (Réimport Europe) : DEF Rupteur Capot pour DFNu","2016-06-27","Annulé","2016-12-01","Abscence valideur ou expert","2016-11-14","OTD","2016-12-15","ACCEPTE_DEFAUT"]
["MCSH-7987-L-105797","EST - MCSI","2016-04-01T11:31:03","ELPS",null,null,"RT_HW","D34E : FEU_AV : Bilan LayOut - Verif CCA et EMC","2016-10-03","Annulé","2016-11-14","Evolution donnée d'entrée","2016-11-14","OTD","2016-11-30","FTR"]
["MCSH-7075-L-114290","AIT - MCSI","2016-11-16T04:35:43","CSAC",null,null,"OF_CAL","T9_MV : RADAR GÉN3 (T9MV) : MAJ des cas d'emplois de 2 des CALs D5.4 suite à l'évoliution LCDV T9 : Moteur EP6FADTX ald EP6FADTXD","2016-11-14","Annulé",null,null,"2016-11-14","DR","2016-11-18","FTR"]
["MCSH-7270-L-88215","AIT - MCSI","2015-04-09T17:41:09","CSAC",null,null,"DO_CESARE","P1UO : VISIO_PARK (P1UO) : Création de référence/Mise à jour CESARE C5","2016-11-15","Annulé",null,null,"2016-11-14","OTD","2016-11-16","FTR"]
["MCSH-7813-L-102077","AIT - MCSI","2016-01-20T17:53:32","SWES",null,null,"VAL_ANA_PT_FNR","_QUALITE,HAB10 : CSV VALEO (dérive qualité - renouvellement outillage) : Analyse Plan De Test FNR","2016-09-09","Annulé","2016-11-15","Retard fournisseur","2016-11-15","OTD","2016-12-07","FTR"]
["MCSH-5267-L-111836","AIT - MCSI","2016-09-07T16:42:24","AURA",null,null,"OF_PIECE","P8X : LECTEUR_CD_EXTERNE (SANS FACADE) : P87 -Officialisation d'une pièce","2016-09-30","Annulé",null,null,"2016-11-15","NDR","2016-12-16","ACCEPTE_DEFAUT"]
["MCSH-7154-L-112972","AIT - MCSI","2016-10-13T13:22:58","CSAC",null,null,"OF_PIECE","P1UO : CVM (P1UO) : Mise à jour des cas d'emploi sur CVM niv2 D5.3","2016-10-30","Annulé","2016-11-18",null,"2016-11-15","DR","2016-11-16","FTR"]
["MCSH-7270-L-88216","AIT - MCSI","2015-04-09T17:41:09","CSAC",null,null,"OF_CAL","P1UO : VISIO_PARK (P1UO) : Calibration pour VRS2","2016-11-15","Annulé",null,null,"2016-11-15","OTD","2016-11-16","FTR"]
["MCSH-7520-L-114068","AIT - MCSI","2016-11-10T14:49:45","CSAC",null,null,"OF_PIECE","K9 : CVP (K9) : Officialisation d'une pièce. Suppression variante caméra AVR et AVP pour K9, car livrées dans des assemblées avec les supports / les enjos plaque,","2016-11-18","Annulé",null,null,"2016-11-15","DR","2016-12-16","ACCEPTE_DEFAUT"]
["MCSH-7990-L-94690","AIT - MCSI","2015-07-22T13:17:14","CSAC",null,null,"DO_CESARE","P87_Chine : RADAR GÉN3 (P87C) : Livraison BE D5.4 EL1","2016-11-28","Annulé",null,null,"2016-11-15","OTD","2016-11-18","FTR"]
["MCSH-6617-L-110216","AIT - MCSI","2016-07-26T14:51:45","CSAC",null,null,"OF_PIECE","X74E : CVM (CVM3 ADAS vague 2) : Officialisation des 2D Fournisseurs C5","2016-11-16","Annulé","2016-11-18",null,"2016-11-16","OTD","2016-12-19","ACCEPTE_DEFAUT"]
["MCSH-925-L-113607","EST - MCSI","2016-10-27T05:49:02","ELAC",null,null,"DO_DIVERS","_METIER,_QUALITE : _QUALITE : Indicateurs qualité ELAC de Novembre (données de Septembre et Octobre)","2016-11-16","Annulé",null,null,"2016-11-16","DR","2016-12-29","RR"]
["MCSH-8869-L-113647","AIT - MCSI","2016-11-03T10:15:33","AURA",null,null,"OF_PIECE","MODULE_EE12 : LECTEUR_CD_EXTERNE : Officialisation d'une pièce - Module EE12 avec façade ECOTECH","2016-11-25","Annulé",null,null,"2016-11-16","DR","2016-11-23","FTR"]
["MCSH-7953-L-113923","AIT - MCSI - NAC","2016-11-09T22:46:52","IVI",null,null,"OF_PIECE","MODULE_EE07 : NAC Wave 3 : Officialisation module HW D SW V4","2016-09-30","Annulé","2016-11-25",null,"2016-11-17","DR","2016-12-19","ACCEPTE_DEFAUT"]
["MCSH-4124-L-112176","AIT - MCSI","2016-09-19T03:44:25","CSAC",null,null,"OF_PIECE","X74E : CVM (X74E) : Reconduction des nouvelles références C5 sur X74 (variantes 1, 2 et 3)","2016-11-04","Annulé","2016-11-23","Retard fournisseur","2016-11-17","OTD","2016-11-23","FTR"]
["MCSH-6771-L-108358","AIT - MCSI","2016-05-31T10:58:14","CSAC",null,null,"DO_FETE","_VS : AVR : Traitement de la FETE n°1 de modification du sertissage du faisceau de la caméra AVR","2016-11-17","Annulé",null,null,"2016-11-17","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7683-L-114069","AIT - MCSI","2016-11-10T14:51:47","CSAC",null,null,"OF_PIECE","R83E : VISIO_PARK (R83E) : Officialisation d'une pièce. REC ECU VP2 Module ADAS Vague 2 sur R83E","2016-11-30","Annulé",null,null,"2016-11-17","DR","2016-12-16","FTR"]
["MCSH-8877-L-114071","AIT - MCSI","2016-11-10T14:57:31","CSAC",null,null,"OF_PIECE","C84_Europe : VISIO_PARK (C84 E) : Officialisation d'une pièce. REC ECU VP2 Module ADAS Vague 2 sur C84E","2016-12-08","Annulé",null,null,"2016-11-17","DR","2016-12-19","ACCEPTE_DEFAUT"]
["MCSH-8650-L-108350","EST - MCSI","2016-05-31T07:46:35","ELAC",null,null,"DO_PRESENTATION","_VS_Clim : FAISCEAU : Présentation","2016-05-31","Annulé","2016-11-18",null,"2016-11-18","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-7911-L-112126","AIT - MCSI","2016-09-16T11:39:45","CSAC",null,null,"OF_CAL","D34E : RADAR_GÉN4 (D34E) : Officialisation d'une calibration pour stade TI","2016-11-04","Annulé","2016-11-30","Retard fournisseur","2016-11-21","OTD","2016-12-05","FTR"]
["MCSH-3533-L-114369","AIT - MCSI","2016-11-18T11:30:36","CSAC",null,null,"DO_CESARE","P8X : CVM (P8) : P84 (F02/2017): Mise à jour BE SW6x pour VAEB 0.9g full breaking suite à la MAJ CAL","2016-11-25","Annulé",null,null,"2016-11-21","DR","2016-11-24","FTR"]
["MCSH-7990-L-94691","AIT - MCSI","2015-07-22T13:17:14","CSAC",null,null,"OF_CAL","P87_Chine : RADAR GÉN3 (P87C) : CAL D5.4 EL1","2016-11-28","Annulé",null,null,"2016-11-21","OTD","2016-11-21","FTR"]
["MCSH-7147-L-112478","AIT - MCSI","2016-09-29T05:52:06","CSAC",null,null,"DO_CESARE","G95_PH2 : RADAR GÉN3 (G95Ph2) : Livraison BE CESARE D5.4 pour MDL","2016-12-01","Annulé",null,null,"2016-11-21","OTD","2016-11-21","FTR"]
["MCSH-7987-L-105799","EST - MCSI","2016-04-01T11:31:03","ELPS",null,null,"DO_FC_TI","D34E : FEU_AV : Fiches composants pour SDP TI","2016-04-21","Annulé","2016-11-22",null,"2016-11-22","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-7065-L-82281","AIT - MCSI","2015-01-14T13:01:09","CSAC",null,null,"OF_DOTE","R83E : CVM (R83E) : Pour Stade OCM VRS1 (C4)","2016-11-18","Annulé","2016-11-30","Retard fournisseur","2016-11-22","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-3533-L-113878","AIT - MCSI","2016-11-08T04:57:39","CSAC",null,null,"OF_CAL","P8X : CVM (P8) : P84 (F02/2017): CAL VAEB SW6e","2016-11-25","Annulé",null,null,"2016-11-22","DR","2016-11-24","FTR"]
["MCSH-7147-L-112477","AIT - MCSI","2016-09-29T05:49:36","CSAC",null,null,"OF_CAL","G95_PH2 : RADAR GÉN3 (G95Ph2) : CAL D5.4 pour MDL","2016-12-01","Annulé",null,null,"2016-11-22","OTD","2016-11-29","FTR"]
["MCSH-7066-L-110685","AIT - MCSI","2016-07-29T13:48:08","CSAC",null,null,"OF_PIECE","G95_PH2 : CVM (G95 Ph2) : F03/2017: Reconduction de la CVM niv2 D5.3","2016-12-10","Annulé",null,null,"2016-11-22","OTD","2016-11-23","FTR"]
["MCSH-7358-L-106689","EST - MCSI","2016-04-18T09:50:41","ELPS",null,null,"DO_FC_TI","D34E : FEUX_AR : Fiches composants pour SDP TI","2016-05-15","Annulé","2016-11-23",null,"2016-11-23","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-7358-L-106696","EST - MCSI","2016-04-18T09:50:41","ELPS",null,null,"RT_MECA","D34E : FEUX_AR : Revue Technique de Conception Préliminaire Mécanique ","2016-10-03","Annulé","2016-11-28","Retard fournisseur","2016-11-23","OTD","2016-11-30","FTR"]
["MCSH-7343-L-111597","AIT - MCSI","2016-09-01T15:51:33","CSAC",null,null,"OF_PIECE","K9 : CVM (K9) : recondiction CVM C5.1 sur K9 pour stade VRS ","2016-11-25","Annulé",null,null,"2016-11-23","OTD","2016-12-26","ACCEPTE_DEFAUT"]
["MCSH-5893-L-114418","AIT - MCSI","2016-11-22T10:11:11","CSAC",null,null,"OF_CAL","P1MO : CVM (A88,P1MO) : P1MO: Calibrations CVM2 niv1 D5.3 et VAEB SW6d pour stade MVBns","2016-11-25","Annulé",null,null,"2016-11-24","DR","2016-12-05","FTR"]
["MCSH-5893-L-114419","AIT - MCSI","2016-11-22T10:14:22","CSAC",null,null,"OF_CAL","A88 : CVM (A88,P1MO) : A88: Calibrations CVM2 niv1 D5.3 et VAEB SW6d pour stade PPVV3","2016-11-25","Annulé",null,null,"2016-11-24","DR","2016-12-05","FTR"]
["MCSH-5893-L-114658","AIT - MCSI","2016-11-23T10:13:32","CSAC",null,null,"DO_CESARE","P1MO : CVM (A88,P1MO) : P1MO (DàD/DàG): BE niv1 et VAEB à partir du stade MVBNs","2016-11-25","Annulé",null,null,"2016-11-24","DR","2016-12-05","FTR"]
["MCSH-5893-L-114659","AIT - MCSI","2016-11-23T10:14:33","CSAC",null,null,"DO_CESARE","A88 : CVM (A88,P1MO) : A88 (DàD/DàG): BE niv1 et VAEB à partir du stade PPV3","2016-11-25","Annulé",null,null,"2016-11-24","DR","2016-12-05","FTR"]
["MCSH-8077-L-114706","AIT - MCSI","2016-11-23T04:14:41","CSAC",null,null,"OF_CAL","C84_Europe : RADAR_GÉN4 (C84_Export) : Calibration pour TI","2016-12-02","Annulé",null,null,"2016-11-24","DR","2016-11-25","FTR"]
["MCSH-8827-L-112841","AIT - MCSI","2016-10-10T17:08:20","AURA",null,null,"OF_PIECE","P8X : LECTEUR_CD_EXTERNE (AVEC FACADE) : Officialisation d'une pièce","2016-10-28","Annulé",null,null,"2016-11-25","NDR","2016-11-16","FTR"]
["MCSH-7467-L-81930","EST - MCSI","2015-01-09T13:59:43","ELPS",null,null,"OF_DOTE","R83E : SIRENE_LIN_SSCAS,RUPTEUR_CAPOT,MUS2 : DOTE pour VRS1","2016-11-18","Annulé","2016-11-30","Blocage technique","2016-11-25","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-4288-L-111073","EST - MCSI","2016-08-10","HD2C",null,null,"VAL_ANA_RAPP_ESSAIS","A9 : MATTC : Analyse rapports d'essais FNR ou PSA.","2016-11-25","Annulé",null,null,"2016-11-25","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-5267-L-113619","AIT - MCSI","2016-10-28T09:50:57","AURA",null,null,"OF_PIECE","W2_R : LECTEUR_CD_EXTERNE (SANS FACADE) : Officialisation d'une pièce - ECOTECH","2016-11-25","Annulé",null,null,"2016-11-25","DR","2016-11-16","FTR"]
["MCSH-5234-L-114073","AIT - MCSI","2016-11-10T15:49:58","AURA",null,null,"OF_PIECE","A9 : LECTEUR_CD_EXTERNE (AVEC FACADE) : Reconduction d'une pièce - ECOTECH","2016-11-25","Annulé",null,null,"2016-11-25","DR","2016-11-30","FTR"]
["MCSH-5234-L-114088","AIT - MCSI","2016-11-11T15:57:46","AURA",null,null,"OF_PIECE","A94 : LECTEUR_CD_EXTERNE (AVEC FACADE) : Officialisation d'une pièce - ECOTECH","2016-11-25","Annulé",null,null,"2016-11-25","DR","2016-11-30","FTR"]
["MCSH-5267-L-114134","AIT - MCSI","2016-11-14T18:48:18","AURA",null,null,"OF_PIECE","MODULE_EE12 : LECTEUR_CD_EXTERNE (SANS FACADE) : Officialisation du lecteur CD sans façade - ECOTECH","2016-11-25","Annulé",null,null,"2016-11-25","DR","2016-11-30","FTR"]
["MCSH-5267-L-114177","AIT - MCSI","2016-11-15T17:38:02","AURA",null,null,"OF_PIECE","B7_Mi_Vie : LECTEUR_CD_EXTERNE (SANS FACADE) : Reconduction d'une pièce sur B7 - Lecteur CD sans façade ECOTECH","2016-11-25","Annulé",null,null,"2016-11-25","DR","2016-11-30","FTR"]
["MCSH-5234-L-114178","AIT - MCSI","2016-11-15T18:06:02","AURA",null,null,"OF_PIECE","B78 : LECTEUR_CD_EXTERNE (AVEC FACADE) : Reconduction d'une pièce - Lecteur CD avec façade ECOTECH","2016-11-25","Annulé",null,null,"2016-11-25","DR","2016-11-30","FTR"]
["MCSH-8518-L-107089","EST - MCSI","2016-04-25T10:57:19","ELAC",null,null,"DO_INC_SPEC","CMP,P21_AMLAT,P21_DMOA,P23_AMLAT,P23_CHINE,P23_DMOA,P24E,P24_AMLAT,P24_CHINE : GRPE_CLIM : Incontournables partie spécification : Remplir le document en accord avec le CDC","2016-11-25","Annulé",null,null,"2016-11-25","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-5616-L-113879","EST - MCSI","2016-11-09T08:17:25","ELAC",null,null,"DO_DIVERS","_METIER : LDA / référentiel technique CLIM : Traduction en anglais du nouveau scénario RFQ ELAC (mis à jour par SOAB)","2016-11-25","Annulé",null,null,"2016-11-25","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-8310-L-114396","EST - MCSI","2016-11-21T13:13:26","EACC",null,null,"OF_PIECE","C84_Europe : JDV (Rec C84E) : Officialisation d'une pièce AVM DàD","2016-12-15","Annulé",null,null,"2016-11-25","DR","2016-12-26","ACCEPTE_DEFAUT"]
["MCSH-7363-L-114401","AIT - MCSI","2016-11-21T15:08:38","CSAC",null,null,"OF_CAL","C84_Chine : CVM (C84) : Calibration CVM2 niv2 D5.3 & VAEB SW6d pour VRS2","2016-11-30","Annulé",null,null,"2016-11-27","DR","2016-12-05","FTR"]
["MCSH-208-L-112606","EST - MCSI","2016-10-05T14:45:09","EACC",null,null,"DO_PRESENTATION","_METIER,_GLS : RETRO_EXT,RETRO_INT_ELEC : processus EDS à appliquer sur les RETRO_EXT","2016-11-28","Annulé",null,null,"2016-11-28","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-2509-L-114130","AIT - MCSI","2016-11-14T17:01:33","SWES",null,null,"OF_PIECE","MODULE_HAB10 : COM2005_EV3 (Delphi : Suivi Vie Série) : Officialisation d'une pièce - MAJ couple de serrage du COM2005DELPHI","2016-11-28","Annulé",null,null,"2016-11-28","DR","2016-12-07","FTR"]
["MCSH-3036-L-110635","AIT - MCSI","2016-07-29T08:48:27","CSAC",null,null,"DO_CDCI_BILAN","B751_3_4_MV,B78_mi_vie,B81_Chine_Fenêtre_VS,C84_Chine,G95_PH2,K0,MODULE_EE02,P1UO,P84_Chine,P87_Chine,P8X,T9_MV,X81_Chine : RADAR GÉN3 : Synthèses d'avancement de toutes les implantation Radar / Fichier de pilotage interne et avec fournisseur.","2016-11-30","Annulé",null,null,"2016-11-28","OTD","2016-11-29","FTR"]
["MCSH-8378-L-101789","EST - MCSI","2016-01-18T13:36:05","ELPS",null,null,"OF_DOTE","A55_PRO : SIRENE_LIN_SSCAS,RUPTEUR_CAPOT,MUS_LIN,SIRENE_LIN_CAS : DOTE MUS1 pour TI (calibration générique)","2016-11-30","Annulé",null,null,"2016-11-29","OTD","2016-12-08","FTR"]
["MCSH-7989-L-114397","AIT - MCSI","2016-11-21T13:33:51","CSAC",null,null,"OF_CAL","P87_Chine : CVM (P87C) : Officialisation des calibrationAs CVM niv1 & 2 D5.3 (EL0-EL1)","2016-11-30","Annulé",null,null,"2016-11-29","DR","2016-12-05","FTR"]
["MCSH-6555-L-65045","EST - MCSI","2014-02-21T14:19:28","ELAC",null,null,"SDF_NS","A88,MODULE_HAB05,P1MO : GRPE_CLIM : Note de Synthèse SDF organe","2015-02-04","Annulé","2016-11-30","Blocage technique","2016-11-30","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7345-L-111334","AIT - MCSI","2016-08-25T11:17:03","CSAC",null,null,"OF_DOTE","R83_Chine : CVM (R83C) : Pour Stade DFE TI (B2)","2016-11-04","Annulé","2016-12-31","Abscence valideur ou expert","2016-11-30","OTD","2016-12-07","FTR"]
["MCSH-7953-L-114638","AIT - MCSI - NAC","2016-11-22T18:08:18","IVI",null,null,"OF_PIECE","X74E : NAC Wave 3 : Officialisation Rec NAC WAVE 3 pour projet X74","2016-11-25","Annulé","2016-12-02",null,"2016-11-30","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-7858-L-114695","EST - MCSI","2016-11-23T15:51:35","ELAC",null,null,"DO_DIVERS","D41 : BCC,GRPE_CLIM : Mettre à jour synthèse CTP NEA","2016-11-29","Annulé","2016-11-30",null,"2016-11-30","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-6555-L-65075","EST - MCSI","2014-02-21T14:19:28","ELAC",null,null,"DO_INC_VALID","A88,MODULE_HAB05,P1MO : GRPE_CLIM : Incontournable après validation","2016-11-30","Annulé",null,null,"2016-11-30","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-8378-L-101817","EST - MCSI","2016-01-18T13:39:59","ELPS",null,null,"OF_DOTE","A55_PRO : SIRENE_LIN_SSCAS,RUPTEUR_CAPOT,MUS_LIN,SIRENE_LIN_CAS : DOTE pour TI","2016-11-30","Annulé",null,null,"2016-11-30","OTD","2016-12-08","FTR"]
["MCSH-5616-L-114470","EST - MCSI","2016-11-22T12:20:19","ELAC",null,null,"DO_DIVERS","_METIER : LDA / référentiel technique CLIM : MàJ Template roadmap ELAC","2016-11-30","Annulé",null,null,"2016-11-30","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-3039-L-112327","AIT - MCSI","2016-09-27T10:06:59","CSAC",null,null,"DO_CDCI_BILAN","A88,A88_Chine,B618,B751_3_4_MV,B78_mi_vie,B81_Chine_Fenêtre_VS,C84_Chine,F3,G95_PH2,K0,K0_Russie,MODULE_EE02,P1MO,P1UO,P84_Chine,P87_Chine,P8X,T9_MV,X81_Chine : CVM : Synthèse des implantations CVM ADAS V1","2016-11-30","Annulé","2016-12-30",null,"2016-11-30","OTD","2017-01-02","ACCEPTE_DEFAUT"]
["MCSH-4124-L-82322","AIT - MCSI","2015-01-14T13:07:17","CSAC",null,null,"OF_DOTE","X74E : CVM (X74E) : Pour Stade OCM VRS2 (C5)","2016-12-02","Annulé","2016-10-31",null,"2016-11-30","OTD","2016-09-19","ACCEPTE_DEFAUT"]
["MCSH-4124-L-113912","AIT - MCSI","2016-11-09T02:33:43","CSAC",null,null,"OF_CAL","X74E : CVM (X74E) : Calibration pour VRS2 (compatible C5)","2016-12-02","Annulé",null,null,"2016-11-30","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-6604-L-108385","AIT - MCSI","2016-06-01T05:16:47","CSAC",null,null,"OF_CAL","P1UO : RADAR GÉN3 (P1UO) : CALs EL0 (TMC5 selon planning du 20/01/16) D5.4","2016-12-19","Annulé",null,null,"2016-11-30","OTD","2016-12-16","FTR"]
["MCSH-8263-L-114379","EST - MCSI","2016-11-18T17:09:44","EACC",null,null,"OF_PIECE","P1UO : AVE (P1UO) : Officialisation d'une pièce","2017-01-06","Annulé",null,null,"2016-11-30","OTD","2016-12-01","FTR"]
["MCSH-7358-L-106695","EST - MCSI","2016-04-18T09:50:41","ELPS",null,null,"DO_FC_VRS","D34E : FEUX_AR : Fiches composants pour SDP VRS","2016-09-17","Annulé","2016-12-05","Manque donnée d'entrée","2016-12-01","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-3533-L-114370","AIT - MCSI","2016-11-18T11:31:31","CSAC",null,null,"DO_CESARE","P8X : CVM (P8) : P87 (lancement 01/2017): Mise à jour BE CVM tous niveaux (D5.2f et SW6x) suite à la màj CAL","2016-12-09","Annulé","2016-12-29",null,"2016-12-01","DR","2016-12-19","FTR"]
["MCSH-7953-L-114198","AIT - MCSI - NAC","2016-11-16T14:16:41","IVI",null,null,"OF_PIECE","MODULE_EE07 : NAC Wave 3 : Officialisation module HW D SW V4 projet A55P","2016-10-25","Annulé","2016-12-02",null,"2016-12-02","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-7065-L-113513","AIT - MCSI","2016-10-26T14:16:43","CSAC",null,null,"OF_PIECE","R83E : CVM (R83E) : Reconduction des nouvelles références C5 sur R83E (variantes 2 et 3)","2016-11-18","Annulé","2016-12-31",null,"2016-12-02","DR","2016-12-07","FTR"]
["MCSH-5267-L-114287","AIT - MCSI","2016-11-16T15:19:48","AURA",null,null,"OF_PIECE","B8_Mi_Vie : LECTEUR_CD_EXTERNE (SANS FACADE) : B81\r\nReconduction d'une pièce - Lecteur CD sans façade ECOTECH","2016-12-02","Annulé",null,null,"2016-12-02","DR","2016-11-30","FTR"]
["MCSH-8301-L-113176","AIT - MCSI","2016-10-17T02:14:40","CSAC",null,null,"OF_CAL","F3 : CVM (F3) : VRS1 (EUROPE): Calibration pour CVM VAEB SW6","2016-12-02","Annulé","2016-12-02",null,"2016-12-02","OTD","2016-12-05","FTR"]
["MCSH-6604-L-108386","AIT - MCSI","2016-06-01T05:18:09","CSAC",null,null,"DO_CESARE","P1UO : RADAR GÉN3 (P1UO) : Livraison BEs EL0 (TMC5 selon planning du 20/01/16) D5.4","2016-12-19","Annulé",null,null,"2016-12-02","OTD","2016-12-02","FTR"]
["MCSH-7358-L-106685","EST - MCSI","2016-04-18T09:50:41","ELPS",null,null,"SDF_PSDF_FNR","D34E : FEUX_AR : Plan de sûreté de fonctionnement du fournisseur. Attendu : AMDEC, AFI, AFE et ADD","2016-06-15","Annulé","2016-12-12","Evolution donnée d'entrée","2016-12-05","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7230-L-100761","AIT - MCSI","2015-12-22T14:58:43","CSAC",null,null,"DO_CESARE","R83_Chine : RADAR_GÉN4 (R83_Chine) : Création de référence/Mise à jour CESARE pour stade TI","2016-09-16","Annulé","2016-12-31","Retard fournisseur","2016-12-05","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-5267-L-88288","AIT - MCSI","2015-04-13T10:11:58","AURA",null,null,"OF_PIECE","MODULE_EE12 : LECTEUR_CD_EXTERNE (SANS FACADE) : Officialisation d'une pièce DAD","2016-09-30","Annulé",null,"Retard","2016-12-05","Retard",null,"ACCEPTE_DEFAUT"]
["MCSH-8301-L-100196","AIT - MCSI","2015-12-10T14:42:45","CSAC",null,null,"OF_DOTE","F3 : CVM (F3) : VRS1 (EUROPE):\r\nDOTE pour CVM VAEB","2016-11-18","Annulé","2016-11-30","Retard","2016-12-06","Retard",null,"ACCEPTE_DEFAUT"]
["MCSH-7311-L-77853","AIT - MCSI","2014-10-30T15:11:16","SWES",null,null,"ANI_TRI_PR","_QUALITE : COM2005_EV3 (Réactivité sans délai_DELPHI : pb son) : Tri des Pièces de Rechange","2016-11-30","Annulé","2016-12-06","Retard PSA","2016-12-06","OTD","2016-12-07","FTR"]
["MCSH-8563-L-111241","AIT - MCSI","2016-08-23T14:15:31","CSAC",null,null,"OF_DOTE","C84_Europe : CVM (C84E) : Pour Stade DFE TI (B2)","2016-11-30","Annulé","2016-12-09","Erreur Metier (RCD, Impl., Concept…)","2016-12-06","OTD","2016-12-14","FTR"]
["MCSH-3036-L-110521","AIT - MCSI","2016-07-29T08:42:47","CSAC",null,null,"SYN_ALTIS ","B751_3_4_MV,B78_mi_vie,B81_Chine_Fenêtre_VS,C84_Chine,G95_PH2,K0,MODULE_EE02,P1UO,P84_Chine,P87_Chine,P8X,T9_MV,X81_Chine : RADAR GÉN3 : Gestion Hebdomadaire Altis\r","2016-11-30","Annulé",null,null,"2016-12-06","Retard",null,"ACCEPTE_DEFAUT"]
["MCSH-8301-L-100193","AIT - MCSI","2015-12-10T14:42:45","CSAC",null,null,"DO_CESARE","F3 : CVM (F3) : Création de référence/Mise à jour CESARE pour mulet","2016-12-06","Annulé","2016-12-16",null,"2016-12-06","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-3533-L-113877","AIT - MCSI","2016-11-08T04:57:15","CSAC",null,null,"OF_CAL","P8X : CVM (P8) : P87 (lancement 01/2017): CAL tous niveaux (D5.2f + SW6d)","2016-12-09","Annulé",null,null,"2016-12-06","DR","2016-12-14","FTR"]
["MCSH-1658-L-110471","AIT - MCSI","2016-07-28T13:08:51","SWES",null,null,"ANI_MENSUELLE","MODULE_HAB10,_QUALITE,A9,A94,A94_Chine,A97,Ai94M,Ai9M,T9,T9_Chine,  : VCI DELPHI (A9-T9-B7x-B8-E3) : Trimestrielle FNR. En pièce jointe ODJ (1 semaine avant) + CR technique. Lien vers l'ODJ type : http://docinfogroupe.inetpsa.com/ead/doc/ref.00948_10_00977/v.vc/fiche. Lien vers le CR type : http://docinfo.inetpsa.com/ead00/doc/ref.00948_10_00984/v.vc/fic","2016-11-24","Annulé","2016-12-07","Diponibilté des interlocuteurs","2016-12-07","OTD","2016-12-07","FTR"]
["MCSH-1658-L-115439","AIT - MCSI","2016-12-07T10:21:28","SWES",null,null,"DO_BE_CESARE","MODULE_HAB10,_QUALITE,A9,A94,A94_Chine,A97,Ai94M,Ai9M,T9,T9_Chine,  : VCI DELPHI (A9-T9-B7x-B8-E3) : Création /Mise à jour BE CESARE. Livraison BE F3 =>REC VCI E3 (DELPHI)","2016-12-09","Annulé",null,null,"2016-12-07","DR","2016-12-12","FTR"]
["MCSH-8052-L-106722","EST - MCSI","2016-04-18T14:44:35","EACC",null,null,"RT_CDCI","D34E,P21,P21_DMOA,P23_DMOA,P24E : POMPES_LV_LP : Revue technique de CDCI","2016-12-09","Annulé","2016-11-25",null,"2016-12-07","OTD","2016-12-19","FTR"]
["MCSH-7066-L-109517","AIT - MCSI","2016-07-06T10:04:47","CSAC",null,null,"DO_CESARE","G95_PH2,MODULE_EE02 : CVM (G95 Ph2) : BE pour CVM niv2 D5.3","2016-12-10","En cours","2016-12-28",null,"2016-12-07","OTD","2016-12-14","FTR"]
["MCSH-4124-L-111854","AIT - MCSI","2016-09-08T14:26:26","CSAC",null,null,"DO_BE_CESARE","X74E : CVM (X74E) : Mise à jour et livraison BE CESARE pour VRS UT","2016-12-12","En cours",null,null,"2016-12-07","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-8246-L-104528","AIT - MCDV","2016-03-10","HDTC",null,null,"OF_PIECE","_TOUS : _TRAVAUX_CAO : création et officialisation de référence FNR support capteur oxyde azote amont pour EMP2 motorisation DV5R, et rattachement au FCT 9819665580","2016-04-22","En cours","2016-12-09","Erreur Metier (RCD, Impl., Concept…)","2016-12-08","OTD","2017-01-09","ACCEPTE_DEFAUT"]
["MCSH-8063-L-95691","EST - MCSI","2015-08-14T10:43:36","ELAC",null,null,"DO_ETAT_ACCEPT","R83E : CTP : Etat acceptation pour VRS1.","2016-10-28","En cours","2016-12-30","Manque donnée d'entrée","2016-12-09","OTD","2016-12-23","FTR"]
["MCSH-8064-L-95718","EST - MCSI","2015-08-14T13:43:01","ELAC",null,null,"DO_ETAT_ACCEPT","R83E : SONDE_POLLUTION (AQS) : Etat acceptation pour VRS1.","2016-10-28","En cours","2016-12-30","Manque donnée d'entrée","2016-12-09","OTD","2016-12-23","FTR"]
["MCSH-8077-L-95881","AIT - MCSI","2015-08-24T15:35:30","CSAC",null,null,"OF_DOTE","C84_Europe : RADAR_GÉN4 (C84_Export) : Pour Stade DFE TI","2016-10-28","En cours","2016-12-31","Retard du TOP offi","2016-12-09","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-6206-L-113692","EST - MCSI","2016-11-04T11:37:33","EACC",null,null,"DO_EDS","B618,B81,B8_Mi_Vie,MODULE_CPE09,W2_VS : RETRO_EXT : Renseigner OPHELIE EDS Tool pour le stade robuste","2016-11-18","En cours",null,null,"2016-12-09","NDR",null,"ACCEPTE_DEFAUT"]
["MCSH-8563-L-111238","AIT - MCSI","2016-08-23T14:15:31","CSAC",null,null,"OF_PIECE","C84_Europe : CVM (C84E) : DFNU/TI: reconduction CVM3 niveaux 2 & 4","2016-12-09","En cours",null,null,"2016-12-09","OTD","2016-12-14","FTR"]
["MCSH-8822-L-114179","AIT - MCSI","2016-11-15T19:03:09","AURA",null,null,"OF_PIECE","T93_Malaisie : LECTEUR_CD_EXTERNE : Reconduction d'une pièce, Lecteur CD sans façade ECOTECH","2016-12-09","En cours",null,null,"2016-12-09","DR","2017-01-04","FTR"]
["MCSH-7990-L-94692","AIT - MCSI","2015-07-22T13:17:14","CSAC",null,null,"DO_CESARE","P87_Chine : RADAR GÉN3 (P87C) : Livraison BE D5.4 EL2 (full braking)","2016-12-14","En cours",null,null,"2016-12-09","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-5893-L-115613","AIT - MCSI","2016-12-09T04:17:21","CSAC",null,null,"OF_CAL","P1MO : CVM (A88,P1MO) : P1MO: Calibrations CVM2 niv1 D5.3 et VAEB SW6d pour stades MVBns & MVBs","2016-12-16","En cours",null,null,"2016-12-09","DR","2016-12-14","FTR"]
["MCSH-5893-L-115614","AIT - MCSI","2016-12-09T04:22:15","CSAC",null,null,"OF_CAL","A88 : CVM (A88,P1MO) : A88: Calibrations CVM2 niv1 D5.3 et VAEB SW6d pour stade PPVV3 & MVBns","2016-12-16","En cours",null,null,"2016-12-09","DR","2016-12-14","FTR"]
["MCSH-5893-L-115616","AIT - MCSI","2016-12-09T04:30:42","CSAC",null,null,"DO_CESARE","P1MO : CVM (A88,P1MO) : P1MO (DàD/DàG): BE niv1 et VAEB à partir du stade MVBNs","2016-12-16","En cours",null,null,"2016-12-09","DR","2016-12-15","FTR"]
["MCSH-5893-L-115617","AIT - MCSI","2016-12-09T04:32:04","CSAC",null,null,"DO_CESARE","A88 : CVM (A88,P1MO) : A88 (DàD/DàG): BE niv1 et VAEB à partir du stade PPV3","2016-12-16","En cours",null,null,"2016-12-09","DR","2016-12-15","FTR"]
["MCSH-8246-L-108691","AIT - MCDV","2016-06-10","HDTC",null,null,"OF_PIECE","_TOUS : _TRAVAUX_CAO : Officialisation d'une pièce","2016-12-19","En cours",null,null,"2016-12-09","OTD","2017-01-10","ACCEPTE_DEFAUT"]
["MCSH-8557-L-109455","EST - MCSI","2016-07-04T16:48:24","HD2C",null,null,"VAL_ANA_RAPP_ESSAIS","MODULE_EE09 : MATTP (Sw1.6 (DMTLess)) : Analyse rapport d'essais B217130","2016-12-30","En cours",null,null,"2016-12-09","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-8557-L-109457","EST - MCSI","2016-07-04T16:52:28","HD2C",null,null,"VAL_ANA_RAPP_ESSAIS","MODULE_EE09 : MATTP (Sw1.6 (DMTLess)) : Analyse rapport d'essais B217120","2016-12-30","En cours",null,null,"2016-12-09","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-8007-L-115596","EST - MCSI","2016-12-09T11:58:49","HD2C",null,null,"OF_CAL","MODULE_EE09 : MATTC (SW3.0) : Officialisation d'une calibration \r\n MATT_c sw2.8 sur A94 chine Adaptation NAC/RCC ALTIS\r\n 6687229 CALE SW2.8)","2016-12-30","En cours",null,null,"2016-12-09","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-7344-L-93407","AIT - MCSI","2015-06-29T09:37:32","CSAC",null,null,"LIV_SW_CAL","D34E : CVM (D34€) : Calibration pour TI livrée par le FNR","2016-12-31","En cours","2016-12-31",null,"2016-12-09","OTD","2016-12-14","FTR"]
["MCSH-8717-L-109937","AIT - MCSI","2016-07-21T17:20:33","CSAC",null,null,"LIV_SW_CAL","X74_Chine : CVM (X74_Chine) : Calibration pour TI livrée par le FNR","2016-12-31","En cours","2016-12-31",null,"2016-12-09","OTD","2016-12-14","FTR"]
["MCSH-8563-L-111240","AIT - MCSI","2016-08-23T14:15:31","CSAC",null,null,"LIV_SW_CAL","C84_Europe,MODULE_EE02 : CVM (C84E) : Calibration pour TI livrée par le FNR","2016-12-31","En cours","2016-12-31",null,"2016-12-09","OTD","2016-12-14","FTR"]
["MCSH-7345-L-111333","AIT - MCSI","2016-08-25T11:17:03","CSAC",null,null,"LIV_SW_CAL","R83_Chine : CVM (R83C) : Calibration pour TI livrée par le FNR","2016-12-31","En cours","2016-12-31",null,"2016-12-09","OTD","2016-12-14","FTR"]
["MCSH-8481-L-103592","EST - MCSI","2016-02-18T17:03:44","ELAC",null,null,"DO_QIA","_DMTRless_ELAC : TDC_RF2 : Animation d'un QIA","2016-06-03","En cours","2016-12-10","Décalage projet","2016-12-10","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-8847-L-113440","EST - MCSI","2016-10-24T16:27:14","HD2C",null,null,"OF_PIECE","MODULE_EE09 : TNB (Tous types) : Officialisation d'une pièce Evolution Sw « clignotement témoins airbag » ","2016-12-21","En cours",null,null,"2016-12-10","OTD","2017-01-11","ACCEPTE_DEFAUT"]
["MCSH-8161-L-112196","EST - MCSI","2016-09-21T10:22:22","IDEV",null,null,"CAO_3D_FCT","MODULE_EE07 : SMEG+_I_V2 : 3D Fonctionnel PSA\r\nEcran seul 2 ISO pour l'APV ","2016-10-28","En cours",null,null,"2016-12-12","NDR",null,"ACCEPTE_DEFAUT"]
["MCSH-7953-L-114681","AIT - MCSI - NAC","2016-11-23T12:36:28","IVI",null,null,"OF_PIECE","R83E : NAC Wave 3 : Officialisation Rec NAC WAVE 3 pour projet R8","2016-12-02","En cours","2016-12-28",null,"2016-12-12","DR","2017-01-04","FTR"]
["MCSH-6206-L-107761","EST - MCSI","2016-05-13T17:17:35","EACC",null,null,"DO_FETE","B618,B81,B8_Mi_Vie,MODULE_CPE09,W2_VS : RETRO_EXT : FETE transmise au fournisseur:\r\nECOTECH reconduction de l'IHM SAM DPA développée dans le cadre de B618 sur W2 et B81","2016-05-31","En cours","2016-12-09",null,"2016-12-13","NDR",null,"ACCEPTE_DEFAUT"]
["MCSH-5891-L-114377","AIT - MCSI","2016-11-18T15:40:25","CSAC",null,null,"OF_CAL","B618 : CVM (B618) : F05/2017 - EL2: CAL VAEB SW6 (0,3g)","2016-12-14","En cours",null,null,"2016-12-14","DR","2016-12-15","FTR"]
["MCSH-1658-L-114150","AIT - MCSI","2016-11-15T11:47:01","SWES",null,null,"OF_PIECE","MODULE_HAB10 : VCI DELPHI (A9-T9-B7x-B8-E3) : Officialisation d'une pièce - MAJ plan VCI DELPHI (sup decli EQ)","2016-12-16","En cours",null,null,"2016-12-14","DR","2017-01-04","FTR"]
["MCSH-8140-L-110896","EST - MCSI","2016-08-04T08:22:43","ELAC",null,null,"DO_FC_VRS","B78,K9,P8X,R82E,R83E,T9_MV,X74E : RECHAUFF : Fiches composants pour SDP VRS","2016-12-16","En cours",null,null,"2016-12-14","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-1201-L-115679","EST - MCSI","2016-12-13T10:57:10","ECPC",null,null,"OF_PIECE","B9_Mi_Vie_2 : PUSH_LVE_AV : Officialisation (REC) 3D/2D Fonctionnel - Push LVE BITRON","2016-12-23","En cours",null,null,"2016-12-14","DR","2016-12-21","FTR"]
["MCSH-5849-L-72766","EST - MCSI","2014-06-27T23:33:02","ELPS",null,null,"VAL_ANA_RAPP_ESSAIS","X81_Chine : FEU_AV : Analyse CR Essais PV","2015-12-06","En cours","2016-01-08","Retard fournisseur","2016-12-15","Retard",null,"ACCEPTE_DEFAUT"]
["MCSH-7911-L-91025","AIT - MCSI","2015-05-06T13:54:05","CSAC",null,null,"DO_CESARE","D34E : RADAR_GÉN4 (D34E) : Création de référence/Mise à jour CESARE pour stade TI","2016-11-04","En cours","2017-01-06",null,"2016-12-15","Retard",null,"ACCEPTE_DEFAUT"]
["MCSH-7977-L-106656","EST - MCSI","2016-04-15T17:16:17","EACC",null,null,"DO_INC_CONCEPT","D34E,MODULE_CPE02,P21 : EVAV : Incontournables partie conception","2016-12-15","En cours","2016-12-16",null,"2016-12-15","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-5891-L-114378","AIT - MCSI","2016-11-18T15:40:38","CSAC",null,null,"DO_CESARE","B618 : CVM (B618) : F05/2017 - Flotte/EL2: BE VAEB SW6d (0,3g)","2016-12-15","En cours",null,null,"2016-12-15","DR","2016-12-16","FTR"]
["MCSH-3382-L-114299","AIT - MCSI","2016-11-17T09:59:58","CSAC",null,null,"DO_ETAT_ACCEPT","MODULE_EE02 : CVP (ADAS vague 1) : Réunion tripartite de détermination de l'état d'acceptation CVP Bosch 180°","2016-12-15","En cours",null,null,"2016-12-15","DR","2017-01-03","FTR"]
["MCSH-2916-L-107956","AIT - MCSI","2016-05-19T01:56:06","CSAC",null,null,"DO_PEPP","A55_PRO,A5X_F_05_16,B9_Mi_Vie_2_F11/2015,F3,MODULE_EE02 : LIDAR : Réactivité 120j Buée Lidar: PEPP Solde","2016-12-15","En cours",null,null,"2016-12-15","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-2509-L-106488","AIT - MCSI","2016-04-13T11:45:36","SWES",null,null,"VAL_ANA_INDIC","MODULE_HAB10,A58VS,Ai51M,B9,B9E,G9,T1_Iran,T3,T3_Iran,T61_Chine,T7,T7xA,T73,T7x_Mercosur,T73_Chine,T73_Malaisie,T73_Russie,T75,T76,T7H : COM2005_EV3 (Delphi : Suivi Vie Série) : Vérifier les engagements qualité du FNR et prioriser en fonction des têtes de pareto. Objectif en début d'année, bilan à mi et fin d'année.","2016-12-16","En cours",null,null,"2016-12-15","OTD","2017-01-09","RBA"]
["MCSH-6617-L-113519","AIT - MCSI","2016-10-26T15:20:51","CSAC",null,null,"DO_TDB","C84_Europe,D34E,K9,MODULE_EE02,P21,R82E,R83E,R83_Chine,X74E,X74_Chine,X83_Chine : CVM (CVM3 ADAS vague 2) : CVM3: Création d'un tableau de bord des reconductions","2016-12-16","En cours",null,null,"2016-12-15","OTD","2016-12-21","FTR"]
["MCSH-8246-L-115449","AIT - MCDV","2016-12-07","HDTC",null,null,"OF_PIECE","_TOUS : _TRAVAUX_CAO : Officialisation d'une pièce","2016-12-20","En cours",null,null,"2016-12-15","DR","2016-12-16","FTR"]
["MCSH-2984-L-115682","EST - MCSI","2016-12-13T11:53:42","ECPC",null,null,"OF_PIECE","B9_Mi_Vie_2 : PUSH_LVI_AR,PUSH_LVI_AV : Officialisation (REC) 3D/2D Fonctionnel - Push LVI BITRON","2016-12-23","En cours",null,null,"2016-12-15","DR","2016-12-21","FTR"]
["MCSH-5562-L-59835","EST - MCSI","2013-12-05T16:36:06","ELAC",null,null,"DO_PMR_PSA","B618,MODULE_HAB05 : GRPE_CLIM : Plan de Maîtrise des Risques organe PSA. Doit- être créé à partir du PMR GENERIQUE : Rédaction quand rg1 et contributeur quand rg2 ","2016-10-17","En cours","2016-12-16","Manque donnée d'entrée","2016-12-16","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7911-L-91027","AIT - MCSI","2015-05-06T13:54:05","CSAC",null,null,"OF_DOTE","D34E : RADAR_GÉN4 (D34E) : Pour Stade DFE TI (B2)","2016-11-04","En cours","2016-12-31","Erreur Metier (RCD, Impl., Concept…)","2016-12-16","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7065-L-111857","AIT - MCSI","2016-09-08T14:44:40","CSAC",null,null,"DO_BE_CESARE","R83E : CVM (R83E) : Mise à jour et livraison BE CESARE pour VRS DV","2016-11-18","En cours","2016-12-31","Manque donnée d'entrée","2016-12-16","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-3036-L-110522","AIT - MCSI","2016-07-29T08:42:47","CSAC",null,null,"SYN_ALTIS ","B751_3_4_MV,B78_mi_vie,B81_Chine_Fenêtre_VS,C84_Chine,G95_PH2,K0,MODULE_EE02,P1UO,P84_Chine,P87_Chine,P8X,T9_MV,X81_Chine : RADAR GÉN3 : Gestion Hebdomadaire Altis\r\n","2016-12-16","En cours",null,null,"2016-12-16","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-3036-L-110636","AIT - MCSI","2016-07-29T08:48:27","CSAC",null,null,"DO_CDCI_BILAN","B751_3_4_MV,B78_mi_vie,B81_Chine_Fenêtre_VS,C84_Chine,G95_PH2,K0,MODULE_EE02,P1UO,P84_Chine,P87_Chine,P8X,T9_MV,X81_Chine : RADAR GÉN3 : Synthèses d'avancement de toutes les implantation Radar / Fichier de pilotage interne et avec fournisseur.","2016-12-16","En cours",null,null,"2016-12-16","OTD","2016-12-19","FTR"]
["MCSH-5616-L-113615","EST - MCSI","2016-10-27T18:02:15","ELAC",null,null,"DO_DIVERS","_METIER : LDA / référentiel technique CLIM : Création Template rétroplanning RFQ","2016-12-16","En cours",null,null,"2016-12-16","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-8140-L-114189","EST - MCSI","2016-11-16T11:08:07","ELAC",null,null,"RT_PASS_DEV_MET","B78,K9,P8X,R82E,R83E,T9_MV,X74E : RECHAUFF : Revue de passation du développement vers le métier en fin de développement","2016-12-16","En cours",null,null,"2016-12-16","DR","2016-12-23","FTR"]
["MCSH-3533-L-114196","AIT - MCSI","2016-11-16T13:53:46","CSAC",null,null,"OF_CAL","P8X : CVM (P8) : P87 (F05/2017): CAL CVM niv1 & 2 D5.3","2016-12-16","En cours","2016-12-28",null,"2016-12-16","DR","2016-12-16","FTR"]
["MCSH-5267-L-114289","AIT - MCSI","2016-11-16T15:22:55","AURA",null,null,"OF_PIECE","B7_Mi_Vie : LECTEUR_CD_EXTERNE (SANS FACADE) : B73 AMLAT - Reconduction d'une pièce ECOTECH","2016-12-16","En cours",null,null,"2016-12-16","DR","2017-01-04","FTR"]
["MCSH-3533-L-114371","AIT - MCSI","2016-11-18T11:31:36","CSAC",null,null,"DO_CESARE","P8X : CVM (P8) : P87 (F05/2017): Mise à jour BE CVM niv1 et 2 D5.3 suite à la màj CAL","2016-12-16","En cours","2016-12-27",null,"2016-12-16","DR","2016-12-19","FTR"]
["MCSH-3039-L-115252","AIT - MCSI","2016-12-02T15:50:17","CSAC",null,null,"SYN_ALTIS ","A88,A88_Chine,B618,B751_3_4_MV,B78_mi_vie,B81_Chine_Fenêtre_VS,C84_Chine,F3,G95_PH2,K0,K0_Russie,MODULE_EE02,P1MO,P1UO,P84_Chine,P87_Chine,P8X,T9_MV,X81_Chine : CVM : Synthèse Altis","2016-12-16","En cours",null,null,"2016-12-16","DR","2016-12-21","FTR"]
["MCSH-5891-L-115716","AIT - MCSI","2016-12-14T01:53:20","CSAC",null,null,"OF_CAL","B618 : CVM (B618) : F05/2017 - Flotte: CAL VAEB SW6d (0,9g)","2016-12-28","En cours",null,null,"2016-12-16","DR","2016-12-19","FTR"]
["MCSH-7154-L-115276","AIT - MCSI","2016-12-05T15:16:04","CSAC",null,null,"OF_CAL","P1UO : CVM (P1UO) : EL1: mise à jour CAL VAEB SW6d","2017-01-06","En cours",null,null,"2016-12-16","DR","2016-12-16","FTR"]
["MCSH-8161-L-109070","EST - MCSI","2016-06-22T16:52:40","IDEV",null,null,"OF_PIECE","MODULE_EE07 : SMEG+_I_V2 : Officialisation d'un écran SMEG en 2ISO pour l'APV","2016-10-07","En cours",null,null,"2016-12-19","Retard","2017-01-04","FTR"]
["MCSH-7990-L-94693","AIT - MCSI","2015-07-22T13:17:14","CSAC",null,null,"OF_CAL","P87_Chine : RADAR GÉN3 (P87C) : CAL D5.4 EL2 (full braking)","2016-12-14","En cours","2016-12-23","Abscence valideur ou expert","2016-12-19","OTD","2016-12-19","FTR"]
["MCSH-2509-L-106489","AIT - MCSI","2016-04-13T11:45:36","SWES",null,null,"ANI_MENSUELLE","MODULE_HAB10,A58VS,Ai51M,B9,B9E,G9,T1_Iran,T3,T3_Iran,T61_Chine,T7,T7xA,T73,T7x_Mercosur,T73_Chine,T73_Malaisie,T73_Russie,T75,T76,T7H : COM2005_EV3 (Delphi : Suivi Vie Série) : Trimestrielle FNR. En pièce jointe ODJ (1 semaine avant) + CR technique. Lien vers l'ODJ type : http://docinfogroupe.inetpsa.com/ead/doc/ref.00948_10_00977/v.vc/fiche. Lien vers le CR type : http://docinfo.inetpsa.com/ead00/doc/ref.00948_10_00984/v.vc/fic","2016-12-16","En cours","2016-12-19",null,"2016-12-19","OTD","2017-01-09","FTR"]
["MCSH-8246-L-108692","AIT - MCDV","2016-06-10","HDTC",null,null,"OF_PIECE","_TOUS : _TRAVAUX_CAO : création d'une réf de capteur vitesse roue AR","2016-12-19","En cours",null,null,"2016-12-19","OTD","2017-03-03","RR"]
["MCSH-8007-L-115821","EST - MCSI","2016-12-19T13:38:12","HD2C",null,null,"DO_BE_CESARE","MODULE_EE09 : MATTC (SW3.0) : Création /Mise à jour BE CESARE\r\n\r\nBE MATT_C 2010 SW2.8/2.9 sur A94 Chine mi-vie","2016-12-19","En cours",null,null,"2016-12-19","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-8007-L-115822","EST - MCSI","2016-12-19T01:38:40","HD2C",null,null,"DO_BE_CESARE","MODULE_EE09 : MATTC (SW3.0) : Création /Mise à jour BE CESARE\r\n\r\nBE MATT_C 2010 SW2.8/2.9 sur W2 Chine ","2016-12-19","En cours",null,null,"2016-12-19","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-5891-L-115717","AIT - MCSI","2016-12-14T13:57:33","CSAC",null,null,"DO_CESARE","B618 : CVM (B618) : F05/2017 - Flotte/EL2: BE VAEB SW6d (0,9g)","2016-12-30","En cours",null,null,"2016-12-19","DR","2016-12-19","FTR"]
["MCSH-7154-L-115277","AIT - MCSI","2016-12-05T15:16:30","CSAC",null,null,"DO_CESARE","P1UO : CVM (P1UO) : EL1: BE VAEB SW6d avec nouvelle CAL","2017-01-06","En cours",null,null,"2016-12-19","DR","2016-12-19","FTR"]
["MCSH-8007-L-115597","EST - MCSI","2016-12-09T12:07:52","HD2C",null,null,"OF_DOTE","MODULE_EE09 : MATTC (SW3.0) : Officialisation d'une DOTE\r\n MATT_c sw2.8 sur W2 chine Adaptation NAC/RCC ALTIS\r\n 6687229 CALE SW2.8)","2017-01-13","En cours",null,null,"2016-12-19","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-8007-L-115598","EST - MCSI","2016-12-09T12:08:41","HD2C",null,null,"OF_DOTE","MODULE_EE09 : MATTC (SW3.0) : Officialisation de DOTE\r\n\r\n\r\n Officialisation d'une DOTE MATT_c sw2.9 sur A94 chine Adaptation NAC/RCC ALTIS\r\n 6687229 CALE SW2.8)","2017-01-13","En cours",null,null,"2016-12-19","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-8304-L-99946","EST - MCSI","2015-12-07T16:49:28","ELPS",null,null,"DO_EDS","A9X_F_05_17 : PROJ (_STT) : Renseigner OPHELIE EDS Tool pour le stade consolidé","2016-09-30","En cours","2016-12-26","Retard fournisseur","2016-12-20","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-8246-L-114151","AIT - MCDV","2016-11-15","HDTC",null,null,"OF_PIECE","_TOUS : _TRAVAUX_CAO : Officialisation d'une pièce","2016-12-20","En cours",null,null,"2016-12-20","DR","2016-12-21","FTR"]
["MCSH-3855-L-85793","EST - MCSI","2015-03-04T14:12:12","EACC",null,null,"ANI_MENSUELLE","K0,MODULE_CE_MDT : CMD_PBAR : CR point technique mensuel avec le fournisseur\r\n(idem ARIS)","2016-09-30","En cours",null,null,"2016-12-22","Retard",null,"ACCEPTE_DEFAUT"]
["MCSH-8246-L-113730","AIT - MCDV","2016-11-07","HDTC",null,null,"OF_PIECE","_TOUS : _TRAVAUX_CAO : Officialisation d'une pièce, Plan FNR pour la phase EI avec PCP confirmé(AR Non Signé B751B753)","2016-12-20","En cours","2016-12-27","Erreur Metier (RCD, Impl., Concept…)","2016-12-22","OTD","2017-01-23","ACCEPTE_DEFAUT"]
["MCSH-8246-L-113731","AIT - MCDV","2016-11-07","HDTC",null,null,"OF_PIECE","_TOUS : _TRAVAUX_CAO : Officialisation d'une pièce, Plan FNR pour la phase EI avec PCP confirmé (AR Signé B751B753)","2016-12-20","En cours","2016-12-27","Erreur Metier (RCD, Impl., Concept…)","2016-12-22","OTD","2017-01-04","FTR"]
["MCSH-8246-L-113732","AIT - MCDV","2016-11-07","HDTC",null,null,"OF_PIECE","_TOUS : _TRAVAUX_CAO : Officialisation d'une pièce Plan FNR pour la phase EI avec PCP confirmé (AR Non Signé B81CB754) ","2016-12-20","En cours","2016-12-27","Erreur Metier (RCD, Impl., Concept…)","2016-12-22","OTD","2017-01-04","FTR"]
["MCSH-8246-L-113733","AIT - MCDV","2016-11-07","HDTC",null,null,"OF_PIECE","_TOUS : _TRAVAUX_CAO : Officialisation d'une pièce, Plan FNR pour la phase EI avec PCP confirmé (AR Signé B81CB754)","2016-12-20","En cours","2016-12-27","Erreur Metier (RCD, Impl., Concept…)","2016-12-22","OTD","2017-01-04","FTR"]
["MCSH-8718-L-109977","EST - MCSI","2016-07-22T14:04:52","ELAC",null,null,"DO_DIVERS","_ELAC : AQI  : Maj au format 2016 de 4 synthèses projet format 2015","2016-12-22","En cours",null,null,"2016-12-22","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7186-L-92246","EST - MCSI","2015-06-08T09:28:39","EACC",null,null,"VAL_ANA_PT_FNR","B618,R82E,R83E : POMPES_LV_LP : Analyse Plan De Test FNR","2016-01-29","En cours","2016-12-23","Retard fournisseur","2016-12-23","OTD","2017-01-04","FTR"]
["MCSH-8481-L-103590","EST - MCSI","2016-02-18T17:03:44","ELAC",null,null,"DO_PEPP","_DMTRless_ELAC : TDC_RF2 : PEPP 2 Industrialisation","2016-09-30","En cours","2016-12-23","Décalage projet","2016-12-23","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-2509-L-106481","AIT - MCSI","2016-04-13T11:45:36","SWES",null,null,"DO_ALTIS","MODULE_HAB10,A58VS,Ai51M,B9,B9E,G9,T1_Iran,T3,T3_Iran,T61_Chine,T7,T7xA,T73,T7x_Mercosur,T73_Chine,T73_Malaisie,T73_Russie,T75,T76,T7H : COM2005_EV3 (Delphi : Suivi Vie Série) : Date cible fin d'année et MAJ date plannifiée bi-mensuelle - ALTIS EE","2016-12-16","En cours","2016-12-23","Evolution donnée d'entrée","2016-12-23","OTD","2017-01-17","NOT FTR"]
["MCSH-7006-L-114964","AIT - MCSI","2016-12-02T11:35:33","AURA",null,null,"OF_PIECE","B73_Russie : LECTEUR_CD_EXTERNE : Officialisation d'une pièce - ECOTECH","2016-12-23","En cours",null,null,"2016-12-23","DR","2016-12-07","FTR"]
["MCSH-6822-L-104708","EST - MCSI","2016-03-16T15:46:56","EACC",null,null,"RT_HW","D34E,MODULE_CE_MDT,P21,X74_Chine : LVEAP,LVE : Revue Technique de Conception Préliminaire Electronique","2016-12-23","En cours","2016-12-23",null,"2016-12-23","OTD","2017-01-06","RR"]
["MCSH-1658-L-110468","AIT - MCSI","2016-07-28T13:08:51","SWES",null,null,"DO_ALTIS","MODULE_HAB10,_QUALITE,A9,A94,A94_Chine,A97,Ai94M,Ai9M,T9,T9_Chine,  : VCI DELPHI (A9-T9-B7x-B8-E3) : ALTIS EE\r\nDate cible fin d'année et MAJ date plannifiée bi-mensuelle","2016-12-23","En cours",null,null,"2016-12-23","OTD","2017-01-17","FTR"]
["MCSH-1727-L-110480","AIT - MCSI","2016-07-28T13:09:41","SWES",null,null,"DO_ALTIS","MODULE_HAB10,_QUALITE,G95,K0,M44_Chine,T7xA,T9_Chine,W2_VS : VCI MARQUARDT (W2-K0) : ALTIS QUALITE\r\nDate cible fin d'année et MAJ date plannifiée bi-mensuelle","2016-12-23","En cours",null,null,"2016-12-23","OTD","2017-01-17","FTR"]
["MCSH-6867-L-89685","EST - MCSI","2015-04-22T16:39:50","ELPS",null,null,"RI_CONTRAINTES","K9 : PROJ : Revue technique d'interface HW avec BSLE et CA2E","2017-01-20","En cours","2016-12-31",null,"2016-12-27","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-6867-L-89668","EST - MCSI","2015-04-22T16:39:50","ELPS",null,null,"RT_STD","K9 : PROJ : Avec le Fournisseur - Vérif indice STD","2015-08-31","En cours","2016-12-31","Décalage projet","2016-12-29","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-7987-L-105805","EST - MCSI","2016-04-01T11:31:03","ELPS",null,null,"RT_BILAN_MECA","D34E : FEU_AV : Revue Technique de bilan de Conception Mécanique","2016-09-07","En cours","2017-01-02","Retard fournisseur","2016-12-29","OTD","2017-01-05","FTR"]
["MCSH-6867-L-99707","EST - MCSI","2015-11-30T08:44:09","ELPS",null,null,"DO_EDS","K9 : PROJ : Renseigner OPHELIE EDS Tool pour le stade robuste","2016-12-31","En cours",null,null,"2016-12-29","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-6867-L-89671","EST - MCSI","2015-04-22T16:39:50","ELPS",null,null,"DO_FC_VRS","K9 : PROJ : Fiches composants pour SDP VRS","2017-01-14","En cours",null,null,"2016-12-29","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-8106-L-98739","EST - MCSI","2015-11-09T07:44:17","ELAC",null,null,"DO_PRESENTATION","_VS : CDE_PULSEUR : Présentation VALEO","2015-11-09","En cours","2016-12-30",null,"2016-12-30","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-6641-L-80521","EST - MCSI","2014-12-15T22:43:47","ELPS",null,null,"DO_INC_CONCEPT","P1UO : FEUX_AR : Incontournables partie conception","2016-01-19","En cours","2017-01-16","Retard fournisseur","2016-12-30","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-8482-L-103586","EST - MCSI","2016-02-18T16:58:49","ELAC",null,null,"VAL_ANA_PV_FNR","_DMTRless_ELAC : TDC_RFTA_CH/RF  : Analyse du planning de validation fournisseur","2016-03-30","En cours","2016-12-30",null,"2016-12-30","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-8481-L-103588","EST - MCSI","2016-02-18T17:03:44","ELAC",null,null,"DO_ALTIS","_DMTRless_ELAC : TDC_RF2 : Mise à jour ALTIS (EE ou Qualité)","2016-06-15","En cours","2016-12-30","Retard fournisseur","2016-12-30","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-5751-L-80315","EST - MCSI","2014-12-15T16:46:12","ELAC",null,null,"VAL_ALTIS","P8X : TDC AR : Réunion de suivi des défauts D5 : prise en compte par le FNR ou par le métier spécificateur","2016-06-17","En cours","2016-12-30","Retard fournisseur","2016-12-30","OTD","2017-01-20","FTR"]
["MCSH-8798-L-113269","AIT - MCSI","2016-10-20T15:02:49","CSAC",null,null,"DO_CDCI_BILAN","P21 : VISIO_PARK (P21 E) : Bilan des retours des CDCI","2016-12-28","En cours",null,null,"2016-12-30","OTD","2017-01-03","FTR"]
["MCSH-8140-L-105222","EST - MCSI","2016-03-23T16:04:47","ELAC",null,null,"DO_MAT_CONF","B78,K9,P8X,R82E,R83E,T9_MV,X74E : RECHAUFF : Matrice de conformité Diag","2016-12-30","En cours",null,null,"2016-12-30","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-4127-L-85620","EST - MCSI","2015-03-02T03:55:21","EACC",null,null,"DO_EDS","C84_Europe,MODULE_CPE09,P1UO,P8X,X74E : RETRO_EXT : Renseigner OPHELIE EDS Tool pour P1UO","2017-01-06","En cours","2016-12-30",null,"2016-12-30","OTD",null,"ACCEPTE_DEFAUT"]
["MCSH-5616-L-115893","EST - MCSI","2016-12-22T09:51:47","ELAC",null,null,"DO_DIVERS","_METIER : LDA / référentiel technique CLIM : Tableau de bord mise en projet","2016-12-31","En cours",null,null,"2016-12-31","DR",null,"ACCEPTE_DEFAUT"]
["MCSH-8735-L-115895","EST - MCSI","2016-12-22T09:54:24","ELAC",null,null,"DO_DIVERS","A9x_Iran,M33_Iran_Full_Speed : SONDE_PRESSION : Mise à jour de la MSE (matrice d'exigences) associées à la dernière version de STO","2016-12-31","En cours",null,null,"2016-12-31","DR",null,"ACCEPTE_DEFAUT"]

{"sheet":"Livraison","index":1,"n_rows":1,"n_cols":21,"rows_kept":1,"cut":false,"hidden":false,"merged":[]}
["Reference","Opportunité","Date \nCréation","ENTITE","CONSULTANT","user name","CLE","DESCRIPTION","Date \nCible","Charge estimé (j)","Charge consommé","Status","Date fin de plan d'action","Justificatif du retard","Date de livraison","Timming","Date du retour","Retour \nQualité","QG1","QG2","Description"]

{"sheet":"TB","index":2,"n_rows":43,"n_cols":14,"rows_kept":43,"cut":false,"hidden":false,"merged":[]}
[]
[]
[null,"DR","NDR","OTD","Retard",null,null,null,null,null,"DR","NDR","OTD","Retard"]
["Janvier",33,21,23,21,null,null,null,null,"AURA",12,23,8,10]
["Février",23,12,21,21,null,null,null,null,"CSAC",32,12,11,8]
["Mars",21,12,12,33,null,null,null,null,"EACC",34,7,9,12]
["Avril",41,21,32,43,null,null,null,null,"ECHP",32,12,11,8]
["Mai",22,32,12,23,null,null,null,null,"ECPC",7,12,12,9]
["Juin",32,23,21,23,null,null,null,null,"EEMS",9,5,14,8]
["Juillet",20,44,34,21,null,null,null,null,"ELAC",7,7,9,5]
["Août",25,33,21,22,null,null,null,null,"ELPS",3,2,4,6]
["Septembre",21,23,12,42,null,null,null,null,"HD2C",13,8,9,3]
["Octobre",4,33,21,32,null,null,null,null,"HDTC",16,9,12,0]
["Novembre",12,23,12,32,null,null,null,null,"IDEV",23,9,9,9]
["Décembre",34,22,32,19,null,null,null,null,"IVI",34,34,43,23]
[null,null,null,null,null,null,null,null,null,"SWES",21,34,21,12]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
["Attente Go",30]
["Planifié",43]
["En cours",56]
["Plan d'action",65]
["Terminé",34]
["Annulé",23]

{"sheet":"KPI","index":3,"n_rows":5,"n_cols":4,"rows_kept":5,"cut":false,"hidden":false,"merged":[]}
[]
[]
[]
[]
[null,"Key performance indicator","FTR","OTD"]