{"text_format":"1","workbook":"xlsx","n_sheets":4,"sheets":["Feuille de route","Listing Avions","Listes","Listing CPB"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":0,"defined_names":6,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Feuille de route","index":0,"n_rows":18,"n_cols":14,"rows_kept":18,"cut":false,"hidden":false,"merged":[[14,9,14,11],[2,5,2,6],[7,12,7,13],[8,12,8,13],[11,9,11,11],[12,9,12,11],[13,9,13,11],[2,12,2,13],[3,12,3,13],[4,12,4,13],[5,12,5,13],[6,12,6,13],[17,1,17,13],[10,8,10,13],[10,1,10,6],[1,2,1,6],[1,9,1,13],[11,2,11,4],[12,2,12,4],[3,5,3,6],[4,5,4,6],[5,5,5,6],[6,5,6,6],[16,1,16,13],[7,5,7,6],[8,5,8,6],[13,2,13,4],[14,2,14,4]]}
[]
[null,7992,"Visites Client",null,null,null,null,null,8244,"Visites Client"]
[null,"Item","Description","Statut","Date","Observation",null,null,"Item","Description","Statut","Date","Observation"]
[null,"3.10","Présentation C65",{"$f":"VLOOKUP(B2,Tableau6[],5,FALSE)","v":"Fait Wp"},{"$f":"VLOOKUP(B2,Tableau6[],6,FALSE)","v":"2017-11-06"},{"$f":"VLOOKUP(B2,Tableau6[],7,FALSE)","v":"-"},null,null,"3.10","Présentation C65",{"$f":"VLOOKUP(I2,Tableau6[],5,FALSE)","v":"Fait P25"},{"$f":"VLOOKUP(I2,Tableau6[],6,FALSE)","v":"2018-03-14"},{"$f":"VLOOKUP(I2,Tableau6[],7,FALSE)","v":"-"}]
[null,"3.19","Présentation C34",{"$f":"VLOOKUP(B2,Tableau6[],8,FALSE)","v":"Fait P25"},{"$f":"VLOOKUP(B2,Tableau6[],9,FALSE)","v":"2017-10-23"},{"$f":"VLOOKUP(B2,Tableau6[],10,FALSE)","v":"-"},null,null,"3.19","Présentation C34",{"$f":"VLOOKUP(I2,Tableau6[],8,FALSE)","v":"Fait P25"},{"$f":"VLOOKUP(I2,Tableau6[],9,FALSE)","v":"2018-03-13"},{"$f":"VLOOKUP(I2,Tableau6[],10,FALSE)","v":"-"}]
[null,"3.24","Présentation C24",{"$f":"VLOOKUP(B2,Tableau6[],11,FALSE)","v":"Fait P25"},{"$f":"VLOOKUP(B2,Tableau6[],12,FALSE)","v":"2017-10-23"},{"$f":"VLOOKUP(B2,Tableau6[],13,FALSE)","v":"-"},null,null,"3.24","Présentation C24",{"$f":"VLOOKUP(I2,Tableau6[],11,FALSE)","v":"Fait P25"},{"$f":"VLOOKUP(I2,Tableau6[],12,FALSE)","v":"2018-03-13"},{"$f":"VLOOKUP(I2,Tableau6[],13,FALSE)","v":"-"}]
[null,"3.25","Présentation Final Soute 2",{"$f":"VLOOKUP(B2,Tableau6[],14,FALSE)","v":"Fait WP"},{"$f":"VLOOKUP(B2,Tableau6[],15,FALSE)","v":"2017-11-07"},{"$f":"VLOOKUP(B2,Tableau6[],16,FALSE)","v":"-"},null,null,"3.25","Présentation Final Soute 2",{"$f":"VLOOKUP(I2,Tableau6[],14,FALSE)","v":"A Faire"},{"$f":"VLOOKUP(I2,Tableau6[],15,FALSE)","v":"-"},{"$f":"VLOOKUP(I2,Tableau6[],16,FALSE)","v":"Prévue le 27/03/2018"}]
[null,"3.26","Présentation Final Soute 1",{"$f":"VLOOKUP(B2,Tableau6[],17,FALSE)","v":"Fait WP"},{"$f":"VLOOKUP(B2,Tableau6[],18,FALSE)","v":"2017-11-07"},{"$f":"VLOOKUP(B2,Tableau6[],19,FALSE)","v":"-"},null,null,"3.26","Présentation Final Soute 1",{"$f":"VLOOKUP(I2,Tableau6[],17,FALSE)","v":"Fait P25"},{"$f":"VLOOKUP(I2,Tableau6[],18,FALSE)","v":"2018-03-13"},{"$f":"VLOOKUP(I2,Tableau6[],19,FALSE)","v":"-"}]
[null,"3.27","Présentation Final Cabine",{"$f":"VLOOKUP(B2,Tableau6[],20,FALSE)","v":"Fait WP"},{"$f":"VLOOKUP(B2,Tableau6[],21,FALSE)","v":"2017-11-08"},{"$f":"VLOOKUP(B2,Tableau6[],22,FALSE)","v":"-"},null,null,"3.27","Présentation Final Cabine",{"$f":"VLOOKUP(I2,Tableau6[],20,FALSE)","v":"Fait P25"},{"$f":"VLOOKUP(I2,Tableau6[],21,FALSE)","v":"2018-03-13"},{"$f":"VLOOKUP(I2,Tableau6[],22,FALSE)","v":"-"}]
[]
[null,"CPB",null,null,null,null,null,null,"CPB"]
[null,"N°","Description",null,null,"Statut","Stamp",null,"N°","Description",null,null,"Statut","Stamp"]
[null,{"$f":"VLOOKUP(B2,Tableau62[],2,FALSE)","v":"-"},{"$f":"VLOOKUP(B2,Tableau62[],3,FALSE)","v":"-"},null,null,{"$f":"VLOOKUP(B2,Tableau62[],4,FALSE)","v":"-"},{"$f":"VLOOKUP(B2,Tableau62[],5,FALSE)","v":"-"},null,{"$f":"VLOOKUP(I2,Tableau62[],2,FALSE)","v":"-"},{"$f":"VLOOKUP(I2,Tableau62[],3,FALSE)","v":"-"},null,null,{"$f":"VLOOKUP(I2,Tableau62[],4,FALSE)","v":"-"},{"$f":"VLOOKUP(I2,Tableau62[],5,FALSE)","v":"-"}]
[null,{"$f":"VLOOKUP(B2,Tableau62[],6,FALSE)","v":"-"},{"$f":"VLOOKUP(B2,Tableau62[],7,FALSE)","v":"-"},null,null,{"$f":"VLOOKUP(B2,Tableau62[],8,FALSE)","v":"-"},{"$f":"VLOOKUP(B2,Tableau62[],9,FALSE)","v":"-"},null,{"$f":"VLOOKUP(I2,Tableau62[],6,FALSE)","v":"-"},{"$f":"VLOOKUP(I2,Tableau62[],7,FALSE)","v":"-"},null,null,{"$f":"VLOOKUP(I2,Tableau62[],8,FALSE)","v":"-"},{"$f":"VLOOKUP(I2,Tableau62[],9,FALSE)","v":"-"}]
[null,{"$f":"VLOOKUP(B2,Tableau62[],10,FALSE)","v":"-"},{"$f":"VLOOKUP(B2,Tableau62[],11,FALSE)","v":"-"},null,null,{"$f":"VLOOKUP(B2,Tableau62[],12,FALSE)","v":"-"},{"$f":"VLOOKUP(B2,Tableau62[],13,FALSE)","v":"-"},null,{"$f":"VLOOKUP(I2,Tableau62[],10,FALSE)","v":"-"},{"$f":"VLOOKUP(I2,Tableau62[],11,FALSE)","v":"-"},null,null,{"$f":"VLOOKUP(I2,Tableau62[],12,FALSE)","v":"-"},{"$f":"VLOOKUP(I2,Tableau62[],13,FALSE)","v":"-"}]
[]
[null,"Commentaire"]
[null,"MD1 : MSN 7992 Présent en WP pour MC7."]

{"sheet":"Listing Avions","index":1,"n_rows":9,"n_cols":22,"rows_kept":9,"cut":false,"hidden":false,"merged":[[0,6,1,21],[3,20,3,21],[3,5,3,6],[3,14,3,15],[3,17,3,18],[2,0,4,0],[2,1,4,1],[2,2,4,2],[2,3,4,3],[2,4,2,21],[3,11,3,12],[3,8,3,9]]}
[null,null,null,null,null,null,"MSN WP 320 Cabine"]
[]
["MSN","Poste","Entrée","Sortie","Visites Client"]
[null,null,null,null,"3.10","Présentation C65",null,"3.19","Présentation C34",null,"3.24 ","Présentation C24",null,"3.25 ","Final Soute 2",null,"3.26  ","Final Soute 1",null,"3.27 ","Final Cabine"]
[null,null,null,null,"Statut","Date","Observations","Statut","Date","Observations","Statut","Date","Observations","Statut","Date","Observations","Statut","Date","Observations","Statut","Date","Observations"]
["MSN","Poste","Entrée","Sortie","3.10 Statut","3.10 Date","3.10 Observations","3.19 Statut","3.19 Date","3.19 Observations","3.24 Statut","3.24 Date","3.24 Observations","3.25 Statut","3.25 Date","3.25 Observations","3.26 Statut","3.26 Date","3.26 Observations","3.27 Statut","3.27 Date","3.27 Observations"]
["-","-","-","-","-","-","-","-","-","-","-","-","-","-","-","-","-","-","-","-","-","-"]
[7992,"P25A","2018-03-23","2018-03-26","Fait Wp","2017-11-06","-","Fait P25","2017-10-23","-","Fait P25","2017-10-23","-","Fait WP","2017-11-07","-","Fait WP","2017-11-07","-","Fait WP","2017-11-08","-"]
[8244,"P25B","2018-03-26","2018-03-27","Fait P25","2018-03-14","-","Fait P25","2018-03-13","-","Fait P25","2018-03-13","-","A Faire","-","Prévue le 27/03/2018","Fait P25","2018-03-13","-","Fait P25","2018-03-13","-"]

{"sheet":"Listes","index":2,"n_rows":7,"n_cols":7,"rows_kept":7,"cut":false,"hidden":true,"merged":[]}
[]
[]
[null,null,"Statut",null,"Poste",null,"Statut2"]
[null,null,"Fait P25",null,"P25A",null,"Fait"]
[null,null,"Fait WP",null,"P25B",null,"A Faire"]
[null,null,"A Faire",null,"P25C"]
[null,null,null,null,"P25D"]

{"sheet":"Listing CPB","index":3,"n_rows":7,"n_cols":13,"rows_kept":7,"cut":false,"hidden":false,"merged":[[0,1,1,12]]}
[null,"Liste CPB"]
[]
["MSN","N°","Description","Statut","Stamp","N°","Description","Statut","Stamp","N°","Description","Statut","Stamp"]
["MSN","N°","Description","Statut","Colonne1","N°2","Description3","Statut4","Colonne15","N°3","Description4","Statut5","Colonne16"]
["-","-","-","-","-","-","-","-","-","-","-","-","-"]
[7992,"-","-","-","-","-","-","-","-","-","-","-","-"]
[8244,"-","-","-","-","-","-","-","-","-","-","-","-"]