## Actions followup
ID | Topic | Priority | Description | Status | Owner | Due Date | Initial Due Date | Closure date | Followed in | Originated from
A_001 | Project Management | Medium | Add TSW to March | In progress | AA | 2019-11-18
A_002 | Contract | High | Get quotation from b | To do | AA | 2019-11-25
A_003 | Contract | High | Get NDA AAA | Completed | BB | 2019-11-15 |  | 2019-11-16

## Param
Status | Priority | Date du jour
To do | High | 2019-11-17
In progress | Medium
Completed | Low
On hold
Cancelled