{"text_format":"1","workbook":"xlsx","n_sheets":4,"sheets":["Base de données à saisir","Rétroplanning","Données auto","Chronologie des tâches"],"not_rendered":{"charts":3,"images":0,"macros":1,"external_links":0,"defined_names":9,"comments":0,"pivot_tables":4},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Base de données à saisir","index":0,"n_rows":35,"n_cols":6,"rows_kept":35,"cut":false,"hidden":false,"merged":[]}
[null,null," "," "]
[null,null,null,null," "]
[]
["Action","Tâches à effectuer","Service","Responsable","Début tâche","Fin tâche"]
["ACTION 1","Tâche 1 ","Service A","Hélène","2021-03-11","2021-04-13"]
["ACTION 1","Tâche 2","Service A","Hélène","2021-03-15","2021-03-19"]
["ACTION 1","Tâche 3","Service A","Pascal","2021-03-15","2021-03-22"]
["ACTION 1","Tâche 4  ","Service A","Hélène","2021-03-18","2021-03-29"]
["ACTION 1","Tâche 5","Service A","Hélène","2021-03-30","2021-04-09"]
["ACTION 1","Tâche 6","Service A","Hélène","2021-03-31","2021-04-07"]
["ACTION 1","Tâche 7","Service A","Hélène","2021-03-31","2021-04-07"]
["ACTION 2","Tâche 8","Service B","Philippe","2021-02-12","2021-02-22"]
["ACTION 2","Tâche 9","Service B","Philippe","2021-04-01","2021-04-26"]
["ACTION 2","Tâche 10","Service B","Charlotte","2021-04-19","2021-04-30"]
["ACTION 3","Tâche 11","Service B","Philippe","2021-02-12","2021-02-26"]
["ACTION 3","Tâche 12","Service C","Samir","2021-04-01","2021-04-30"]
["ACTION 3","Tâche 13","Service C","Karine","2021-05-03","2021-05-03"]
["ACTION 4","Tâche 14 ","Service B","Philippe","2021-04-01","2021-04-30"]
["ACTION 4","Tâche 15","Service D","Olivier","2021-05-03","2021-05-03"]
["ACTION 4","Tâche 16","Service E","Pierre","2021-05-03","2021-05-03"]
["ACTION 4","Tâche 17","Service F","Béatrice","2021-05-06","2021-05-12"]
["ACTION 5","Tâche 18","Service B","Philippe","2021-02-12","2021-03-05"]
["ACTION 5","Tâche 19","Service G","Paula","2021-04-01","2021-04-30"]
["ACTION 5","Tâche 20","Service G","Paula","2021-04-01","2021-04-30"]
["ACTION 5","Tâche 21","Service B","Philippe","2021-03-08","2021-03-12"]
["ACTION 5","Tâche 22","Service G","Paula","2021-05-17","2021-05-21"]
["ACTION 5","Tâche 23","Service G","Paula","2021-05-25","2021-06-30"]
["ACTION 5","Tâche 24","Service G","Paula","2021-05-17","2021-07-09"]
["ACTION 5","Tâche 25","Service G","Paula","2021-06-18","2021-06-23"]
["ACTION 5","Tâche 26","Service G","Paula","2021-06-18","2021-07-06"]
["ACTION 5","Tâche 27","Service B","Philippe","2021-03-08","2021-05-24"]
["ACTION 5","Tâche 28","Service C","Samir","2021-06-17","2021-06-28"]
["ACTION 6","Tâche 29","Service H","Sylvian","2021-05-18","2021-06-30"]
["ACTION 6","Tâche 30","Service H","Sylvian","2021-06-15","2021-06-30"]
["ACTION 6","Tâche 31","Service H","Sylvian","2021-06-16","2021-07-09"]

{"sheet":"Rétroplanning","index":1,"n_rows":44,"n_cols":376,"rows_kept":44,"cut":false,"hidden":true,"merged":[[34,0,36,0],[37,0,39,0],[40,0,42,0],[43,0,43,5],[12,2,18,2],[22,2,23,2],[26,2,30,2],[34,2,36,2],[37,2,40,2],[41,2,42,2],[12,3,17,3],[22,3,23,3],[26,3,30,3],[34,3,36,3],[37,3,38,3],[14,4,15,4],[12,0,18,0],[19,0,22,0],[23,0,33,0],[29,4,30,4],[0,0,0,2],[10,333,10,363],[10,364,10,375],[10,180,10,210],[10,10,10,26],[10,302,10,332],[10,211,10,240],[10,241,10,271],[10,272,10,301],[10,27,10,57],[10,58,10,87],[10,88,10,118],[10,119,10,148],[10,149,10,179]]}
[{"$f":"'Base de données à saisir'!#REF!","v":{"$error":"#REF!"}}]
["Date de démarrage du projet :",null,null,null,null,null,null,null,null,null,null,null,0,null,null,null,null,{"$f":"TEXT(MIN(F13:F994),\"J-MMM-AA\")&\" au \"&TEXT(MAX(G13:G994),\"J-MMM-AA\")","v":"22-févr-21 au 0-janv-00"}]
[{"$f":"MIN(F13:F994)","v":"2021-02-22"}]
["Date de clôture du projet :"]
[{"$f":"MAX(G13:G994)","v":"00:00:00"}]
[]
[]
["DATE DU JOUR :",{"$f":"TODAY()","v":"2021-09-10"},{"$f":"TODAY()","v":"2021-09-10"}]
[]
[]
[null,null,null,null,null,null,null,null,null,null,"2021-02-12",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2021-03-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2021-04-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2021-05-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2021-06-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2021-07-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2021-08-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2021-09-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2021-10-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2021-11-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2021-12-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2022-01-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2022-02-01"]
["Action","Tâches à effectuer","Service","Responsable","Début tâche","Fin tâche",null,null,null,null,{"$f":"$A$3+M2","v":"2021-02-22"},{"$f":"K12+1","v":"2021-02-23"},{"$f":"L12+1","v":"2021-02-24"},"2021-02-25","2021-02-26","2021-02-27","2021-02-28","2021-03-01","2021-03-02","2021-03-03","2021-03-04","2021-03-05","2021-03-06","2021-03-07","2021-03-08","2021-03-09","2021-03-10","2021-03-11","2021-03-12","2021-03-13","2021-03-14","2021-03-15","2021-03-16","2021-03-17","2021-03-18","2021-03-19","2021-03-20","2021-03-21","2021-03-22","2021-03-23","2021-03-24","2021-03-25","2021-03-26","2021-03-27","2021-03-28","2021-03-29","2021-03-30","2021-03-31","2021-04-01","2021-04-02","2021-04-03","2021-04-04","2021-04-05","2021-04-06","2021-04-07","2021-04-08","2021-04-09","2021-04-10","2021-04-11","2021-04-12","2021-04-13","2021-04-14","2021-04-15","2021-04-16","2021-04-17","2021-04-18","2021-04-19","2021-04-20","2021-04-21","2021-04-22","2021-04-23","2021-04-24","2021-04-25","2021-04-26","2021-04-27","2021-04-28",{"$f":"BX12+1","v":"2021-04-29"},"2021-04-30","2021-05-01","2021-05-02","2021-05-03","2021-05-04","2021-05-05","2021-05-06","2021-05-07","2021-05-08","2021-05-09","2021-05-10","2021-05-11","2021-05-12","2021-05-13","2021-05-14","2021-05-15","2021-05-16","2021-05-17","2021-05-18","2021-05-19","2021-05-20","2021-05-21","2021-05-22","2021-05-23","2021-05-24","2021-05-25","2021-05-26","2021-05-27","2021-05-28","2021-05-29","2021-05-30","2021-05-31","2021-06-01","2021-06-02","2021-06-03","2021-06-04","2021-06-05","2021-06-06","2021-06-07","2021-06-08","2021-06-09","2021-06-10","2021-06-11","2021-06-12","2021-06-13","2021-06-14","2021-06-15","2021-06-16","2021-06-17","2021-06-18","2021-06-19","2021-06-20","2021-06-21","2021-06-22","2021-06-23","2021-06-24","2021-06-25","2021-06-26","2021-06-27","2021-06-28","2021-06-29","2021-06-30","2021-07-01",{"$f":"EJ12+1","v":"2021-07-02"},"2021-07-03","2021-07-04","2021-07-05","2021-07-06","2021-07-07","2021-07-08","2021-07-09","2021-07-10","2021-07-11","2021-07-12","2021-07-13","2021-07-14","2021-07-15","2021-07-16","2021-07-17","2021-07-18","2021-07-19","2021-07-20","2021-07-21","2021-07-22","2021-07-23","2021-07-24","2021-07-25","2021-07-26","2021-07-27","2021-07-28","2021-07-29","2021-07-30","2021-07-31","2021-08-01","2021-08-02","2021-08-03","2021-08-04","2021-08-05","2021-08-06","2021-08-07","2021-08-08","2021-08-09","2021-08-10","2021-08-11","2021-08-12","2021-08-13","2021-08-14","2021-08-15","2021-08-16","2021-08-17","2021-08-18","2021-08-19","2021-08-20","2021-08-21","2021-08-22","2021-08-23","2021-08-24","2021-08-25","2021-08-26","2021-08-27","2021-08-28","2021-08-29","2021-08-30","2021-08-31","2021-09-01","2021-09-02","2021-09-03",{"$f":"GV12+1","v":"2021-09-04"},"2021-09-05","2021-09-06","2021-09-07","2021-09-08","2021-09-09","2021-09-10","2021-09-11","2021-09-12","2021-09-13","2021-09-14","2021-09-15","2021-09-16","2021-09-17","2021-09-18","2021-09-19","2021-09-20","2021-09-21","2021-09-22","2021-09-23","2021-09-24","2021-09-25","2021-09-26","2021-09-27","2021-09-28","2021-09-29","2021-09-30","2021-10-01","2021-10-02","2021-10-03","2021-10-04","2021-10-05","2021-10-06","2021-10-07","2021-10-08","2021-10-09","2021-10-10","2021-10-11","2021-10-12","2021-10-13","2021-10-14","2021-10-15","2021-10-16","2021-10-17","2021-10-18","2021-10-19","2021-10-20","2021-10-21","2021-10-22","2021-10-23","2021-10-24","2021-10-25","2021-10-26","2021-10-27","2021-10-28","2021-10-29","2021-10-30","2021-10-31","2021-11-01","2021-11-02","2021-11-03","2021-11-04","2021-11-05","2021-11-06",{"$f":"JH12+1","v":"2021-11-07"},"2021-11-08","2021-11-09","2021-11-10","2021-11-11","2021-11-12","2021-11-13","2021-11-14","2021-11-15","2021-11-16","2021-11-17","2021-11-18","2021-11-19","2021-11-20","2021-11-21","2021-11-22","2021-11-23","2021-11-24","2021-11-25","2021-11-26","2021-11-27","2021-11-28","2021-11-29","2021-11-30","2021-12-01","2021-12-02","2021-12-03","2021-12-04","2021-12-05","2021-12-06","2021-12-07","2021-12-08","2021-12-09","2021-12-10","2021-12-11","2021-12-12","2021-12-13","2021-12-14","2021-12-15","2021-12-16","2021-12-17","2021-12-18","2021-12-19","2021-12-20","2021-12-21","2021-12-22","2021-12-23","2021-12-24","2021-12-25","2021-12-26","2021-12-27","2021-12-28","2021-12-29","2021-12-30","2021-12-31","2022-01-01","2022-01-02","2022-01-03","2022-01-04","2022-01-05","2022-01-06","2022-01-07","2022-01-08","2022-01-09",{"$f":"LT12+1","v":"2022-01-10"},"2022-01-11","2022-01-12","2022-01-13","2022-01-14","2022-01-15","2022-01-16","2022-01-17","2022-01-18","2022-01-19","2022-01-20","2022-01-21","2022-01-22","2022-01-23","2022-01-24","2022-01-25","2022-01-26","2022-01-27","2022-01-28","2022-01-29","2022-01-30","2022-01-31","2022-02-01","2022-02-02","2022-02-03","2022-02-04","2022-02-05","2022-02-06","2022-02-07","2022-02-08","2022-02-09","2022-02-10","2022-02-11","2022-02-12","2022-02-13","2022-02-14","2022-02-15","2022-02-16","2022-02-17","2022-02-18","2022-02-19","2022-02-20","2022-02-21","2022-02-22"]
["ACTION 1","Tâche 2","Service A","Hélène","2021-03-15","2021-03-19"]
[null,"Tâche 5","Service A","Hélène","2021-03-30","2021-04-09"]
[null,"Tâche 6","Service A","Hélène","2021-03-31","2021-04-07"]
[null,"Tâche 7","Service A","Hélène","2021-03-31","2021-04-07"]
[null,"Tâche 1 ","Service A","Hélène","2021-03-11","2021-04-13"]
[null,"Tâche 4  ","Service A","Hélène","2021-03-18","2021-03-29"]
[null,"Tâche 3","Service A","Pascal","2021-03-15","2021-03-22"]
["ACTION 4","Tâche 16","Service E","Pierre","2021-05-03","2021-05-03"]
[null,"Tâche 17","Service F","Béatrice","2021-05-06","2021-05-12"]
[null,"Tâche 15","Service D","Olivier","2021-05-03","2021-05-03"]
[null,"Tâche 14 ","Service B","Philippe","2021-04-01","2021-04-30"]
["ACTION 5","Tâche 18","Service B","Philippe","2021-02-12","2021-03-05"]
[null,"Tâche 20","Service G","Paula","2021-04-01","2021-04-30"]
[null,"Tâche 21","Service B","Philippe","2021-03-08","2021-03-12"]
[null,"Tâche 22","Service G","Paula","2021-05-17","2021-05-21"]
[null,"Tâche 23","Service G","Paula","2021-05-25","2021-06-30"]
[null,"Tâche 24","Service G","Paula","2021-05-17","2021-07-09"]
[null,"Tâche 25","Service G","Paula","2021-06-18","2021-06-23"]
[null,"Tâche 26","Service G","Paula","2021-06-18","2021-07-06"]
[null,"Tâche 27","Service B","Philippe","2021-03-08","2021-05-24"]
[null,"Tâche 28","Service C","Samir","2021-06-17","2021-06-28"]
[null,"Tâche 19","Service G","Paula","2021-04-01","2021-04-30"]
["ACTION 6","Tâche 29","Service H","Sylvian","2021-05-18","2021-06-30"]
[null,"Tâche 30","Service H","Sylvian","2021-06-15","2021-06-30"]
[null,"Tâche 31","Service H","Sylvian","2021-06-16","2021-07-09"]
["ACTION 2","Tâche 8","Service B","Philippe","2021-02-12","2021-02-22"]
[null,"Tâche 9","Service B","Philippe","2021-04-01","2021-04-26"]
[null,"Tâche 10","Service B","Charlotte","2021-04-19","2021-04-30"]
["ACTION 3","Tâche 11","Service B","Philippe","2021-02-12","2021-02-26"]
[null,"Tâche 12","Service C","Samir","2021-04-01","2021-04-30"]
[null,"Tâche 13","Service C","Karine","2021-05-03","2021-05-03"]
["Total général"]

{"sheet":"Données auto","index":2,"n_rows":23,"n_cols":13,"rows_kept":23,"cut":false,"hidden":true,"merged":[[0,0,0,8]]}
["NE RIEN MODIFIER SUR CETTE FEUILLE"]
[]
[]
["Tâche(s) non commencée(s)",{"$f":"COUNTIF(Rétroplanning!I13:I994,\"=\"&0)","v":0},null,null,null,null,"Jours terminés",{"$f":"GETPIVOTDATA(\" Jours achevés\",$D$4)/GETPIVOTDATA(\"Somme de Durée tâche\",$D$4)","v":{"$error":"#REF!"}},null,null,null,null,1]
["En progression",{"$f":"COUNTIFS(Rétroplanning!J13:J994,\"<>\"&0,Rétroplanning!J13:J994,\"<\"&1)","v":0},null,null,null,null,"Jours restants",{"$f":"1-H4","v":{"$error":"#REF!"}},null,null,null,null,2]
["Terminée(s)",{"$f":"COUNTIF(Rétroplanning!J13:J994,\"=\"&1)","v":0},null,null,null,null,null,null,null,null,null,null,3]
["Restants",{"$f":"B4+B5","v":0},null,null,null,null,null,null,null,null,null,null,4]
["Total",{"$f":"B7+B6","v":0},null,null,null,null,null,null,null,null,null,null,5]
[null,null,null,null,null,null,null,null,null,null,null,null,6]
[null,null,null,null,null,null,null,null,null,null,null,null,7]
[null,null,null,null,null,null,null,null,null,null,null,null,8]
[null,null,null,null,null,null,null,null,null,null,null,null,9]
[null,null,null,null,null,null,null,null,null,null,null,null,10]
[null,null,null,null,null,null,null,null,null,null,null,null,11]
[null,null,null,null,null,null,null,null,null,null,null,null,12]
[null,null,null,null,null,null,null,null,null,null,null,null,13]
[null,null,null,null,null,null,null,null,null,null,null,null,14]
[null,null,null,null,null,null,null,null,null,null,null,null,15]
[null,null,null,null,null,null,null,null,null,null,null,null,16]
[null,null,null,null,null,null,null,null,null,null,null,null,17]
[null,null,null,null,null,null,null,null,null,null,null,null,18]
[null,null,null,null,null,null,null,null,null,null,null,null,19]
[null,null,null,null,null,null,null,null,null,null,null,null,20]

{"sheet":"Chronologie des tâches","index":3,"n_rows":40,"n_cols":32,"rows_kept":40,"cut":false,"hidden":false,"merged":[[8,23,8,24],[8,30,8,31],[9,11,9,12],[9,13,9,16],[9,19,9,21],[9,25,9,27],[36,11,36,12],[36,13,36,17],[36,19,36,21],[36,23,36,24],[36,30,36,31],[37,11,37,12],[37,13,37,16],[37,19,37,21],[37,25,37,27],[36,1,36,3],[36,4,36,5],[36,7,36,8],[34,1,34,3],[34,4,34,12],[34,13,34,18],[34,19,34,26],[34,27,34,31],[8,1,8,3],[8,4,8,5],[8,7,8,8],[8,11,8,12],[8,13,8,17],[8,19,8,21],[6,1,6,3],[6,4,6,12],[6,13,6,18],[6,19,6,26],[6,27,6,31]]}
[]
[]
[]
[]
[]
[]
["DEBUT","2021-02-12",null,null,"2021-03-08",null,null,null,null,null,null,null,null,"2021-04-01",null,null,null,null,null,"2021-05-03",null,null,null,null,null,null,null,"2021-06-15"]
[null,"Début tâche","Fin tâche","Tâches à effectuer","Responsable"]
["DEBUT","2021-02-12",null,null,"2021-03-08",null,"2021-03-11","2021-03-15",null,"2021-03-18","2021-03-30","2021-03-31",null,"2021-04-01",null,null,null,null,"2021-04-19","2021-05-03",null,null,"2021-05-06","2021-05-17",null,"2021-05-18","2021-05-25","2021-06-15","2021-06-16","2021-06-17","2021-06-18"]
["FIN","2021-03-05","2021-02-22","2021-02-26","2021-03-12","2021-05-24","2021-04-13","2021-03-19","2021-03-22","2021-03-29","2021-04-09","2021-04-07",null,"2021-04-30",null,null,null,"2021-04-26","2021-04-30","2021-05-03",null,null,"2021-05-12","2021-05-21","2021-07-09","2021-06-30","2021-06-30","2021-06-30","2021-07-09","2021-06-28","2021-06-23","2021-07-06"]
[null,"Tâche 18","Tâche 8","Tâche 11","Tâche 21","Tâche 27","Tâche 1 ","Tâche 2","Tâche 3","Tâche 4  ","Tâche 5","Tâche 6","Tâche 7","Tâche 20","Tâche 12","Tâche 19","Tâche 14 ","Tâche 9","Tâche 10","Tâche 16","Tâche 13","Tâche 15","Tâche 17","Tâche 22","Tâche 24","Tâche 29","Tâche 23","Tâche 30","Tâche 31","Tâche 28","Tâche 25","Tâche 26"]
["RESPONSABLE","Philippe","Philippe","Philippe","Philippe","Philippe","Hélène","Hélène","Pascal","Hélène","Hélène","Hélène","Hélène","Paula","Samir","Paula","Philippe","Philippe","Charlotte","Pierre","Karine","Olivier","Béatrice","Paula","Paula","Sylvian","Paula","Sylvian","Sylvian","Samir","Paula","Paula"]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
["VOICI LE TYPE D'AFFICHAGE QUE JE SOUHAITERAIS AVOIR  EN AUTOMATIQUE PEU IMPORTE L'ATTRIBUTION DES COULEURS"]
[]
[]
["DEBUT","2021-02-12",null,null,"2021-03-08",null,null,null,null,null,null,null,null,"2021-04-01",null,null,null,null,null,"2021-05-03",null,null,null,null,null,null,null,"2021-06-15"]
[null,"Début tâche","Fin tâche","Tâches à effectuer","Responsable"]
["DEBUT","2021-02-12",null,null,"2021-03-08",null,"2021-03-11","2021-03-15",null,"2021-03-18","2021-03-30","2021-03-31",null,"2021-04-01",null,null,null,null,"2021-04-19","2021-05-03",null,null,"2021-05-06","2021-05-17",null,"2021-05-18","2021-05-25","2021-06-15","2021-06-16","2021-06-17","2021-06-18"]
["FIN","2021-03-05","2021-02-22","2021-02-26","2021-03-12","2021-05-24","2021-04-13","2021-03-19","2021-03-22","2021-03-29","2021-04-09","2021-04-07",null,"2021-04-30",null,null,null,"2021-04-26","2021-04-30","2021-05-03",null,null,"2021-05-12","2021-05-21","2021-07-09","2021-06-30","2021-06-30","2021-06-30","2021-07-09","2021-06-28","2021-06-23","2021-07-06"]
[null,"Tâche 18","Tâche 8","Tâche 11","Tâche 21","Tâche 27","Tâche 1 ","Tâche 2","Tâche 3","Tâche 4  ","Tâche 5","Tâche 6","Tâche 7","Tâche 20","Tâche 12","Tâche 19","Tâche 14 ","Tâche 9","Tâche 10","Tâche 16","Tâche 13","Tâche 15","Tâche 17","Tâche 22","Tâche 24","Tâche 29","Tâche 23","Tâche 30","Tâche 31","Tâche 28","Tâche 25","Tâche 26"]
["RESPONSABLE","Philippe","Philippe","Philippe","Philippe","Philippe","Hélène","Hélène","Pascal","Hélène","Hélène","Hélène","Hélène","Paula","Samir","Paula","Philippe","Philippe","Charlotte","Pierre","Karine","Olivier","Béatrice","Paula","Paula","Sylvian","Paula","Sylvian","Sylvian","Samir","Paula","Paula"]